## Overview
Story ID | 24.10
Title | Order Cancellation
Epic | Order Management
Build Status | Scope locked 2026-07-03 (Step-1 gate complete). 10 to implement here, 1 covered elsewhere (24.10-j -> 24.9), 0 out of scope. Release model: all remaining OM stories ship together.
To implement here | 10
Summary | Cancel endpoint as one transaction (status flip, PT cascade + next_retry_at null, NEW 24.10-k inventory releaseForOrder, audit in-tx); ALL refund work delegated to 24.9 (composition call; ledger from day one); former Partial/Blocked rows upgraded to Deliverable-sequenced; 24.10-g producer corrected to 24.8 -> 24.7; register empty.
Covered Elsewhere | 1 (24.10-j -> 24.9)
Total requirements | 11
Deliverable | 10
Partial | 0
Blocked | 0
Not Deliverable | 0
Out of Scope | 0
Implementation | Not started — scope locked 2026-07-03 (gate complete)
Impl Branch | —
Impl Commits | —
PR | —

## Requirements
Req ID | Requirement | Verdict | Build Focus | Delivered By | Reason (exists vs to-build / gap) | Code Evidence | Dependency | Build Consolidation (reuse / delivered-by) | Story Wording (verbatim, from Confluence) | Confluence | Impl Status (2026-07-03)
24.10-a | A 'Cancel Order' button at the top of the Order Details page that opens a confirmation modal requiring explicit confirmation before cancelling (full vs partial refund options; partial captures a manual amount). | Deliverable | Implement here |  | CONFIRMED 2026-07-03. Orders module SHIPPED (24.1-24.4 + 24.14) -> POST /api/v1/orders/:id/cancel is an ADDITIVE route (stale 'no order module' reason dropped). Zero cancel endpoints anywhere. Seed orders.cancel + @Permissions() per shipped block. Modal/button = FE; explicit POST is the confirmation contract. | admin orders.controller.ts:41 (GET / :50, notes :94/:131); grep cancel in src/admin/orders = zero; permission.seeder.ts:1229-1248 |  | [C2 build-once-reuse] OWNER — build here (POST /api/v1/orders/:id/cancel — one $transaction: refund c…); reused by other stories in this cluster. | A "Cancel Order" button shall be at the top of the Order Details page. On click, a confirmation modal shall ask the user to confirm the cancellation. Cancellation Options Cancel Entire Order with Full Refund Cancel Entire Order with Partial Refund For partial refund, the user shall enter the refund amount manually, validated not to exceed the total amount paid against the order. | Open §Order Management → Story 24.10 | Gate locked 2026-07-03: Deliverable (additive route).
24.10-b | Backend endpoint to cancel the entire order and set Order.status to Cancelled, enforced server-side. | Deliverable | Implement here |  | CONFIRMED 2026-07-03. Guarded update in the cancel $transaction: where {id, order_type product, deleted_at null, status not canceled} -> canceled (guard doubles as idempotency). Two proven write-paths to copy. Exhibitor free: canceled already in NON_PAYABLE. | admin schema:421-430 (canceled :427), Order.status :1547; ext webhook.service.ts:1172-1175 & :2998-3001; exh orders.helpers.ts:34 |  | [C2 build-once-reuse] OWNER — build here (POST /api/v1/orders/:id/cancel — one $transaction: refund c…); reused by other stories in this cluster. | Order status shall change to "Cancelled". / Cancellation effects and refund processing shall be enforced on the backend, and logged. | Open §Order Management → Story 24.10 | Gate locked 2026-07-03: Deliverable.
24.10-c | On cancellation, all unpaid or pending payment plans (installments) become inactive/cancelled. | Deliverable | Implement here |  | CONFIRMED 2026-07-03, shape agreed: updateMany widened to status IN (scheduled, processing, failed) -> canceled, ALWAYS next_retry_at: null (retry cron keys off it; skipping resurrects canceled installments), + failure_message. Three proven patterns. | admin schema:496; ext webhook.service.ts:1176-1187, :2901-2911, :3002-3012; worker payment-charge.service.ts:62-78 (cron predicates) |  | [C2 build-once-reuse] OWNER — build here (POST /api/v1/orders/:id/cancel — one $transaction: refund c…); reused by other stories in this cluster. | All unpaid or pending payment plans shall automatically become inactive or cancelled. | Open §Order Management → Story 24.10 | Gate locked 2026-07-03: Deliverable; widened where-clause + next_retry_at null agreed.
24.10-d | Already-paid payment plans are retained as historical records, marked appropriately based on refund activity. | Deliverable | Implement here |  | CONFIRMED 2026-07-03 - upgraded Partial -> Deliverable (sequenced on 24.9, same release). Retention free (no PT delete path). Marking fully specified by 24.9's locked design: Refund ledger rows per refunded installment; PT flips refunded only on FULL refund (amount-aware handler, 24.9 D2); OrderStatus.refunded derived. | ext webhook.service.ts:3038-3060; 24.9 doc D1/D2 locked 2026-07-03; no PT delete path (grep) | 24.9 (SBE-1133) Refund ledger + statuses — same release, sequenced (build order 24.9 -> 24.10 -> 24.11 -> 24.8 -> 24.7 -> 24.6 -> 24.15) |  | Already-paid payment plans shall remain as historical records, marked appropriately based on refund activity. | Open §Order Management → Story 24.10 | Gate locked 2026-07-03: upgraded Partial -> Deliverable (sequenced on 24.9).
24.10-e | Partial refund: admin enters the refund amount manually, validated not to exceed the total amount paid against the order (refund cap). | Deliverable | Implement here |  | CONFIRMED 2026-07-03. DTO refund_type full¦partial + amount (iff partial); Decimal validation 0 < amount <= paid_amount - sum(prior Refund rows) — ledger real from day one. Cap check CENTRALIZED in 24.9's refund service (cancel calls it). paid_amount gross per 24.9 D3. | admin schema:1578; ext webhook.service.ts:2112/:2123 (sole bumper); admin orders.helpers.ts:33 | Cap check delegated to 24.9 service (same release) | [C2 build-once-reuse] OWNER — build here (POST /api/v1/orders/:id/cancel — one $transaction: refund c…); reused by other stories in this cluster. | For partial refund, the user shall enter the refund amount manually, validated not to exceed the total amount paid against the order. / A partial refund shall not exceed the total amount paid against the order. | Open §Order Management → Story 24.10 | Gate locked 2026-07-03: Deliverable; cap delegated to 24.9.
24.10-f | Where Stripe payments exist, process Stripe refunds (full or partial) as part of cancellation. | Deliverable | Implement here |  | CONFIRMED 2026-07-03 - upgraded Partial -> Deliverable (sequenced on 24.9). 24.10 hand-rolls NO Stripe call: cancel tx invokes 24.9's order-level composition (one wrapper call per charge, newest-first, refund_failed per leg). Confluence itself says 'Refer User Story Refund Management'. Offline leg = 24.10-g. | grep refunds.create = zero all repos; admin schema:1567/:2083; 24.9 doc D1 (composition) | 24.9 (SBE-1133) wrapper + composition — same release, sequenced (build order 24.9 -> 24.10 -> 24.11 -> 24.8 -> 24.7 -> 24.6 -> 24.15) | [C2 build-once-reuse] OWNER — build here (POST /api/v1/orders/:id/cancel — one $transaction: refund c…); reused by other stories in this cluster. ¦ [C7 build-once-reuse] Mostly delivered by building 24.9 (external-api-service POST /v1/refunds (internal) — stripe.r…). Residual: the cancel endpoint's Stripe-refund leg CALLS this same wrapper; residual is only wiring the call into the cancel transaction. Partial-refund amount accounting stays Blocked (24.10-h). | If Stripe payments exist, the system can process Stripe refunds where applicable. | Open §Order Management → Story 24.10 | Gate locked 2026-07-03: upgraded Partial -> Deliverable (sequenced on 24.9).
24.10-g | For offline or manual payments, refunds shall be marked manually. | Deliverable | Implement here |  | CONFIRMED 2026-07-03 - upgraded Blocked -> Deliverable (sequenced). D2 RESOLVED: true gate is the PRODUCER (offline-paid installments representable), owned by 24.8-f/-a (relax NOT-NULL stripe cols, add payment_type) -> 24.7 (manual lifecycle) — both same release. Marking mechanism = 24.9's Manual-refund path. 24.10 builds nothing for this row. | admin schema:2084-2085 (NOT-NULL stripe cols), :2094 (idempotency_key), :503-511 (PaymentTransactionSource 5 values incl. admin_change_plan :508, all Stripe-driven) | Producer: 24.8 (SBE-1132) -> 24.7 (SBE-1131); marking: 24.9 manual path — all same release |  | For offline or manual payments, refunds shall be marked manually. | Open §Order Management → Story 24.10 | Gate locked 2026-07-03: upgraded Blocked -> Deliverable (sequenced); D2 resolved (24.8 -> 24.7).
24.10-h | Record/track refund activity (refund records, refunded amount, partial-refund accounting) so order/plan state reflects refunds. | Deliverable | Implement here |  | CONFIRMED 2026-07-03 - upgraded Blocked -> Deliverable (sequenced on 24.9's migration, landing first inside 24.9's build). The row IS 24.9's Refund ledger, consumed: cancel writes ledger rows through 24.9's service in-tx. NO 24.10-owned schema work. (Synthesized decomposition of 24.10-d — analysis row, kept.) | grep model Refund / refunded_amount / refund_failed = zero @0ac2769 (pre-24.9); 24.9 doc migration-first | 24.9 (SBE-1133) migration — same release, sequenced (build order 24.9 -> 24.10 -> 24.11 -> 24.8 -> 24.7 -> 24.6 -> 24.15) |  | Already-paid payment plans shall remain as historical records, marked appropriately based on refund activity. | Open §Order Management → Story 24.10 | Gate locked 2026-07-03: upgraded Blocked -> Deliverable (sequenced on 24.9 migration).
24.10-i | Cancellation effects and refund processing are enforced on the backend and logged. | Deliverable | Implement here |  | CONFIRMED 2026-07-03. Enforcement = the cancel $transaction. Logging = one AdminAuditService.record() in-tx (note: refund_type/amount/reason). M1 CLOSED: the AC's 24.14 cross-reference satisfied by the shipped audit-log read (GET /api/v1/logs/admin-audit?entity_type=order&entity_id=:id). NO auto-write to internal_notes (audit log is the ledger); Order.notes untouched (reserved idempotency-key store). BA flag only if stricter intent. | admin admin-audit.service.ts:30/:50; schema:2210 (order entity), :2227; checkout.service.ts:329 precedent; shipped audit read (24.14 cluster) |  | [C2 build-once-reuse] OWNER — build here (POST /api/v1/orders/:id/cancel — one $transaction: refund c…); reused by other stories in this cluster. ¦ [C8 build-once-reuse] Mostly delivered by building 24.1 (The existing JWT + roles guard + @Permissions(...) decorato…). Residual: none beyond applying the guard on cancel (audit-log half of 24.10-i is C9). ¦ [C9 build-once-reuse] Mostly delivered by building 24.14 (AdminAuditService.record()/recordMany() with entity_type='o…). Residual: one record() call inside the cancel transaction (guard half of 24.10-i is C8). | Cancellation effects and refund processing shall be enforced on the backend, and logged. | Open §Order Management → Story 24.10 | Gate locked 2026-07-03: Deliverable; M1 interpretation recorded.
24.10-j | Operational flexibility: instead of cancelling the whole order, continue managing refunds individually at the payment-plan level. | Covered elsewhere | Covered elsewhere | 24.9 (SBE-1133) | CONFIRMED 2026-07-03. This IS 24.9's per-installment primitive (POST /orders/:id/refunds with payment_transaction_id). Clause states the two flows coexist: 24.10 = quick composition, 24.9 = individual flow. Nothing built here. | 24.9 doc D1 (per-installment primitive) | — delivered by 24.9, same release |  | Client Services may use the Cancel Entire Order action for quick handling or continue managing refunds individually at the payment-plan level. | Open §Order Management → Story 24.10 | Gate locked 2026-07-03: reclassified Out of Scope -> Covered elsewhere (delivered by 24.9).
24.10-k | Release committed inventory reservations on cancel (scope addition 2026-07-03 — absorbed from OOS 24.12; analysis-derived) | Deliverable | Implement here |  | ADDED + CONFIRMED 2026-07-03. Data-integrity invariant, not a 24.12 feature: reservations created 'committed' with order_id at checkout (both repos); availability sums committed rows with no expiry; ONLY release writers are two webhook payment-failure paths — a cancel that skips release STRANDS UNITS FOREVER (a regression 24.10 would introduce). Unit: InventoryService.releaseForOrder(orderId, tx) (~5 lines updateMany committed -> released + released_at), called in the cancel tx, guarded cart_id != null; named method so 24.13 reuses it. | admin src/admin/inventory/inventory.service.ts:104-127 (commitForCart; create {order_id, committed} :117-127; NO release method — grep zero); exh cart.helpers.ts:140-165; ext webhook.service.ts:2919-2926 & :3017-3023 (only release writers) |  | [C2] built here as reusable InventoryService method; 24.13 calls it next sprint | (none — not in Confluence; BA note: cancellation spec omits inventory behavior) |  | Added at gate 2026-07-03: Deliverable (absorbed integrity scope).

## Endpoints
Method | Path | Purpose | Serves Req(s) | Shared With
POST | /api/v1/orders/:id/cancel | One $transaction: guarded status -> canceled; PT cascade (scheduled/processing/failed -> canceled, next_retry_at null, failure_message); releaseForOrder(orderId, tx); refund leg via 24.9's order-level composition (full/partial, cap-checked in 24.9's service); AdminAuditService.record in-tx. DTO: refund_type full¦partial, amount (iff partial), send_notification (default true — 24.11 rider). | 24.10-a…k | 24.11 (email toggle rides this DTO); 24.13 next sprint (reuses releaseForOrder); refund legs delegated to 24.9.

## Open Questions
Req | Item | Verdict | Open Question / What is needed | Dependency (blocking story + Jira) | Assignee | Sprint / Jira status | Decision / Current direction
— | Register empty — gate locked 2026-07-03 |  | Q1 (where does Refund Management live) RESOLVED: sibling 24.9 (SBE-1133), same release. Q2 (partial refunds vs binary PT.refunded) RESOLVED by 24.9 gate: ledger carries partials; PT flips only on full refund (amount-aware handler, 24.9 scope). |  |  |  | All rows Deliverable (sequenced intra-release) or covered elsewhere.

## Cross-Epic Dependencies
Dependency | Needed For | Likely Owner
Refund stack: ledger model + refund_failed, refunds service/endpoint, Stripe wrapper, amount-aware handler | 24.10-d, 24.10-e, 24.10-f, 24.10-h, 24.10-j | 24.9 (SBE-1133) — same release, builds first (migration lands first)
Offline/manual payment producer: payment_type column, NOT-NULL relaxation, manual lifecycle | 24.10-g | 24.8 (SBE-1132) -> 24.7 (SBE-1131) — same release

## Implementation Status
Section | Detail
Status | Not started — Step-1 gate complete 2026-07-03; scope + decisions locked (D1 refunds fully delegated to 24.9; D2 producer = 24.8 -> 24.7; 24.10-k added). Release model: all remaining OM stories ship together; sibling gating = sequenced, not Blocked.
Branch | —
SBE ticket | SBE-1134 (In Progress, Prantik Saha)
Commits | —
PR | —
Swagger tag | —
Build gates | —
Live smoke | —
Confirmed build scope | 24.10-a/b/c/d/e/f/g/h/i/k — cancel tx + releaseForOrder + orders.cancel seed + audit; refund legs = calls into 24.9 service
Remaining | All confirmed scope unbuilt
Not ready — see Open Questions | none — register empty (Q1/Q2 resolved 2026-07-03)
External dependencies — see Cross-Epic Dependencies | 24.9 refund stack; 24.8 -> 24.7 manual producer — all same-release, sequenced
Out of API scope | FE Cancel button + confirmation modal wiring