## Overview
Story ID | 24.6
Title | Order Details
Epic | Order Management
Build Status | SCOPE LOCKED at Step-1 gate 2026-07-03. 22 Deliverable / 1 Deferred / 3 Needs clarification (BA) / 1 Covered elsewhere (24.5, live) / 1 Blocked (epic 65). Ship-together release; builds after 24.8.
To implement here | 22
Summary | Gate outcome: GET :id aggregate + PATCH :id (billing/additional_emails, status-gated) + PATCH :id/sales-rep + 24.6-OWNED per-installment void (D-z). Status = derived 6-value display mapping (D1, no migration; qualifiers from 24.9 ledger). Rep/source = read-time derivation (D3/D4, 'Self-Service' default per story). additional_emails = Json column (D5). Admin-checkout snapshot gaps registered to Cart Mgmt team (D2/OQ-1) — page renders gracefully. Parked: send-email (OQ-4), HubSpot v/x (OQ-5 — no owning epic). Deferred: l2 onsite contact (SBE-1169/1171). Blocked: w on QB epic 65. Order Status sheet fetched in full (6 tabs) and applied; label map + edit-rules matrix sourced from it.
Deferred / Parked / Covered / Blocked | 1 Deferred (l2) · 3 Needs clarification (r, v, x) · 1 Covered by 24.5 (s) · 1 Blocked (w)
Total requirements | 28
Deliverable | 22
Deferred | 1
Needs clarification (BA) | 3
Covered elsewhere | 1
Blocked | 1
Implementation | Delivered — merged to dev 2026-07-05 (Phase 6 of the OM Phase-1 one-release).
Impl Branch | feature/SBE-1125
Impl Commits | admin 4c3308c (feat — order details aggregate, billing/sales-rep edit, installment void) + 5826f19 (SonarQube S4624)
PR | admin #537 -> dev 64ef8e3

## Requirements
Req ID | Requirement | Verdict | Build Focus | Delivered By | Reason (exists vs to-build / gap) | Code Evidence | Dependency | Build Consolidation (reuse / delivered-by) | Story Wording (verbatim, from Confluence) | Confluence | Impl Status (2026-07-05)
24.6-a | Display General Information: Order ID/Number, Date Created, Order Status | Deliverable | Implement here |  | CONFIRMED 2026-07-03. order_number/status/created_at on Order, populated by both checkout paths; GET :id detail aggregate is net-new and is the story's core route. | schema order_number:1543/status:1547/created_at:1586; route inventory re-verified on dev@34c6fb4 |  |  | General Information Order ID/Number Date Created Order Status | Open §Order Management → Story 24.6 | Gate 2026-07-03: Deliverable. -> ✅ DELIVERED 2026-07-05 (SBE-1130, admin 4c3308c, PR#537) merged to dev; audit-verified.
24.6-b | Order Status taxonomy: Active (Payment Pending), Active (Paid In Full), Cancelled (Full/Partial/No/Never Paid Refund) with automated vs manual transitions per Order Status sheet | Deliverable — sequenced intra-release (24.9) | Implement here |  | D1 = option (b): derived status_display, NO enum migration. Active pair from stored enum (pending/partially_paid -> Payment Pending; completed -> Paid In Full); the four Cancelled qualifiers = arithmetic over 24.9's per-installment refund ledger (Never Paid paid=0 / No Refund refunded=0 / Partial 0<r<p / Full r=p). Status Breakdowns tab confirms: stored overall notion is just 'Active'; richness is per-milestone. Installment label map: succeeded->Paid, scheduled->Unpaid, failed->CC Failed, canceled->Voided, refunded->Refunded; chargeback trio stays ND per 24.8-l (this sheet is its source). BA note: spec has NO standalone 'Refunded' top-level — refund w/o cancel stays Active; 'failed' maps to Active (Payment Pending). | OrderStatus enum :421-430; Status Breakdowns tab rows 12-18; sheet fetched in full (6 tabs) 2026-07-03; 24.9 gate D1 (derived refund state) | 24.9 refund ledger — same release; label map = C13 shared unit |  | Active (Payment Pending, Automated) Active (Paid In Full, Automated) Cancelled (Full Refund, Manual Update) Cancelled (Partial Refund, Manual Update) Cancelled (No Refund, Manual Update) Cancelled (Never Paid, Manual Update) For order status behavior, available actions, and corresponding updates in HubSpot and QuickBooks, refer to the Order Status sheet. | Open §Order Management → Story 24.6 | Gate 2026-07-03: Partial -> Deliverable-sequenced (D1 option b). -> ✅ DELIVERED 2026-07-05 (SBE-1130, admin 4c3308c, PR#537) merged to dev; audit-verified.
24.6-c | Display and (admin) edit Internal Notes | Deliverable | Implement here |  | CONFIRMED 2026-07-03. Column + GET/PATCH :id/notes live via 24.14. Display-only here. Order.notes (:1571) RESERVED — exhibitor idempotency-key store, NEVER expose. | Order.internal_notes :1572; orders.controller.ts:94/131; migration 20260702120000; perms :1240/:1248 |  | [C5 cross-reference] Mostly delivered by building 24.14 (GET + PATCH /api/v1/orders/:id/notes — the single read/writ…). Residual: the WRITE/EDIT of internal-notes / invoice-note / additional-terms / payment-memo is delivered by 24.14's PATCH .../notes (24.14-a/b/c/d) — these were removed from 24.6's PATCH .../:id. 24.6 retains only DISPLAY of these fields inside its GET .../:id aggregate (reading the columns 24.14 adds; no separate write path). NOTE: 24.6-d (Payment Memo) is 'Not Deliverable' in the input ONLY because the column does not exist yet — once 24.14 adds payment_memo + its PATCH (24.14-b), 24.6-d's edit IS delivered by 24.14 and only its display remains 24.6's. The catalog deliberately excludes 24.6-d from the notes-write requirements list, but the column dependency is real. | Internal Notes | Open §Order Management → Story 24.6 | Gate 2026-07-03: Deliverable (24.14 flip re-confirmed). -> ✅ DELIVERED 2026-07-05 (SBE-1130, admin 4c3308c, PR#537) merged to dev; audit-verified.
24.6-d | Display/edit Payment Memo | Deliverable | Implement here |  | CONFIRMED 2026-07-03. Order-level memo live via 24.14; display-only here. Keep distinct from PT.payment_memo (24.8's installment-level check-#/wire-ref field) — two fields, same name; FE must not conflate (BA note carried on 24.8). | Order.payment_memo :1573 (Text) |  | [C5 cross-reference] Mostly delivered by building 24.14 (GET + PATCH /api/v1/orders/:id/notes — the single read/writ…). Residual: the WRITE/EDIT of internal-notes / invoice-note / additional-terms / payment-memo is delivered by 24.14's PATCH .../notes (24.14-a/b/c/d) — these were removed from 24.6's PATCH .../:id. 24.6 retains only DISPLAY of these fields inside its GET .../:id aggregate (reading the columns 24.14 adds; no separate write path). NOTE: 24.6-d (Payment Memo) is 'Not Deliverable' in the input ONLY because the column does not exist yet — once 24.14 adds payment_memo + its PATCH (24.14-b), 24.6-d's edit IS delivered by 24.14 and only its display remains 24.6's. The catalog deliberately excludes 24.6-d from the notes-write requirements list, but the column dependency is real. | Payment Memo | Open §Order Management → Story 24.6 | Gate 2026-07-03: Deliverable. -> ✅ DELIVERED 2026-07-05 (SBE-1130, admin 4c3308c, PR#537) merged to dev; audit-verified.
24.6-e | Display Invoice Note / PO # | Deliverable | Implement here |  | CONFIRMED 2026-07-03. Column live via 24.14 (VarChar(255), mirrors Cart def). Display-only. | Order.invoice_note :1574 |  | [C5 cross-reference] Mostly delivered by building 24.14 (GET + PATCH /api/v1/orders/:id/notes — the single read/writ…). Residual: the WRITE/EDIT of internal-notes / invoice-note / additional-terms / payment-memo is delivered by 24.14's PATCH .../notes (24.14-a/b/c/d) — these were removed from 24.6's PATCH .../:id. 24.6 retains only DISPLAY of these fields inside its GET .../:id aggregate (reading the columns 24.14 adds; no separate write path). NOTE: 24.6-d (Payment Memo) is 'Not Deliverable' in the input ONLY because the column does not exist yet — once 24.14 adds payment_memo + its PATCH (24.14-b), 24.6-d's edit IS delivered by 24.14 and only its display remains 24.6's. The catalog deliberately excludes 24.6-d from the notes-write requirements list, but the column dependency is real. | Invoice Note / PO # | Open §Order Management → Story 24.6 | Gate 2026-07-03: Deliverable. -> ✅ DELIVERED 2026-07-05 (SBE-1130, admin 4c3308c, PR#537) merged to dev; audit-verified.
24.6-f | Display Additional Terms & Conditions | Deliverable | Implement here |  | CONFIRMED 2026-07-03. Column live via 24.14 (Text, mirrors Cart def). Display-only. | Order.additional_terms :1575 |  | [C5 cross-reference] Mostly delivered by building 24.14 (GET + PATCH /api/v1/orders/:id/notes — the single read/writ…). Residual: the WRITE/EDIT of internal-notes / invoice-note / additional-terms / payment-memo is delivered by 24.14's PATCH .../notes (24.14-a/b/c/d) — these were removed from 24.6's PATCH .../:id. 24.6 retains only DISPLAY of these fields inside its GET .../:id aggregate (reading the columns 24.14 adds; no separate write path). NOTE: 24.6-d (Payment Memo) is 'Not Deliverable' in the input ONLY because the column does not exist yet — once 24.14 adds payment_memo + its PATCH (24.14-b), 24.6-d's edit IS delivered by 24.14 and only its display remains 24.6's. The catalog deliberately excludes 24.6-d from the notes-write requirements list, but the column dependency is real. | Additional Terms & Conditions | Open §Order Management → Story 24.6 | Gate 2026-07-03: Deliverable. -> ✅ DELIVERED 2026-07-05 (SBE-1130, admin 4c3308c, PR#537) merged to dev; audit-verified.
24.6-g | Linked Customer with option to view customer profile and the customer's other orders | Deliverable | Implement here |  | CONFIRMED 2026-07-03. company relation + index live; profile = existing company module; 'other orders' = shipped 24.1 list filtered by company_id. Include linkage in response — no other backend. | company relation :1589; @@index([company_id]) :1602; company-management controller live |  |  | Linked Customer with option to view customer profile and other orders | Open §Order Management → Story 24.6 | Gate 2026-07-03: Deliverable. -> ✅ DELIVERED 2026-07-05 (SBE-1130, admin 4c3308c, PR#537) merged to dev; audit-verified.
24.6-h | Billing Information display (Company Name, Billing Address, Email, Phone) with Billing Address editable by admin | Deliverable | Implement here |  | D2 = option (b): display + net-new PATCH :id billing edit SHIP; admin-checkout write gap (only company/first/last/email written — NO address/phone/city/state/zip keys) REGISTERED to Cart Mgmt team (OQ-1), not fixed here: checkout.service.ts is Suman Paul's actively-evolving Cart Mgmt module (c0e1c46 2026-06-11 .. bb94413 2026-06-29) — record-don't-own. Net effect: admin-created orders show empty address/phone until PATCHed; nothing breaks. | billing cols :1554-1564; exhibitor full write payments.service.ts:202-212; admin partial write checkout.service.ts:263-266 (blame = Suman Paul, Cart Mgmt) | Cart Mgmt team upstream fix (OQ-1) — non-blocking |  | Billing Information Company Name and Billing Address (Billing Address editable by admin) Email Address with option to add Additional Emails Phone Number | Open §Order Management → Story 24.6 | Gate 2026-07-03: Partial -> Deliverable (D2 option b, gap registered). -> ✅ DELIVERED 2026-07-05 (SBE-1130, admin 4c3308c, PR#537) merged to dev; audit-verified.
24.6-i | Email Address with option to add Additional Emails | Deliverable | Implement here |  | D5 = option (a): net-new Order.additional_emails Json string-array, edited via PATCH :id, DTO email validation. No existing store (grep additional_email/cc_email = 0; Cart.share_email = one-off snapshot). Child table rejected (no per-email metadata requirement anywhere). CC-on-automated-sends = ONE consolidated BA row (OQ-2) naming all four senders (24.6-r, 24.11, 24.15, 24.5); worst case = one-line CC-append per sender, all still unbuilt. | billing_email :1564; Cart.share_email :2862 (not reusable) | BA (CC scope only — column unblocked) |  | Email Address with option to add Additional Emails | Open §Order Management → Story 24.6 | Gate 2026-07-03: Partial -> Deliverable (D5 option a). -> ✅ DELIVERED 2026-07-05 (SBE-1130, admin 4c3308c, PR#537) merged to dev; audit-verified.
24.6-j | Sales Representative, Order Created By, and Order Type (Sales Person Sale vs Self-Service) display | Deliverable | Implement here |  | D3 = option (a): read-time derivation, NO new columns. Chain: sales_person_id set -> rep name ('Sales Person Sale') -> cart created_by_type=exhibitor -> 'Self-Service' -> created_by_type=admin -> admin creator name -> no cart (subscription/ppl_addon) -> order_type label. Every product order has cart_id by domain design -> 100% coverage. OrderType enum is the BILLING taxonomy, not this notion. Sheet's prefix table (SLF/PPL/...) confirms source = derived classification. Rep name resolved server-side (salesPerson join + shared name-builder, same as 24.1 list). | sales_person_id :1580; NO created_by/source col on Order (re-verified @34c6fb4); cart.created_by/type cart.service.ts:251-252; OrderType enum :412 |  |  | Sales Representative Order Created By Order Type (Sales Person Sale, Self-Service) | Open §Order Management → Story 24.6 | Gate 2026-07-03: Partial -> Deliverable (D3 option a). -> ✅ DELIVERED 2026-07-05 (SBE-1130, admin 4c3308c, PR#537) merged to dev; audit-verified.
24.6-k | Display Signer First Name, Last Name, and Sign Date | Deliverable | Implement here |  | CONFIRMED 2026-07-03. OrderAgreement signer_first/last_name + signed_at written at signing; include-in-aggregate. | OrderAgreement :1612-1638 (signer :1615-1616, signed_at :1618); written checkout.service.ts:302 |  |  | Signer First Name, Last Name, and Sign Date | Open §Order Management → Story 24.6 | Gate 2026-07-03: Deliverable. -> ✅ DELIVERED 2026-07-05 (SBE-1130, admin 4c3308c, PR#537) merged to dev; audit-verified.
24.6-l | Order Line Items: product name (linked to product details), show name (linked to show details), included items list, Regular Price/Price/Quantity/Total per item | Deliverable | Implement here |  | CONFIRMED 2026-07-03. OrderItem carries description/quantity/unit_price/custom_unit_price/amount/show_product_id/is_default_included + product FK; mirror exhibitor 13.3 rendering (classifyOrderItems + child-amount folding — copy cross-repo, don't import). COUPON CAVEAT: Order.coupon_code (:1549) never populated at checkout — join cart.coupon.code (13.3-proven). | OrderItem :1943-1974; exhibitor order-details.service.ts:39/:163 (coupon join), order-details.helpers.ts:104 |  |  | Order Line Items Product name linked to product details Show name linked to show details Included Items list / Regular Price, Price, Quantity, and Total per item | Open §Order Management → Story 24.6 | Gate 2026-07-03: Deliverable (coupon-join caveat carried to plan). -> ✅ DELIVERED 2026-07-05 (SBE-1130, admin 4c3308c, PR#537) merged to dev; audit-verified.
24.6-l2 | Per line-item Company Contact Name, Email, and Phone | Deferred | Hold | SBE-1169/1171 (onsite-contact stories) | D6: DEFERRED, aligned with 13.3-w. Zero contact columns on OrderItem/CartItem anywhere; 'Company Contact' appears exactly ONCE on the whole Confluence page. Best-fit producer OnsiteBoothContact (exact 3-field match; keyed (company_id, show_id); orders are multi-show -> values differ per item's show) has producer (exhibitor module, SBE-1165, 2026-07-02) + edit story SBE-1171 (merged 2026-07-03). RECONFIRMED 2026-07-06: SBE-1169 'View Onsite Boot Contact' is now DEV DONE (fixVersion Release 3, parent SBE-1071) — the display-semantics dependency has CLEARED. The (company_id, show_id) join + billing-contact fallback is now a small additive NATIVE ADMIN READ. Stays Deferred (not built this release), parked only on BA interpretation (OQ-3) + 13.3-w parity — no longer blocked on an unbuilt story. | OnsiteBoothContact model (@@unique(company_id, show_id)); producer exhibitor src/onsite-booth-contact/* (upsert :121; commits 79757af/bd9d234); no show_id on Order/Cart (multi-show per fee comments) | SBE-1169 DEV DONE (Release 3, Ritam Mondal; parent SBE-1071) + SBE-1171 (merged 2026-07-03); producer SBE-1165 shipped [reconfirmed 2026-07-06] |  | Company Contact Name, Email, and Phone | Open §Order Management → Story 24.6 | Gate 2026-07-03: Partial -> Deferred (D6; aligned with 13.3-w). -> ⏸ DEFERRED (SBE-1169/1171 onsite/booth contact; aligned with 13.3-w) — not built.
24.6-m | Sub-items / Add-on products shown under their parent booth/order item via Parent Order Item reference | Deliverable | Implement here |  | D2 (same register as 24.6-h): tree render ships (parent_order_item_id/cart_item_type/OrderItemTree live via 13.3-era migration; mirror classifyOrderItems) with GRACEFUL FLAT FALLBACK — admin checkout omits the linkage, so admin-created orders render flat (amounts correct, nothing breaks). Write gap on the combined cart-team register row (OQ-1). Tree self-heals for post-fix orders; historical tree not reconstructable (register asks cart team to decide backfill). | parent_order_item_id :1958, cart_item_type :1959, OrderItemTree :1968-1969, index :1972; set only by exhibitor cart.helpers.ts:53; admin checkout + exhibitor payments omit it (grep = 0) | Cart Mgmt team upstream fix (OQ-1) — non-blocking |  | Sub-items / Add-on Products Add-on products linked to a parent booth or order item with Parent Order Item reference | Open §Order Management → Story 24.6 | Gate 2026-07-03: Partial -> Deliverable (flat fallback; gap registered). -> ✅ DELIVERED 2026-07-05 (SBE-1130, admin 4c3308c, PR#537) merged to dev; audit-verified.
24.6-n | Fees: Cleaning Fee and Booth Setup Fee (auto-calculated based on admin configuration) | Deliverable | Implement here |  | CONFIRMED 2026-07-03. Frozen per-show snapshot columns; admin checkout computes+writes, exhibitor path leaves 0 (reverse asymmetry — appended to OQ-1). Auto-calc is upstream; 24.6 displays the snapshot. | setup_fees :1582, cleaning_fees :1583; written checkout.service.ts:255-256 |  |  | Fees Cleaning Fee (auto-calculated based on admin configuration) Booth Setup Fee (auto-calculated based on admin configuration) | Open §Order Management → Story 24.6 | Gate 2026-07-03: Deliverable. -> ✅ DELIVERED 2026-07-05 (SBE-1130, admin 4c3308c, PR#537) merged to dev; audit-verified.
24.6-o | Order Totals: Items Subtotal, Fees, Subtotal, Order Total, Balance Payable, Total Payable | Deliverable | Implement here |  | CONFIRMED 2026-07-03. subtotal/tax/total/paid_amount + shipped deriveBalanceDue (fixed-2). Net-new = items-subtotal/fees breakdown over OrderItem (C10 residual). DEVIATION NOTE: no 'centralized billing service' exists anywhere — Order's frozen columns + shared helpers ARE the authoritative source. Balance renders from gross paid_amount minus refunds via 24.9 ledger (24.9 D3). | subtotal :1548, tax :1551, total :1552, paid_amount :1578; deriveBalanceDue live (24.1) |  | [C10 cross-reference] Mostly delivered by building 24.1 (A single source-of-truth for money figures: balance due = O…). Residual: MOSTLY SEPARATE WORK — the detail breakdown (Items Subtotal, Fees, Subtotal, Order Total, Balance Payable, Total Payable) is a richer aggregation over OrderItem + fees that the list does NOT compute. The ONLY genuinely shared part is the Order Total / Balance scalars off Order.total/paid_amount. Treat as cross-reference (agree on the authoritative source), not a reused computation. | Order Totals Items Subtotal, Fees, Subtotal, Order Total, Balance Payable, Total Payable | Open §Order Management → Story 24.6 | Gate 2026-07-03: Deliverable (deviation noted). -> ✅ DELIVERED 2026-07-05 (SBE-1130, admin 4c3308c, PR#537) — balance_due is NET-of-refund here, the audit-ruled CANONICAL balance surface (24.6 sole balance spec).
24.6-p | Payment Plan reference linked to the Saved Cart Payment Plan | Deliverable — sequenced intra-release (24.8) | Implement here |  | CONFIRMED 2026-07-03. Plan via Order.cart_id join (null-safe: cart_id null for subscription/ppl_addon by design); installment rows consume 24.8's C13 mapper (build order puts 24.8 first). Next-installment piece independent (24.6-q). | CartPaymentPlan :2911, CartPaymentScheduleEntry :2926; cart_id nullable :1581 | 24.8 C13 mapper — same release, builds first | [C13 cross-reference] Mostly delivered by building 24.8 (A single PaymentTransaction -> installment-row mapper (Invo…). Residual: the detail aggregate embeds the payment-plan reference + next-installment amount/date (24.6-q), derivable from the same PaymentTransaction projection (next = earliest unpaid by due_date). 24.6-p stays Partial (cart_id linkage caveat). | Payment Plan reference linked to Saved Cart Payment Plan | Open §Order Management → Story 24.6 | Gate 2026-07-03: Partial -> Deliverable-sequenced (24.8). -> ✅ DELIVERED 2026-07-05 (SBE-1130, admin 4c3308c, PR#537) merged to dev; audit-verified.
24.6-q | Next Installment Amount and Next Payment Date | Deliverable — sequenced intra-release (24.8) | Implement here |  | CONFIRMED 2026-07-03. PT rows carry amount/due_date/status/paid timestamps; @@index([status,due_date]) exists for exactly this query; next installment = earliest scheduled by due_date (3-line query, unblockable). Labels per D1 map (scheduled->Unpaid, canceled->Voided, ...). | PaymentTransaction :2073-2103 (index :2103); worker payment-charge.service.ts:24 | 24.8 C13 mapper (labels/rows) — same release | [C13 cross-reference] Mostly delivered by building 24.8 (A single PaymentTransaction -> installment-row mapper (Invo…). Residual: the detail aggregate embeds the payment-plan reference + next-installment amount/date (24.6-q), derivable from the same PaymentTransaction projection (next = earliest unpaid by due_date). 24.6-p stays Partial (cart_id linkage caveat). | Next Installment Amount Next Payment Date | Open §Order Management → Story 24.6 | Gate 2026-07-03: Deliverable-sequenced (24.8). -> ✅ DELIVERED 2026-07-05 (SBE-1130, admin 4c3308c, PR#537) merged to dev; audit-verified.
24.6-r | Send Order Email: select an email template from a dropdown; save order or send email | Needs clarification (BA) | Hold (small; can slot late) |  | PARKED at gate (user decision). Capability verified buildable: template listing live (SBE-671); dispatch via ADMIN's own MailerService.sendFromTemplate (mailer.service.ts:192 — worker-mailer citation was stale, applies only to 24.15 cron legs); handler drops into 24.5's live order-actions.service.ts pattern. UNIQUENESS SWEPT: no other Confluence story on ANY page has pick-a-template-and-send (E&S epic manages templates only; salesperson 'Save as Template' = cart composition templates, not email, unimplemented); all existing senders fixed-template. OPEN (OQ-4): recipients (spec silent; proposed default [billing_email] + optional override + 400 if none; send by template ID — sidesteps E&S #21), 'Save order' semantics, dropdown scope. Excluded from plan; slots late without re-sequencing. | admin mailer.service.ts:192; order-actions.service.ts:697/:993 (live pattern); notification-template module; uniqueness sweep 2026-07-03 (both Confluence pages + all 5 repos) | BA (OQ-4) | [C11 build-once-reuse] Mostly delivered by building 24.5 (MailerService.sendFromTemplate (renders a NotificationTempl…). Residual: send-email dispatches an admin-SELECTED template (dropdown from notification-template list) — distinct selection UI, same mailer. | Send Order Email Select an email template from a dropdown Save order or send email | Open §Order Management → Story 24.6 | Gate 2026-07-03: Deliverable -> Needs clarification (parked). -> ⛔ PARKED (BA, OQ-4 send-email) — not built; honored (audit 2026-07-05: no route).
24.6-s | Agreement: view and download the linked agreement | Covered elsewhere | Covered elsewhere | 24.5 (SBE-1129) — LIVE on dev | CONFIRMED 2026-07-03 — upgraded to LIVE: 24.5 (PR#521, merged 2026-07-03) ships GET :id/agreement.pdf¦.docx (SIGNED contract). 24.6 residual = zero on download; aggregate includes agreement block (24.6-k fields) + links. | orders.controller.ts:197/:224 on dev@34c6fb4 | — delivered | [C6 cross-reference] Fully delivered by building 24.5 (GET /api/v1/orders/:id/agreement.pdf and /agreement.docx (r…) — no separate work. | Agreement View and download linked agreement | Open §Order Management → Story 24.6 | Gate 2026-07-03: Covered by 24.5 — routes live on dev. -> ✅ COVERED by 24.5 (quick actions live on dev).
24.6-t | Every order shall have an Assigned Sales Representative, regardless of creation path | Deliverable | Implement here |  | D4: the story text supplies the default — self-service orders display 'Self-Service' (D3 chain); no stored field, no house-account user, no backfill, no BA row. sales_person_id stays nullable; 24.6-u PATCH attaches a real rep any time (story explicitly allows reassignment for self-service orders). Rep name resolved server-side (salesPerson join + shared name-builder). | sales_person_id :1580 nullable; checkout comment 'Admin-created or self-service carts carry no sales person' (:267-270); schema re-verified @34c6fb4: no new source cols |  |  | An Assigned Sales Representative shall be associated with every order, regardless of creation path. | Open §Order Management → Story 24.6 | Gate 2026-07-03: Partial -> Deliverable (D4: derivation is the default). -> ✅ DELIVERED 2026-07-05 (SBE-1130, admin 4c3308c, PR#537) merged to dev; audit-verified.
24.6-u | Reassign the Assigned Sales Representative (Deal Owner) via permission-controlled action | Deliverable | Implement here |  | CONFIRMED 2026-07-03. Net-new PATCH :id/sales-rep writing Order.sales_person_id (our module), mirroring the live cart deal-owner pattern (validate active Sales-Team/Admin target); dropdown = reuse/mirror GET carts/deal-owners (plan-time choice). Permission key + audit. HubSpot side-effect explicitly NOT attached (OQ-5). | cart.service.ts:415-427 (deal-owner helper); cart.controller.ts:612-624 (dropdown) |  |  | The Assigned Sales Representative may be reassigned by authorized users per configured role permissions, for both sales-created and self-service orders. | Open §Order Management → Story 24.6 | Gate 2026-07-03: Partial -> Deliverable. -> ✅ DELIVERED 2026-07-05 (SBE-1130, admin 4c3308c, PR#537) merged to dev; audit-verified.
24.6-v | Changing the Assigned Sales Rep (Deal Owner) shall automatically update the Deal Owner in HubSpot | Needs clarification (BA) | Hold |  | PARKED at gate (user decision; was Blocked). RECONFIRMED 2026-07-06: the client updateDeal primitive NOW EXISTS (hubspot-client.service.ts:189) — supersedes the earlier 'no updateDeal' note — BUT it is subscription-only (sole caller webhook.service.ts:1019 -> upsertSubscriptionDeal) and the deal-OWNER piece is still absent: (1) NO order->deal linkage; (2) NO hubspot_deal_id on Order (only CompanySubscription :630 + AttendeeShow :2631); (3) NO owner-id mapping (only hubspot-deals salespersonProperty = affiliate-attribution TEXT, not a hubspot_owner_id / SBE-user->owner map); (4) NO OWNING EPIC (SBE-1307 = inbound-lead scope, To Do, unassigned). Verdict Needs-clarification (BA) stands. | hubspot-client.service.ts:173 createDeal / :189 updateDeal (subscription-only via webhook.service.ts:1019); Order has NO hubspot_deal_id (Order block); exhibitor auth.service.ts:366 (4.8 contact sync live) [reconfirmed 2026-07-06] | BA (OQ-5: create/route a deal-sync epic) |  | The system shall maintain HubSpot synchronization for deal ownership; changing the Assigned Sales Representative (Deal Owner) shall automatically update the Deal Owner in HubSpot. | Open §Order Management → Story 24.6 | Gate 2026-07-03: Blocked -> Needs clarification (no owning epic — BA). -> ⛔ PARKED (BA, OQ-5 HubSpot deal-sync — no owning epic) — not built; PATCH sales-rep carries no HubSpot side-effect.
24.6-w | QuickBooks Force Sync: manually sync Invoices, Payments, and Customers to QuickBooks | Blocked | Hold | Epic 65 (QuickBooks) | CONFIRMED 2026-07-03: Blocked on epic 65. Zero QB code in all 5 repos ('future module' comments + dormant Order.quickbooks_*/Invoice QB columns written by nothing). Owner exists: epic 65 'Quickbooks Integration/Invoice Creation Process' (Page 2, stories 65.1-65.5, un-ticketed in Jira; missing refund/credit-memo + dispute stories — BA flags from 24.9/24.8 gates). Sheet's QB column cited for that epic (invoices, received payments, credit memos, chargeback journal entries). | dormant cols :1568-1570 + Invoice model; grep quickbooks/intuit = comments only; Page 2 epic 65 (65.1-65.5) | Epic 65 (QuickBooks) — external, un-ticketed |  | QuickBooks Force Sync Manually sync Invoices, Payments, and Customers to QuickBooks | Open §Order Management → Story 24.6 | Gate 2026-07-03: Blocked on epic 65 (re-confirmed). -> ⛔ BLOCKED (QuickBooks epic 65, un-ticketed) — not built.
24.6-x | HubSpot manual sync: manually sync Order to HubSpot | Needs clarification (BA) | Hold |  | D7, PARKED with 24.6-v (same OQ-5 row; v = automatic owner sync, x = manual order sync). RECONFIRMED 2026-07-06: client updateDeal now exists (:189) but is subscription-only; create-once-no-resync still risks duplicate deals, and there is still no order->deal linkage, no hubspot_deal_id on Order, no owner-id mapping, and no owning epic. Nothing built. | same as 24.6-v | BA (OQ-5) |  | Hubspot Sync Manually Sync Order to Hubspot | Open §Order Management → Story 24.6 | Gate 2026-07-03: Partial -> Needs clarification (with 24.6-v). -> ⛔ PARKED (BA, OQ-5 HubSpot, with 24.6-v) — not built.
24.6-y | View, edit, refund, void, sync, and reassignment actions are role-based, permission-controlled, and enforced on the backend | Deliverable | Implement here |  | CONFIRMED 2026-07-03. Framework live (roles.guard + roles_permissions + Developer bypass; orders seeder block precedent :1229-1248). Seed keys for SHIPPING actions only (orders.view/update/sales_rep.update/payments.void); refund/cancel keys owned by 24.9/24.10; no keys for parked sync actions. | roles.guard.ts :8/:48/:85-86; permission.seeder.ts orders block :1229-1248 |  | [C8 build-once-reuse] Mostly delivered by building 24.1 (The existing JWT + roles guard + @Permissions(...) decorato…). Residual: per-action keys for edit/refund/void/sync/reassign on the detail routes. | View, edit, refund, void, sync, and reassignment actions are role-based and permission-controlled. / Field edits, permissions, and sync shall be enforced on the backend. | Open §Order Management → Story 24.6 | Gate 2026-07-03: Deliverable. -> ✅ DELIVERED 2026-07-05 (SBE-1130, admin 4c3308c, PR#537) merged to dev; audit-verified.
24.6-z | Refund and Void actions available on the order (per Order Status sheet) | Deliverable — refund sequenced (24.9); void 24.6-OWNED | Implement here |  | SPLIT per sheet's per-row actions (REFUND on paid rows; DELETE+VOID on unpaid/CC-failed rows). Refund half: display flags + wire to 24.9's POST :id/refunds (key orders.refund seeded by 24.9) — zero refund logic here. Void half (D-z, GATE DECISION: 24.6 owns manual per-installment void): POST :id/payments/:transactionId/void, guard status IN (scheduled, failed), sets canceled + next_retry_at:null (24.10 cascade shape — crons never resurrect voided rows), label 'Voided', key orders.payments.void, audited. Distinct from 24.8's scheduled-row delete and 24.10's cancel cascade. | Status Breakdowns rows 3-10 (per-milestone actions); worker cron predicates; 24.10 cascade shape (locked 2026-07-03) | 24.9 (refund flags only) — same release | [C3 build-once-reuse] Mostly delivered by building 24.9 (POST /api/v1/orders/:id/refunds — validate cap (paid_amount…). Residual: the refund HALF of 24.6-z is delivered by this endpoint. The VOID half is a SEPARATE endpoint (POST .../void) and remains Blocked (no Stripe void path / no Refund model) — do not fold void here. 24.6-z is overall Blocked in the input precisely because of the void half + net-new Refund model. ¦ [C7 build-once-reuse] Mostly delivered by building 24.9 (external-api-service POST /v1/refunds (internal) — stripe.r…). Residual: the refund action invoked from Order Details routes through 24.9's endpoint which calls this wrapper; no separate Stripe call. (Void half of 24.6-z is unrelated and Blocked.) | View, edit, refund, void, sync, and reassignment actions are role-based and permission-controlled. / For order status behavior, available actions, and corresponding updates in HubSpot and QuickBooks, refer to the Order Status sheet. | Open §Order Management → Story 24.6 | Gate 2026-07-03: Blocked -> Deliverable (refund sequenced; void owned here per gate decision). -> ✅ DELIVERED 2026-07-05 (SBE-1130, admin 4c3308c, PR#537) merged to dev; audit-verified.
24.6-aa | Edit rules: edits blocked for non-editable statuses; signed/completed orders read-only except permitted post-sale actions; field edits enforced on backend | Deliverable | Implement here |  | CONFIRMED 2026-07-03. Gating state live (status + OrderAgreement presence + guards). Net-new = status->allowed-actions matrix encoded from the Status Breakdowns action columns (held in full), enforced on 24.6's write routes (billing PATCH blocked post-cancel; post-sale actions per permissions). | status :1547; OrderAgreement :1612; Status Breakdowns action columns |  |  | Edits shall be blocked for non-editable statuses; signed or completed orders shall be read-only except for permitted post-sale actions. / Field edits, permissions, and sync shall be enforced on the backend. | Open §Order Management → Story 24.6 | Gate 2026-07-03: Deliverable. -> ✅ DELIVERED 2026-07-05 (SBE-1130, admin 4c3308c, PR#537) merged to dev; audit-verified.

## Endpoints
Method | Path | Purpose | Serves Req(s) | Shared With
GET | /api/v1/orders/:id | Full detail aggregate: general, status_display (D1), notes/memo/terms (read-only), billing, additional_emails, customer link, line-item tree (flat fallback) + coupon join, fees, totals + breakdown, plan + installments + next installment, signer/agreement block, sales rep/source (D3). | a,b,c,d,e,f,g,h,i,j,k,l,m,n,o,p,q,t | Consumes 24.8 C13 mapper, 24.9 ledger, 24.14 columns, 24.5 links
PATCH | /api/v1/orders/:id | Billing-address + additional_emails edit; status-gated (24.6-aa matrix); audited. | h,i,aa,y
PATCH | /api/v1/orders/:id/sales-rep | Reassign rep -> sales_person_id (cart deal-owner pattern); permission-gated; audited. HubSpot side-effect NOT attached (OQ-5). | t,u,y | Dropdown: reuse/mirror GET carts/deal-owners
POST | /api/v1/orders/:id/payments/:transactionId/void | 24.6-OWNED manual installment void (D-z): guard status IN (scheduled, failed) -> canceled + next_retry_at:null; label 'Voided'. | z,y,aa | Shape shared w/ 24.10 cascade (same terminal write)
POST (parked) | /api/v1/orders/:id/send-email | PARKED (OQ-4): template-id send via admin sendFromTemplate; ships only after BA answers recipients/'save order'/dropdown scope. | r
GET (live, 24.5) | /api/v1/orders/:id/agreement.pdf ¦ .docx | LIVE — 24.5's signed-contract routes; 24.6 links only. | s | 24.5 (owner)
PATCH (live, 24.14) | /api/v1/orders/:id/notes | LIVE — 24.14's canonical notes write path; 24.6 displays only. | c,d,e,f | 24.14 (owner)
POST (24.9) | /api/v1/orders/:id/refunds | 24.9's endpoint — 24.6 surfaces per-installment REFUND flags + wiring only. | z,b | 24.9 (owner), 24.11 (email)
(not built) | hubspot-sync / quickbooks-sync / order-level void | NOT BUILT: hubspot-sync parked (OQ-5); quickbooks-sync Blocked (epic 65); order-level void replaced by per-installment void (D-z). | v,w,x

## Open Questions
# | Req | Item | Verdict | Open Question / What is needed | Dependency (blocking story + Jira) | Assignee | Sprint / Jira status | Decision / Current direction
OQ-1 | 24.6-h, 24.6-m (+n note) | Admin-checkout order snapshot gaps | Deliverable (display ships; upstream gap registered) | Admin checkout orders.create (admin src/admin/cart/services/checkout.service.ts, blame c0e1c46/bb94413) omits (1) billing address/phone/city/state/country/zip keys and (2) parent_order_item_id + cart_item_type on items -> admin-created orders show null billing address + flat add-on list. Ask: extend the create call (billing from cart.company; parent map per exhibitor cart.helpers pattern); decide historical backfill. Reverse asymmetry: exhibitor path leaves setup/cleaning fees at 0. | Cart Management epic — un-ticketed; needs a ticket from the cart team | Cart Mgmt team (Suman Paul) via BA/lead | Unticketed as of 2026-07-03 | 24.6 NOT blocked: nulls/flat render gracefully; billing manually fixable via new PATCH; tree self-heals for post-fix orders. Record-don't-own: we don't edit the cart module.
OQ-2 | 24.6-i | additional_emails CC scope on automated sends | Deliverable (column unblocked) | Should Order.additional_emails be CC'd on automated emails? Consumers if yes (one-line CC-append each, all unbuilt): 24.6-r manual send, 24.11 cancel/refund dispatch, 24.15 reminders (carried into its gate), 24.5 resends (note only — shipped). Sheet precedent: refund email offers 'add another email address' (manual, ad-hoc). | — | BA | Open 2026-07-03 | Column + PATCH ship regardless; senders default to billing_email until BA answers.
OQ-3 | 24.6-l2 | Per-item Company Contact interpretation + revisit | Deferred | Confirm 'Company Contact' on line items = the company's onsite booth contact for the item's show (OnsiteBoothContact, exact 3-field match, per-(company,show)). RECONFIRMED 2026-07-06: SBE-1169 now DEV DONE — the display-semantics dependency has cleared; the join is now a small additive native admin read w/ billing-contact fallback. | SBE-1169 View Onsite Boot Contact — DEV DONE (Release 3) [reconfirmed 2026-07-06] (+SBE-1171 merged 2026-07-03; producer SBE-1165 shipped 2026-07-02) | Ritam Mondal (SBE-1169); BA (interpretation) | SBE-1169 DEV DONE, Release 3 (was To Do/Sprint 5) — reconfirmed 2026-07-06 | Deferred this release — dependency cleared; now a buildable native admin read, parked only on BA interpretation + 13.3-w parity.
OQ-4 | 24.6-r | Send Order Email scope | Needs clarification | (1) Recipients — spec silent; proposed: default [billing_email], optional recipients[] override (billing + additional_emails + ad-hoc), 400 if none. (2) 'Save order or send email' — save WHAT state? (3) Dropdown scope — all active templates or a tagged subset? Uniqueness verified: no other Confluence story anywhere has pick-a-template-and-send; send-by-template-id sidesteps E&S #21. | — | BA | Open 2026-07-03 | Excluded from plan; small build (handler + DTO into live order-actions pattern) — slots late without re-sequencing.
OQ-5 | 24.6-v, 24.6-x | HubSpot deal-sync has NO owning epic | Needs clarification | Deal-level order sync (auto owner-update v + manual sync x) spec'd only as scattered clauses. Inventory: 4.8 post-registration CONTACT sync implemented (exhibitor auth.service.ts:366); Nunify attendee webhook = sole createDeal caller. RECONFIRMED 2026-07-06: client updateDeal NOW EXISTS (:189) but is subscription-only; STILL MISSING = order->deal linkage, hubspot_deal_id on Order, SBE-user->hubspot_owner_id owner mapping (current salespersonProperty is affiliate-attribution text only), and an owning epic. Jira's only CRM epic SBE-1307 = inbound-lead scope. Ask: BA to create/route a deal-sync epic. | None exists (that's the issue); nearest: SBE-1307 (different scope, To Do, unassigned) | BA | Open 2026-07-03 (reconfirmed 2026-07-06: updateDeal now exists, owner-sync still unbuilt) | 24.6 builds nothing HubSpot; 24.6-u ships local reassignment cleanly separable from the future sync side-effect.
OQ-6 | 24.6-b (cross-story) | Sheet findings routed for BA | Note | From Status Breakdowns, in no story's scope: (1) internal cancel notification to departments@theshowproducers.com on every cancel (not in 24.11's locked scope — route or add); (2) refund email send-toggle + extra-recipient ability (extends 24.11's optional-send; conditional one-liner in 24.11's PLAN if ratified); (3) no standalone 'Refunded' overall status — refund w/o cancel stays Active (FE brief). Chargeback trio remains ND per 24.8-l (sheet = source; Jackie Questions tab shows disputes unresolved at accounting level). | — | BA | Open 2026-07-03 | Recorded here (sheet referenced from 24.6); locked sibling docs untouched.

## Cross-Epic Dependencies
Dependency | Needed For | Likely Owner
QuickBooks integration service — epic 65 'Quickbooks Integration/Invoice Creation Process' (Admin Panel Page 2, stories 65.1-65.5; un-ticketed in Jira; missing refund/credit-memo + dispute stories, BA-flagged at 24.9/24.8 gates; sheet QB column = spec input) | 24.6-w | Epic 65 (QuickBooks)
HubSpot deal-sync epic (DOES NOT EXIST — OQ-5). Reconfirmed 2026-07-06: client updateDeal now exists but is subscription-only; still missing = order->deal linkage + hubspot_deal_id on Order + SBE-user->hubspot_owner_id owner mapping + an owning epic; sheet Hubspot tab = spec input | 24.6-v, 24.6-x | BA to create/route (nearest existing: SBE-1307, inbound-lead scope only)
Onsite-contact display semantics — SBE-1169 now DEV DONE (Release 3) [reconfirmed 2026-07-06]; producer SBE-1165 shipped 2026-07-02; edit SBE-1171 merged 2026-07-03. Dependency cleared; 24.6-l2 now a buildable native admin read, deferred this release on BA interpretation only | 24.6-l2 | Exhibitor Onboarding (SBE-1071 parent, Ritam Mondal)
Admin-checkout snapshot fixes (billing + item tree — OQ-1); non-blocking display-fidelity gap for admin-created orders | 24.6-h, 24.6-m | Cart Management team (Suman Paul)
In-release (NOT external): 24.9 ledger (b qualifiers, z flags, balance); 24.8 C13 mapper (p/q rows + D1 label map); 24.14 notes columns (c/d/e/f, live); 24.5 agreement routes + order-actions pattern (s live, r's home) | 24.6-b/p/q/z/c/d/e/f/s | Same release — build order 24.9->24.10->24.11->24.8->24.7->24.6

## Implementation Status
Section | Detail
Status | Delivered — merged to dev 2026-07-05 (Phase 6 of the OM Phase-1 one-release).
Branch | feature/SBE-1125 (all 5 repos; per-story SBE-ticket commit scopes; OM Phase-1 one-release model)
SBE ticket | SBE-1130 (In Progress, Prantik Saha)
Commits | admin 4c3308c (feat — order details aggregate, billing/sales-rep edit, installment void) + 5826f19 (SonarQube S4624)
PR | admin #537 -> dev 64ef8e3
Swagger tag | Admin - Order Management (/api/docs/admin)
Build gates | Green — admin 8-step pre-push gate (prisma migrate deploy + full seed:run, typecheck, lint:check, test:cov, build) + Bitbucket pipeline SUCCESSFUL (gitleaks + lint/test + SonarQube quality gate) on every phase.
Live smoke | GET /orders/:id detail aggregate (Order.notes never selected), PATCH billing/additional_emails/sales-rep, per-installment void; six status labels verbatim; all green.
Confirmed build scope | 22 reqs delivered. GET /orders/:id aggregate; PATCH billing/additional_emails/sales-rep; POST /orders/:id/payments/:transaction_id/void; derived status_display + source + net balance (canonical).
Parked pending BA | 24.6-r send-email (OQ-4) · 24.6-v/x HubSpot (OQ-5)
Deferred | 24.6-l2 onsite contact — dependency SBE-1169 now DEV DONE (reconfirmed 2026-07-06); buildable as a native admin read, parked only on BA interpretation (OQ-3)
Blocked external | 24.6-w QuickBooks (epic 65)
External dependencies — see Cross-Epic Dependencies | Cart-team snapshot fixes (OQ-1, non-blocking); in-release: 24.9 ledger + 24.8 mapper
Out of API scope | FE wiring (navigation, buttons, dropdown UI); HubSpot/QB UI affordances for parked actions
Evidence baseline | Verified @admin 0ac2769 (+4 siblings) 2026-07-03; dev moved same day to 34c6fb4 (24.5 PR#521, SBE-1171 PR#520, id-encryption PR#455) — folded in; schema line cites @0ac2769, spot-refresh at plan time.
Canonical balance | 24.6-o balance_due is NET-of-refund — the audit-ruled canonical surface; 24.7/24.8/24.1 aligned to it post-merge (P1).