## Overview
Story ID | 13.3
Title | Order Details Page
Epic | Order History
Build Status | ✅ Implemented & merged to dev. Core aggregate 2026-07-01 (PR #276); 13.3-s invoice 2026-07-05 (PR #300); 13.3-l gift-cert line 2026-07-05 (PR #303); 13.3-w onsite contacts 2026-07-06 (PR #305). Post-ship reworks of GET /orders/:orderId: invoice endpoints rework SBE-1146 2026-07-17 (PRs #346/#347, commit 126cffe) — download-by-invoice-id GET /orders/invoices/:id + new list GET /orders/:orderId/invoices; order-details nesting redesign SBE-1147 2026-07-26 (PR #372, merge eea6713, commit 20ce757) — product-gated + nested-by-show shows[] with unassigned bucket, product_name/purchased_name, per-booth setup_fee/cleaning_fee, additional_purchases[].show.
To implement here | 20
Summary | Read-only exhibitor Order Details page. The core data is well-backed: the exhibitor cart checkout write-path (exhibitor-backend-api cart.service.ts:1229-1305 + cart.helpers.ts materializeCartToOrder) writes Order (subtotal, coupon_amount, setup_fees, cleaning_fees, total_savings, total, paid_amount=0, billing), OrderItems carrying cart_item_type (booth/sponsorship/addon/fee), description, quantity, unit_price, amount and parent_order_item_id, plus OrderAgreement (signer, signature URL, terms_accepted, signed_at) and a processing PaymentTransaction; the external-api webhook (webhook.service.ts:2042-2098 + buildPtSuccessUpdate:2187-2201) flips the order to paid, sets paid_amount/charge id/paid_at, and creates Invoice + InvoiceLineItem tree for cart-flow orders. So a net-new GET order-details endpoint, an invoice-PDF endpoint (a pdfkit renderer already exists in ppl.service.ts) and an agreement download are all Deliverable on built primitives, with ownership enforced via existing auth guards + company_id scoping. Booth Size is now Deliverable: it is joinable structured data (booth OrderItem.product_id -> Product.length/width, the canonical 10x10), not just a name snapshot. Gaps: Gift Certificate redemption has a model (GiftCertificateRedeem) but NO code writes it - admin only reads it (Blocked); booth Number has no column/write-path anywhere (Not Deliverable); and the 'download signed agreement' option only has the captured signature image + acceptance metadata, no composed agreement document is generated (Partial). Per the story note, Booth Type, Booth Upgrade, salesperson Payment Schedule visibility, and Onsite Contact belong to other stories (Out of Scope).
Total requirements | 29
Deliverable | 25
Deferred | 0
Partial | 0
Blocked | 2
Not Deliverable | 2
Out of Scope | 0
Implementation | Implemented & merged to dev 2026-07-01
Impl Branch | feature/SBE-1146-order-listing-table
Impl Commits | 981ebf2, e79a1eb
PR | #276 (merged → dev)

## Requirements
Req ID | Requirement | Verdict | Build Focus | Delivered By | Reason (exists vs to-build / gap) | Code Evidence | Dependency | Build Consolidation (reuse / delivered-by) | Story Wording (verbatim, from Confluence) | Confluence | Impl Status (2026-07-01)
13.3-a | Header: Order ID, Order Date and Time, Payment Status (e.g. Paid in Full) | Deliverable | Implement here | — | Order.order_number, created_at and status are written at checkout; the webhook bumps paid_amount and flips status to completed/partially_paid and sets paid_in_full_at. A net-new read endpoint maps status to a 'Paid in Full' label. | exhibitor-backend-api/src/cart/services/cart.service.ts:1231-1234; admin-backend-api/prisma/schema.prisma:1542,1546,1574,1581; external-api-service/src/modules/webhook/services/webhook.service.ts:2089-2098 |  | [C2 cross-reference] OWNER — build here (GET /orders/:orderId — the read-only ownership-scoped order…); reused by other stories in this cluster. ¦ [C5 build-once-reuse] Mostly delivered by building 13.2 (A NET-NEW read-time order-level payment-status derivation m…). Residual: none on the status computation — the details header 'Payment Status (e.g. Paid in Full)' is the identical derived value (including the overdue rollup). 13.3-a's other header fields (Order ID, date/time) are trivial passthroughs and not part of this shared unit. | Order Header The page shall show Order ID, Order Date and Time, Event Name, City, Event Dates, and Payment Status (the order's payment status, for example Paid in Full). | Open §Order History → Story 13.3 | ✅ Shipped 2026-07-01 (PR #276)
13.3-b | Header: Event Name, City, Event Dates | Deliverable | Implement here | — | OrderItem.show_product_id joins ShowProduct -> Show -> City (already loaded this way in the webhook). Event name/dates/city derivable per order line. | admin-backend-api/prisma/schema.prisma:1940,1952; external-api-service/src/modules/webhook/services/webhook.service.ts:2005-2007 |  | [C2 cross-reference] OWNER — build here (GET /orders/:orderId — the read-only ownership-scoped order…); reused by other stories in this cluster. | Order Header The page shall show Order ID, Order Date and Time, Event Name, City, Event Dates, and Payment Status (the order's payment status, for example Paid in Full). | Open §Order History → Story 13.3 | ✅ Shipped 2026-07-01 (PR #276)
13.3-c | Booth section: Booth Number | Not Deliverable | Open question (parked) | — | No model or write-path captures a physical/stall booth number. A grep for booth_number/stall returns zero matches across all repos and the schema. The booth is represented only by its product (booth-size SKU) and the OrderItem.description name snapshot; there is no booth-number assignment data anywhere. | admin-backend-api/prisma/schema.prisma:1928-1959 (OrderItem, no booth_number); grep booth_number/stall -> none found in any repo or schema | No producing story; booth numbers assigned externally post-purchase (seeder). Lead: 'Booth Sign Print Page' (Admin Panel Page 2), company+show, not order-linked |  | Booth/Workshop Pavilion Details The page shall clearly show Booth Number, Booth Size (for example, 10x10), Booth Type (Standard, Premium, Corner, etc.), Booth Price, Upgrade details (if any), and Booth subtotal. | Open §Order History → Story 13.3 | Not shipped — Not Deliverable (see Open Questions)
13.3-d | Booth section: Booth Size (e.g. 10x10) | Deliverable | Implement here | — | Booth size is structured, joinable data: the booth OrderItem.product_id references the booth-family Product, which carries length/width Decimal columns (the canonical '10x10' representation). These are populated via admin product management and already surfaced as booth-size options. The order-details endpoint can join OrderItem -> Product to format size. It is not a discrete Order/OrderItem column but is fully available on built primitives. | admin-backend-api/prisma/schema.prisma:1227-1229 (Product.length/width),1932,1949 (OrderItem.product_id -> Product); admin-backend-api/src/admin/product-management/product-management.service.ts:112-156 (booth size options from length/width) |  | [C2 cross-reference] OWNER — build here (GET /orders/:orderId — the read-only ownership-scoped order…); reused by other stories in this cluster. | Booth Size (for example, 10x10) | Open §Order History → Story 13.3 | ✅ Shipped 2026-07-01 (PR #276)
13.3-e | Booth section: Booth Price and Booth subtotal | Deliverable | Implement here | — | Booth line is an OrderItem with cart_item_type=booth carrying unit_price/amount; bundled children (is_default_included) and fees are materialized with parent_order_item_id so booth subtotal is computable. | exhibitor-backend-api/src/cart/helpers/cart.helpers.ts:48-68; admin-backend-api/prisma/schema.prisma:1937-1943 |  | [C2 cross-reference] OWNER — build here (GET /orders/:orderId — the read-only ownership-scoped order…); reused by other stories in this cluster. | Booth Price, Upgrade details (if any), and Booth subtotal. | Open §Order History → Story 13.3 | ✅ Shipped 2026-07-01 (PR #276)
13.3-f | Booth section: Booth Type (Standard/Premium/Corner) | Not Deliverable | Open question (parked) | — | Booth Type is owned by a separate Booth Type story/epic per the story note. | story note: 'Booth Type ... belong to OTHER stories' | No Booth Type story located; Standard/Premium/Corner classification data does not exist (ProductType = family only). Open Q: required, or BA artifact? |  | Booth Type (Standard, Premium, Corner, etc.) | Open §Order History → Story 13.3 | Not shipped — Not Deliverable (see Open Questions)
13.3-g | Booth section: Upgrade details (if any) | Blocked | Implement here | — | Booth Upgrade is owned by a separate Booth Upgrade story/epic per the story note ('Refer User Story Booth Upgrade'). | story note: 'Refer User Story Booth Upgrade' | Blocked on 'Booth Upgrade' user story — SBE - Exhibitor Store Application (search 'Booth Upgrade' / 'Upgrade Booth'). Upgrades modelled as fresh purchases; no upgrade detail on original order |  | Upgrade details (if any) / Refer User Story Booth Upgrade | Open §Order History → Story 13.3 | Not shipped — Blocked (see Open Questions)
13.3-h | Add-Ons section: per add-on Product Name, Quantity, Unit Price, Total Price | Deliverable | Implement here | — | Add-on lines are OrderItems with cart_item_type=addon carrying description, quantity, unit_price and amount. | exhibitor-backend-api/src/cart/helpers/cart.helpers.ts:48-68; admin-backend-api/prisma/schema.prisma:1935-1944 |  | [C2 cross-reference] OWNER — build here (GET /orders/:orderId — the read-only ownership-scoped order…); reused by other stories in this cluster. | Add-Ons Section For each add-on, the page shall show Product Name, Quantity, Unit Price, and Total Price. | Open §Order History → Story 13.3 | ✅ Shipped 2026-07-01 (PR #276)
13.3-i | Sponsorship section: per sponsorship Name, Quantity, Unit Price, Total Price | Deliverable | Implement here | — | Sponsorship lines are OrderItems with cart_item_type=sponsorship carrying description, quantity, unit_price and amount (cart_item_type is preserved verbatim by the materializer). | exhibitor-backend-api/src/cart/helpers/cart.helpers.ts:52-60; admin-backend-api/prisma/schema.prisma:1935-1944 |  | [C2 cross-reference] OWNER — build here (GET /orders/:orderId — the read-only ownership-scoped order…); reused by other stories in this cluster. | Sponsorship Section For each sponsorship, the page shall show Sponsorship Name, Quantity, Unit Price, and Total Price. | Open §Order History → Story 13.3 | ✅ Shipped 2026-07-01 (PR #276)
13.3-j | Financial Summary: Subtotal | Deliverable | Implement here | — | Order.subtotal written at checkout from the pricing recalculation (recomputed defensively via sumCartSubtotal). | exhibitor-backend-api/src/cart/services/cart.service.ts:1236; admin-backend-api/prisma/schema.prisma:1547 |  | [C2 cross-reference] OWNER — build here (GET /orders/:orderId — the read-only ownership-scoped order…); reused by other stories in this cluster. | Financial Summary The page shall clearly show Subtotal; Discount, Coupon Code details, or Gift Certificate (if applied); Booth Cleaning Fee (if applicable); Booth Setup Fee (if applicable); Total Saving Made; and Total Paid. | Open §Order History → Story 13.3 | ✅ Shipped 2026-07-01 (PR #276)
13.3-k | Financial Summary: Discount / Coupon Code details (if applied) | Deliverable | Implement here | — | The discount amount (Order.coupon_amount) is written at checkout. Order.coupon_code column EXISTS but the exhibitor cart checkout write-path does NOT populate it (order.create writes coupon_amount only); the coupon code STRING is recoverable via Order.cart_id -> Cart.coupon_code_id -> CouponCode.code (the same cart.coupon.code already surfaced in the cart response). Display achievable via that join. | exhibitor-backend-api/src/cart/services/cart.service.ts:1240 (coupon_amount written, coupon_code NOT written),850 (cart.coupon.code surfaced); admin-backend-api/prisma/schema.prisma:1548-1549 (coupon_code column exists / coupon_amount) |  | [C2 cross-reference] OWNER — build here (GET /orders/:orderId — the read-only ownership-scoped order…); reused by other stories in this cluster. | Discount, Coupon Code details, or Gift Certificate (if applied) | Open §Order History → Story 13.3 | ✅ Shipped 2026-07-01 (PR #276)
13.3-l | Financial Summary: Gift Certificate (if applied) | Deliverable (Shipped 2026-07-05, PR #303) | Implement here | GET /orders/:orderId financial_summary | Re-verified 2026-07-05 — a redemption producer now exists. captureGiftCertificateForOrder (external-api webhook.service.ts:2692->2739) writes GiftCertificateRedeem on payment success from the cart/booth path (:2289); checkout snapshots gift_certificate_purchase_id/code/discount onto the Order (cart.service.ts:1403-1406). Shipped as a gift_certificate_amount/gift_certificate_code line, disambiguated from the coupon by gift_certificate_purchase_id (mutually exclusive), fixing a prior coupon-mislabel. Read-side mapping only. | external-api-service/.../webhook.service.ts:2692-2739,2289; exhibitor-backend-api/src/cart/services/cart.service.ts:1403-1406; exhibitor-backend-api/src/orders/order-details.helpers.ts (buildFinancialSummary); commit 0aef5a1 |  |  | Discount, Coupon Code details, or Gift Certificate (if applied) | Open §Order History → Story 13.3 | Not shipped — Blocked (see Open Questions)
13.3-m | Financial Summary: Booth Cleaning Fee / Booth Setup Fee (if applicable) | Deliverable | Implement here | — | Order.setup_fees and cleaning_fees snapshots written at checkout (and also materialized as fee OrderItems via the cart line item_type). | exhibitor-backend-api/src/cart/services/cart.service.ts:1237-1238; admin-backend-api/prisma/schema.prisma:1577-1578 |  | [C2 cross-reference] OWNER — build here (GET /orders/:orderId — the read-only ownership-scoped order…); reused by other stories in this cluster. | Booth Cleaning Fee (if applicable); Booth Setup Fee (if applicable) | Open §Order History → Story 13.3 | ✅ Shipped 2026-07-01 (PR #276)
13.3-n | Financial Summary: Total Saving Made (actual vs sales price; via centralized billing service) | Deliverable | Implement here | — | Order.total_savings is computed and written at checkout from the (in-process) cart-pricing service. The value exists and is reconcilable; note there is no separate 'centralized billing service' module - savings is computed by cart-pricing.recalculate. | exhibitor-backend-api/src/cart/services/cart.service.ts:1220,1243; admin-backend-api/prisma/schema.prisma:1579 |  | [C2 cross-reference] OWNER — build here (GET /orders/:orderId — the read-only ownership-scoped order…); reused by other stories in this cluster. ¦ [C6 cross-reference] Mostly delivered by building 13.2 (Architectural decision/data-access pattern: read monetary f…). Residual: These are DIFFERENT fields from 13.2-k's Order.total: 13.3-n = total_savings, 13.3-o = paid_amount (Total Paid), 13.3-z = full reconciliation across subtotal/fees/savings/total-paid. Only the 'read from the Order record, do not recompute' principle is shared — the breakdown, the distinct fields and the reconciliation check are all genuine separate work, not redundant. | Total Saving Made shall be calculated from the actual price and the sales price of the products, by the centralized billing service. | Open §Order History → Story 13.3 | ✅ Shipped 2026-07-01 (PR #276)
13.3-o | Financial Summary: Total Paid | Deliverable | Implement here | — | Order.paid_amount is bumped by the webhook on successful charge (order.paid_amount.add(txPt.amount)); Order.total holds the order amount. Both available for display. | admin-backend-api/prisma/schema.prisma:1573 (paid_amount),1551 (total); external-api-service/src/modules/webhook/services/webhook.service.ts:2090-2098 |  | [C2 cross-reference] OWNER — build here (GET /orders/:orderId — the read-only ownership-scoped order…); reused by other stories in this cluster. ¦ [C6 cross-reference] Mostly delivered by building 13.2 (Architectural decision/data-access pattern: read monetary f…). Residual: These are DIFFERENT fields from 13.2-k's Order.total: 13.3-n = total_savings, 13.3-o = paid_amount (Total Paid), 13.3-z = full reconciliation across subtotal/fees/savings/total-paid. Only the 'read from the Order record, do not recompute' principle is shared — the breakdown, the distinct fields and the reconciliation check are all genuine separate work, not redundant. | Total Saving Made; and Total Paid. | Open §Order History → Story 13.3 | ✅ Shipped 2026-07-01 (PR #276)
13.3-p | Payment Details: Payment Method (e.g. Visa ending in 1234) | Deliverable | Implement here | — | PaymentTransaction.stripe_payment_method_id (written at checkout) maps to PaymentMethod (unique on stripe_payment_method_id) which carries brand/last4/type, populated when a card is added. Minor edge: a deleted card row would lose brand/last4. | exhibitor-backend-api/src/cart/services/cart.service.ts:1292 (PT.stripe_payment_method_id); admin-backend-api/prisma/schema.prisma:2067 (PT.stripe_payment_method_id),973,978-979 (PaymentMethod stripe_payment_method_id/brand/last4) |  | [C2 cross-reference] OWNER — build here (GET /orders/:orderId — the read-only ownership-scoped order…); reused by other stories in this cluster. | Payment Details The page shall show Payment Method (for example, Visa ending in 1234), Payment Date, Transaction Reference, a Download Invoice button, and the Payment Schedule | Open §Order History → Story 13.3 | ✅ Shipped 2026-07-01 (PR #276)
13.3-q | Payment Details: Payment Date | Deliverable | Implement here | — | PaymentTransaction.paid_at is set by the webhook on payment_intent.succeeded (buildPtSuccessUpdate). | admin-backend-api/prisma/schema.prisma:2072; external-api-service/src/modules/webhook/services/webhook.service.ts:2187-2201 (buildPtSuccessUpdate sets paid_at) |  | [C2 cross-reference] OWNER — build here (GET /orders/:orderId — the read-only ownership-scoped order…); reused by other stories in this cluster. | Payment Method (for example, Visa ending in 1234), Payment Date, Transaction Reference | Open §Order History → Story 13.3 | ✅ Shipped 2026-07-01 (PR #276)
13.3-r | Payment Details: Transaction Reference | Deliverable | Implement here | — | PaymentTransaction.stripe_charge_id / stripe_payment_intent_id are set by the webhook (buildPtSuccessUpdate); usable as transaction reference. | admin-backend-api/prisma/schema.prisma:2065-2066; external-api-service/src/modules/webhook/services/webhook.service.ts:2194-2195 |  | [C2 cross-reference] OWNER — build here (GET /orders/:orderId — the read-only ownership-scoped order…); reused by other stories in this cluster. | Payment Method (for example, Visa ending in 1234), Payment Date, Transaction Reference, a Download Invoice button | Open §Order History → Story 13.3 | ✅ Shipped 2026-07-01 (PR #276)
13.3-s | Payment Details / Additional: Download Invoice PDF button | Deliverable (Shipped 2026-07-05, PR #300) | Implement here | GET /orders/:orderId/invoice | A-vs-B decision resolved -> Option B (serve persisted Invoice rows, product-gated, paid-only). Shipped as a net-new order-level GET /orders/:orderId/invoice (resolves the order's latest issued invoice, booth/product layout via pdfkit, cached to invoice.invoice_pdf_url, ownership-scoped; 404 for foreign/unknown/subscription/PPL/no-invoice). Details response carries a can_download_invoice flag. | exhibitor-backend-api/src/orders/order-invoice-document.service.ts; orders.controller.ts:121; order-details.service.ts:177 (can_download_invoice) |  | [C3 build-once-reuse] Mostly delivered by building 13.2 (GET /orders/:orderId/invoice — order-scoped invoice PDF (ne…). Residual: 13.3-s (Download Invoice button) is fully covered by the shared invoice endpoint. 13.3-ac is COMPOUND ('signed agreement AND invoice PDF downloadable') and only its invoice half is covered here; its signed-agreement half is served by the single-story GET /orders/:orderId/agreement (13.3-only, no cluster) and is itself Partial — only the captured signature image + acceptance metadata exist, no composed agreement document is generated. That agreement work is separate and not redundant. | a Download Invoice button / Additional The page shall provide a Download Invoice PDF option and Onsite contact information. | Open §Order History → Story 13.3 | Not shipped — Deferred (see Open Questions)
13.3-t | Payment Details: Payment Schedule set by salesperson (Date, Amount, Payment method) | Blocked | Implement here | — | Payment Schedule Visibility is owned by a separate story per the story note ('Refer User Story Payment Schedule Visibility'). Exhibitor self-checkout is always payment_mode=full / 1 installment so no schedule is produced here anyway; salesperson schedules live in CartPaymentScheduleEntry under Order Management. | story note: 'Refer User Story Payment Schedule Visibility'; exhibitor-backend-api/src/cart/services/cart.service.ts:1245-1246 (payment_mode=full, installments_count=1); admin-backend-api/prisma/schema.prisma:2854 (CartPaymentScheduleEntry) | Blocked on SBE-1154 'Payment Schedule Visibility' (backlog/To Do, Prantik Saha); producers SBE-1109/1111/1112 In Progress SBE Sprint 5 -> OM 24.8. CartPaymentScheduleEntry is cart-only, not linked to Order. Option (b): PaymentTransaction split schedule deliverable now |  | the Payment Schedule (as set by the salesperson while placing the order, if the order was created by a salesperson) with Date, Amount, and Payment method. Refer User Story Payment Schedule Visibility | Open §Order History → Story 13.3 | Not shipped — Blocked (see Open Questions)
13.3-u | Agreement: 'You accepted the Event Agreement' + date and time of acceptance | Deliverable | Implement here | — | OrderAgreement (terms_accepted=true, signer names, signed_at default now) is written atomically at checkout; acceptance statement and timestamp displayable. | exhibitor-backend-api/src/cart/services/cart.service.ts:1268-1279; admin-backend-api/prisma/schema.prisma:1607-1623 (OrderAgreement) |  | [C2 cross-reference] OWNER — build here (GET /orders/:orderId — the read-only ownership-scoped order…); reused by other stories in this cluster. | Agreement Confirmation The page shall show "You accepted the Event Agreement", the date and time of acceptance, and a Download signed agreement option. | Open §Order History → Story 13.3 | ✅ Shipped 2026-07-01 (PR #276)
13.3-v | Agreement: Download signed agreement option | Deliverable (existing endpoint; FE wiring only) | Implement here | GET /agreement/signed/:orderId/download (existing) | Re-verified 2026-07-05 — complete and booth-covered. GET /agreement/signed/:orderId/download (agreement.controller.ts:154 -> buildSignedBoothContractDocx) routes booth vs PPL on cart_id (isBoothOrder), ownership-scoped (company_id, 404 on foreign), composes real terms text + captured signature into a DOCX, caches to OrderAgreement.signed_agreement_url. No stubs; last polished 39f82da (2026-07-02), Kshitiz SBE-862/869. Deliverable by FE wiring — no 13.3 backend work. Non-blocking: DOCX-vs-PDF / is_manual_bypass / SBE-1158 reconcile. | exhibitor-backend-api/src/agreement/controllers/agreement.controller.ts:154; agreement.service.ts (buildSignedBoothContractDocx, isBoothOrder) | Reuses existing agreement endpoint (Kshitiz, SBE-862/869); non-blocking: reconcile SBE-1158 |  | a Download signed agreement option | Open §Order History → Story 13.3 | Not shipped — Blocked (see Open Questions)
13.3-w | Additional: Onsite contact information | Delivered (2026-07-06, PR #305) | Implement here | onsite_contacts on GET /orders/:orderId | Producer shipped 2026-07-02 and SBE-1169/1171 reached DEV DONE (Release 3), clearing the block. Delivered as a per-show onsite_contacts block on the details aggregate: one entry per show the order touches, each with the company's saved OnsiteBoothContact for that show via one (company_id, show_id) findMany, or contact:null when absent (no billing fallback, parity with SBE-1169). No Order FK needed — shows reached via OrderItem→ShowProduct→Show. Native reimplementation of the admin twin 24.6-l2 (not imported). No new endpoint/migration. Commit bedf05a. | story note: 'Refer User Story View Onsite Boot Contact'; admin-backend-api/prisma/schema.prisma:2684 (OnsiteBoothContact) | Blocked on SBE-1169 'View Onsite Boot Contact' (To Do, SBE Sprint 5, Ritam Mondal) + producer SBE-1165 'Onsite Booth Contacts Management' (backlog, Manish). OnsiteBoothContact has no producer + no order FK (keyed company_id+show_id) |  | Additional The page shall provide a Download Invoice PDF option and Onsite contact information. Refer User Story View Onsite Boot Contact | Open §Order History → Story 13.3 | Delivered 2026-07-06 — PR #305 → dev; producer SBE-1165 shipped; SBE-1169/1171 DEV DONE.
13.3-x | Ownership: only the owning Exhibitor can access order details, enforced on backend | Deliverable | Implement here | — | Exhibitor auth guards exist and orders carry company_id; the net-new endpoint scopes by the requester's company_id (same pattern used by ppl invoice download where Invoice.company_id is checked against the exhibitor's company). | exhibitor-backend-api/src/auth/guards/*; exhibitor-backend-api/src/ppl/services/ppl.service.ts:757-763 (findExhibitorCompanyOrFail + company_id ownership check); admin-backend-api/prisma/schema.prisma:1543 (Order.company_id) |  | [C2 cross-reference] OWNER — build here (GET /orders/:orderId — the read-only ownership-scoped order…); reused by other stories in this cluster. ¦ [C4 build-once-reuse] Mostly delivered by building 13.2 (Company-ownership scoping guard/predicate (auth guard + com…). Residual: Must apply the SAME predicate to GET /orders/:orderId AND to both sub-routes (/invoice, /agreement) — reuse the helper, but each new route still needs the guard wired plus a per-route 'wrong-company returns 404/403' test. Not zero, but no new logic. | Ownership Only the owning Exhibitor shall access the order details, enforced on the backend. | Open §Order History → Story 13.3 | ✅ Shipped 2026-07-01 (PR #276)
13.3-y | Conditional Display: upgrade/discount/coupon/gift cert/cleaning fee/setup fee shown only when applicable | Deliverable | Implement here | — | Presentation logic over already-written fields (coupon_amount, setup_fees, cleaning_fees, fee OrderItems). The gift-cert branch is governed by 13.3-l (Blocked) and the upgrade branch by 13.3-g (Out of Scope), but the conditional-display behaviour over written fields is achievable. | admin-backend-api/prisma/schema.prisma:1549,1577-1578; exhibitor-backend-api/src/cart/helpers/cart.helpers.ts:97-112 (fee-line classification) |  | [C2 cross-reference] OWNER — build here (GET /orders/:orderId — the read-only ownership-scoped order…); reused by other stories in this cluster. | Conditional Display Upgrade details, discount or coupon or gift certificate, cleaning fee, and setup fee shall appear only when applicable. | Open §Order History → Story 13.3 | ✅ Shipped 2026-07-01 (PR #276)
13.3-z | Financial Accuracy: subtotal, fees, total saving, total paid reconcile | Deliverable | Implement here | — | All totals are persisted snapshots from the pricing recalc (subtotal, setup/cleaning fees, total_savings, total) plus webhook-bumped paid_amount; reconciliation is straightforward arithmetic over stored values. | exhibitor-backend-api/src/cart/services/cart.service.ts:1220,1236-1243 (pricing.recalculate snapshots) |  | [C2 cross-reference] OWNER — build here (GET /orders/:orderId — the read-only ownership-scoped order…); reused by other stories in this cluster. ¦ [C6 cross-reference] Mostly delivered by building 13.2 (Architectural decision/data-access pattern: read monetary f…). Residual: These are DIFFERENT fields from 13.2-k's Order.total: 13.3-n = total_savings, 13.3-o = paid_amount (Total Paid), 13.3-z = full reconciliation across subtotal/fees/savings/total-paid. Only the 'read from the Order record, do not recompute' principle is shared — the breakdown, the distinct fields and the reconciliation check are all genuine separate work, not redundant. | Financial Accuracy Subtotal, fees, total saving, and total paid shall reconcile, with Total Saving Made and totals computed by the centralized billing service. | Open §Order History → Story 13.3 | ✅ Shipped 2026-07-01 (PR #276)
13.3-aa | Per-Item Lines: each add-on and sponsorship line shows quantity, unit price and a correct total | Deliverable | Implement here | — | OrderItem stores quantity, unit_price and amount (= qty x effective unit price) per line. | admin-backend-api/prisma/schema.prisma:1936-1939; exhibitor-backend-api/src/cart/helpers/cart.helpers.ts:57-59 |  | [C2 cross-reference] OWNER — build here (GET /orders/:orderId — the read-only ownership-scoped order…); reused by other stories in this cluster. | Per-Item Lines Each add-on and sponsorship line shall show quantity, unit price, and a correct total. | Open §Order History → Story 13.3 | ✅ Shipped 2026-07-01 (PR #276)
13.3-ab | Net-new GET order-details endpoint aggregating header/booth/add-ons/sponsorships/financial/payment/agreement sections | Deliverable | Implement here | — | No order/order-history module exists yet, but all read primitives (Order + orderItems + agreement + paymentTransactions + invoices + show/product joins) are built; the aggregating endpoint is net-new on working data. | codebase_map.md KEY STRUCTURAL FACTS (no order module); admin-backend-api/prisma/schema.prisma:1586-1600 (Order relations: orderItems/invoices/agreement/paymentTransactions) |  | [C2 cross-reference] OWNER — build here (GET /orders/:orderId — the read-only ownership-scoped order…); reused by other stories in this cluster. | The order details page shall present a complete, read-only summary organized into clear sections: Header: Order ID, date and time, event name, city, event dates, payment status Booth/Workshop Pavilion: number, size, type, price, upgrade details, subtotal Add-Ons: name, quantity, unit price, total per item Sponsorships: name, quantity, unit price, total per item Financial Summary: subtotal, discount/coupon/gift certificate, fees, total saving, total paid Payment Details: method, date, transaction reference, payment schedule, download invoice Agreement: acceptance statement, date and time, download signed agreement Onsite contact information | Open §Order History → Story 13.3 | ✅ Shipped 2026-07-01 (PR #276)
13.3-ac | Documents: signed agreement and invoice PDF shall be downloadable | Deliverable (both halves) | Implement here | GET /orders/:orderId/invoice + GET /agreement/signed/:orderId/download | Compound. Invoice half shipped (13.3-s, GET /orders/:orderId/invoice, Option B). Signed-agreement half Deliverable via the existing GET /agreement/signed/:orderId/download DOCX endpoint (13.3-v) — FE wiring only. Both documents downloadable; only non-blocking agreement confirmations remain (DOCX/is_manual_bypass/SBE-1158). | exhibitor-backend-api/src/orders/order-invoice-document.service.ts (13.3-s); agreement.controller.ts:154 (13.3-v) |  | [C3 build-once-reuse] Mostly delivered by building 13.2 (GET /orders/:orderId/invoice — order-scoped invoice PDF (ne…). Residual: 13.3-s (Download Invoice button) is fully covered by the shared invoice endpoint. 13.3-ac is COMPOUND ('signed agreement AND invoice PDF downloadable') and only its invoice half is covered here; its signed-agreement half is served by the single-story GET /orders/:orderId/agreement (13.3-only, no cluster) and is itself Partial — only the captured signature image + acceptance metadata exist, no composed agreement document is generated. That agreement work is separate and not redundant. | Documents The invoice PDF and signed agreement shall be downloadable. | Open §Order History → Story 13.3 | Not shipped — Blocked (see Open Questions)

## Endpoints
Method | Path | Purpose | Serves Req(s) | Shared With
GET | /orders/:orderId | Order-details aggregate — NESTED BY SHOW (SBE-1147, 2026-07-26): shows[] each carrying its own booths/add-ons/sponsorships + one onsite_contact, a nullable top-level 'unassigned' bucket, per-line product_name/purchased_name, per-booth setup_fee/cleaning_fee, plus financial summary, payment details, agreement, additional_purchases[].show. PRODUCT-GATED (subscription/ppl_addon -> 404). Ownership-scoped. | 13.3-a, 13.3-b, 13.3-d, 13.3-e, 13.3-h, 13.3-i, 13.3-j, 13.3-k, 13.3-m, 13.3-n, 13.3-o, 13.3-p, 13.3-q, 13.3-r, 13.3-u, 13.3-x, 13.3-y, 13.3-z, 13.3-aa, 13.3-ab | Shared with 13.2 Order Listing Table (View action navigates here). Distinct DTO from 13.2 (OrderDetailShowDto, not the shared OrderShowDto).
GET | /orders/invoices/:id (invoice rework SBE-1146, 2026-07-17, PRs #346/#347) | Download a SPECIFIC invoice PDF by invoice id (replaced the old latest-only /orders/:orderId/invoice) — Option B: resolves the persisted Invoice (product-gated, paid-only), renders the booth/product layout, returns a URL. Ownership-scoped; 404 for foreign/unknown/soft-deleted/non-product. Ids come from the list route. | 13.3-s, 13.3-ac (invoice half) | Shared with 13.2 Order Listing Table Invoice action.
GET | /orders/:orderId/invoices (NEW, invoice rework SBE-1146, 2026-07-17) | List every invoice on one product order (newest first): id, invoice_number, status, total, paid_at, created_at. Feeds ids to GET /orders/invoices/:id. Owned order with no invoice yet -> 200 empty list; foreign/unknown/non-product -> 404. | 13.3-s | Supplies the FE's invoice ids for split orders (older invoices now reachable).
GET | /agreement/signed/:orderId/download (existing) | Download the composed signed-agreement DOCX (terms + captured signature). Already exists in the agreement module and covers booth/product orders — 13.3 reuses it (no new /orders/:orderId/agreement route). Re-verified complete 2026-07-05 (Kshitiz, SBE-862/869); non-blocking: reconcile SBE-1158. | 13.3-v, 13.3-ac

## Open Questions
Req | Item | Verdict | Open Question / What is needed | Dependency (blocking story + Jira) | Assignee | Sprint / Jira status | Decision / Current direction
13.3-c | Booth Number | Not Deliverable | Is a physical stall/booth number required on the details page? If yes, from where (it is assigned externally after purchase)? | No producing story. Lead only: 'Booth Sign Print Page' (Confluence: SBE - Admin Panel Page 2) references company+show 'assigned booth numbers' (not order-linked). | — | — (no story / parked) | PARKED. No order-linked booth-number source exists (notification-template.seeder.ts:668 = assigned externally, separate notification). Awaiting team direction. | client dependency - as when client discusses about social table
13.3-f | Booth Type (Standard/Premium/Corner) | Not Deliverable | Is Booth Type actually required here, or was it added arbitrarily by the BA? | No story located. Classification data does not exist (ProductType = product family only; purchased-booths 'boothType' is derived size). | — | — (no story / parked) | PARKED. Not deliverable on current data; needs an upstream classification if genuinely required. | client dependency - as when client discusses about social table
13.3-g | Booth Upgrade ('Upgrade details, if any') | Blocked | Is 'Upgrade details' required on this page, and what would it show (upgrades are fresh purchases)? | 'Booth Upgrade' user story — Confluence: SBE - Exhibitor Store Application (search 'Booth Upgrade' / 'Upgrade Booth'). No discrete Jira key found. | — | — (no sprint found) | BLOCKED on the Booth Upgrade story. No 'upgrade detail' is stored on the original order today. | next sprint
13.3-l | Gift Certificate line | Deliverable (Shipped 2026-07-05) | Awaiting a producer that redeems a gift certificate against an order (writes GiftCertificateRedeem). | Story 12.4 'Gift Cart Redemption' (Confluence: SBE - Exhibitor Store Application); Jira SBE-1069 'Gift Certificate Purchase and Redemption' (Epic). | Unassigned | To Do — backlog (no sprint) | SHIPPED 2026-07-05 (PR #303). Producer re-verified: captureGiftCertificateForOrder in the webhook writes GiftCertificateRedeem on payment success; Order snapshots the voucher at checkout. Gift-certificate line added, disambiguated from coupon (fixes a prior mislabel). | manish
13.3-s | Download Invoice PDF | Deliverable (Shipped 2026-07-05) | DECISION: invoice semantics A vs B — A = generate an order-level PDF from Order+OrderItems (any order, incl. unpaid); B = serve only persisted Invoice rows (paid orders only). | None — a team decision (inherited from 13.2's invoice deferral). pdfkit renderer exists but is subscription/Invoice-shaped. | 13.3 team | Deferred — decision pending | SHIPPED 2026-07-05 (PR #300) — Option B (GET /orders/:orderId/invoice, product-gated, paid-only) + can_download_invoice flag. | ksitish
13.3-t | Payment Schedule (salesperson-set) | Blocked | Salesperson payment plan must be written, LINKED TO THE ORDER, and surfaced to the exhibitor (today CartPaymentScheduleEntry is cart-only, no Order FK). | Visibility: SBE-1154 'Payment Schedule Visibility'. Producers: SBE-1109 'Shared Cart Payment Plan', SBE-1111 'Payment Schedule Management', SBE-1112 'Payment Plan Date Validation' -> OM 24.8. (SBE-1132 'Payment Plan Management' -> 24.8.) | SBE-1154: Prantik Saha; SBE-1109/1111/1112: Suman Paul | SBE-1154: To Do, backlog. SBE-1109/1111/1112: In Progress, SBE Sprint 5 (15 Jun-2 Jul). | BLOCKED on SBE-1154 (+ producers). Option (b): the /payments/checkout split flow already writes a per-installment schedule in PaymentTransaction - deliverable now if the team wants it. | next sprint
13.3-v | Download signed agreement | Deliverable (non-blocking confirmations) | Confirm the EXISTING composed-DOCX download endpoint (GET /agreement/signed/:orderId/download) is complete/final; is DOCX acceptable (vs PDF)? Is SBE-1158 superseded by it? | Code authored by Kshitiz under SBE-862 'Exhibitor Agreement & Checkout Review' + SBE-869 'Signed Agreement Storage'. Separate story SBE-1158 'Download Agreement Option'. | SBE-862/869: Kshitiz; SBE-1158: Prantik Saha | SBE-862/869: In Progress, SBE Sprint 5. SBE-1158: To Do, backlog. | DELIVERABLE via the existing GET /agreement/signed/:orderId/download endpoint (Kshitiz) — re-verified complete, covers booth orders, ownership-scoped. FE wiring only. Non-blocking confirmations: DOCX-vs-PDF / is_manual_bypass / reconcile SBE-1158. | ksitish
13.3-w | Onsite Contact information | Resolved — Delivered (2026-07-06) | Needs a producer for OnsiteBoothContact AND an order-linkage (today keyed company_id+show_id, no Order FK). | SBE-1169 'View Onsite Boot Contact' + SBE-1171 'Edit On-Site Booth Contact'; producer/management SBE-1165 'Onsite Booth Contacts Management' (Epic SBE-1075 Exhibitor Onboarding). | SBE-1169/1171: Ritam Mondal; SBE-1165: Manish Gun | SBE-1169/1171: To Do, SBE Sprint 5. SBE-1165: To Do, backlog. | BLOCKED on SBE-1169 (+ SBE-1165). Confluence Edit story intends per-order onsite contact, so those stories add both the producer and the order-linkage. | next sprint
13.3-ac | Documents downloadable (invoice + agreement) | Deliverable (both halves) | Compound: invoice PDF downloadable AND signed agreement downloadable. | Invoice half -> 13.3-s (Deferred, A-vs-B). Agreement half -> 13.3-v (Blocked; Kshitiz SBE-862/869; reconcile SBE-1158). | see 13.3-s / 13.3-v | see 13.3-s / 13.3-v | DELIVERABLE — invoice half shipped (13.3-s); agreement half via existing endpoint (13.3-v). Both documents downloadable; only non-blocking agreement confirmations remain. | ksitish

## Cross-Epic Dependencies
Dependency | Needed For | Likely Owner
[RESOLVED 2026-07-05] Gift certificate redemption producer now exists (captureGiftCertificateForOrder in the external-api webhook writes GiftCertificateRedeem on payment success; Order snapshots the voucher at checkout), so 13.3-l shipped (PR #303). No longer a cross-epic dependency — Story 12.4 / SBE-1069 delivered the write-path. | 13.3-l (Gift Certificate line in Financial Summary) | Story 12.4 'Gift Cart Redemption' (Exhibitor Store App); Jira SBE-1069 (Epic, To Do, unassigned)
Booth Type attribute (Standard/Premium/Corner) on the order's booth line | 13.3-f (booth section Booth Type) | No story located; classification data does not exist (now Not Deliverable, not just other-story)
Booth Upgrade details captured on the order | 13.3-g (booth section Upgrade details) | 'Booth Upgrade' user story (SBE - Exhibitor Store Application; search 'Booth Upgrade'/'Upgrade Booth')
Salesperson-set payment schedule visibility (CartPaymentScheduleEntry surfaced to exhibitor) | 13.3-t (Payment Schedule in Payment Details) | SBE-1154 Payment Schedule Visibility (backlog, Prantik) + producers SBE-1109/1111/1112 (Sprint 5) -> OM 24.8; needs order-linkage
Onsite contact information at the order level — RESOLVED 2026-07-06. SBE-1169/1171 DEV DONE (Release 3) + producer SBE-1165 shipped 2026-07-02. No Order FK needed ((company_id, show_id) join over the order's shows); 13.3-w delivered as an onsite_contacts block (PR #305). | 13.3-w (delivered) | SBE-1169 View Onsite Boot Contact (Sprint 5, Ritam) + SBE-1165 Onsite Booth Contacts Management (backlog, Manish); needs producer + order-linkage

## Implementation Status
Section | Detail
Status | ✅ Implemented & merged to dev. Core aggregate 2026-07-01; invoice download 13.3-s 2026-07-05; gift-cert line 13.3-l 2026-07-05; onsite contacts 13.3-w 2026-07-06. Post-ship reworks of GET /orders/:orderId: invoice endpoints rework (SBE-1146) 2026-07-17; order-details nesting redesign (SBE-1147) 2026-07-26.
Branch | feature/SBE-1146-order-listing-table (shared with 13.2 — no separate branch; 13.3 has no own Jira key).
SBE ticket | SBE-1146 (commit scope; taken from the 13.2 branch).
Commits | 981ebf2 (feat: order-details endpoint), e79a1eb (fix: SonarQube S7748 zero-fraction examples).
PR | #276 → dev — merged (https://bitbucket.org/unified-dev-cls-a/exhibitor-backend-api/pull-requests/276).
Swagger tag | Orders (GET /orders/:orderId).
Build gates (npm ci / prisma generate / typecheck / lint / test:cov / build) | ✅ green — pre-push (119 suites / 1731 tests, lint, typecheck, build); Bitbucket pipeline #401 SUCCESSFUL; SonarQube quality gate PASS (12 new-code S7748 smells fixed).
Live smoke | ✅ passed 2026-07-01 — 200 owner / 404 foreign+missing / 400 bad input / 401 no-auth; sections, coupon join, payment-method lookup, settled-only payments, agreement, ownership verified; seeded graph torn down clean.
Confirmed build scope (24 Deliverable) | ✅ Shipped by us: GET /orders/:orderId aggregate (20) + 13.3-s invoice download + 13.3-l gift-certificate line. Deliverable via existing agreement endpoint: 13.3-v, 13.3-ac.
Remaining | 22 Deliverable shipped by us; 13.3-v/-ac Deliverable via the existing /agreement/signed/:orderId/download endpoint (FE wiring only). 5 non-Deliverable remain (Open Questions).
Not ready — see Open Questions register | 3 Blocked (13.3-g, -t, -w) + 2 Not Deliverable (13.3-c, -f).
External dependencies | See the Cross-Epic Dependencies sheet.
Out of API scope | Front-end wiring (row-to-detail navigation, document download buttons) and anything marked Out of Scope.
Deployment note | Requires admin migration 20260618120000_add_order_item_tree_and_cart_type (adds order_items.cart_item_type + parent_order_item_id) applied to the target DB — applied to the local dev DB via `migrate deploy` on 2026-07-01.
Follow-on: 13.3-s invoice download | PR #300 (feature/SBE-1125), commits 42b23e4 + 8af6923. Pre-push gate green; pipeline PASS incl. SonarQube; live smoke passed.
Follow-on: 13.3-l gift-certificate line | PR #303 (feature/SBE-1146-order-listing-table), commit 0aef5a1. Pre-push gate green (2082 tests, 80.03% branch cov); pipeline #436 SUCCESSFUL incl. SonarQube; boot smoke passed against live Postgres (seeded rows torn down).
Follow-on: SBE-1146 invoice endpoints rework (2026-07-17) | PRs #346/#347 (fix/SBE-1146-invoice-download-by-invoice-id), commit 126cffe -> dev. Replaced latest-only GET /orders/:orderId/invoice with GET /orders/invoices/:id (download a specific invoice by id; wire param 'id' rides global id-crypto) + NEW GET /orders/:orderId/invoices (per-order list, newest-first; 200 empty when none). Deleted the 'latest' orderBy; ownership via order.company_id/order_type=product/deleted_at=null. New DTOs OrderInvoiceListItemDto + OrderInvoiceListResponseDto. All in src/orders/; no schema/shared change. Pre-push gate + Bitbucket pipeline + SonarQube gate green.
Follow-on: SBE-1147 order details nesting redesign (2026-07-26) | PR #372 (feature/SBE-1147-change-for-ui-design), merge eea6713, commit 20ce757 -> dev. Response-shape only (no requirement verdicts change). (a) Product gate: order_type=product on the ownership findFirst -> subscription/ppl_addon 404 (closes SBE-1621 asymmetry). (b) Nested by show: flat booths/add_ons/sponsorships/onsite_contacts replaced by shows[] (each carries its booths/sponsorships/add_ons + one onsite_contact); unresolvable-show lines go to a nullable top-level 'unassigned' bucket (logged, never dropped); attribution = own showProduct.show_id else one hop up parent. (c) Line naming: product_name (live) + purchased_name (renamed snapshot). (d) Per-booth setup_fee/cleaning_fee folded from fee children. (e) additional_purchases[].show:{id} (nullable). New DTOs OrderDetailShowDto/AdditionalPurchaseShowDto/OrderUnassignedItemsDto; orphan OrderOnsiteContactDto deleted; OrderShowDto untouched (13.2-shared). 6 files, all src/orders/; no schema/migration/new endpoint. Pre-push gate green (2823 tests, 81.32% branch cov); live smoke passed (nested 2-show + subscription->404, rolled back clean); SonarQube gate red only on a pre-existing non-diff issue (attendee.service.ts:161, owned elsewhere), merge approved + fixed on dev ec93d31.