## Summary
Story | Title | Deliverable | Partial | Blocked | Not Deliverable | Out of Scope | Total | To Implement (net) | Build Status | # Endpoints | # Open Qs
13.1 | Order History | 5 | 0 | 0 | 0 | 1 | 6 | 0 | Delivered by 13.2 | 1 | 1
13.2 | Order Listing Table | 13 | 0 | 0 | 0 | 1 | 14 | 13 | 13 to build | 3 | 1
13.3 | Order Details Page | 21 | 2 | 1 | 1 | 4 | 29 | 25 | 25 to build (+ post-ship reworks SBE-1146 invoice endpoints 2026-07-17 & SBE-1147 nesting 2026-07-26) | 4 | 3
TOTAL | 3 stories | 39 | 2 | 1 | 1 | 6 | 49 | 38 | net items to build (excl. covered/out-of-scope)

## Endpoint Catalog
Method | Path | Purpose | Stories | Requirements | Notes
GET | /orders | Authenticated exhibitor's company-scoped, paginated order listing (product/booth orders only, past+current; SBE-1621) returning Order ID, date, derived order-level payment status (Paid in Full / Partially Paid / Unpaid), grouped associated shows, total from billing, per-row action-availability flags (view/invoice always; pay when not paid in full), and empty-state. | 13.1, 13.2 | 13.1-a, 13.1-b, 13.1-c, 13.1-d, 13.1-e, 13.2-a, 13.2-b, 13.2-c, 13.2-d, 13.2-e, 13.2-h, 13.2-i, 13.2-j, 13.2-k, 13.2-l, 13.2-m | Single canonical listing primitive. 13.1 (Order History container page) introduces NO separate route — its invented 'GET /order-history' was removed; ownership scoping, backend enforcement, past+current completeness and empty-state are behaviors/guards ON this same endpoint. Reuses existing PPL listOrderHistory pagination + findExhibitorCompanyOrFail scoping.
GET | /orders/:orderId | Read-only Order Details aggregate — NESTED BY SHOW (SBE-1147, 2026-07-26): shows[] each with its booths/add_ons/sponsorships + onsite_contact, plus financial_summary, settled payments[], agreement, additional_purchases[].show, nullable 'unassigned' bucket, can_download_invoice. PRODUCT-GATED (subscription/ppl_addon -> 404). | 13.2, 13.3 | 13.2-f, 13.3-a, 13.3-b, 13.3-d, 13.3-e, 13.3-h, 13.3-i, 13.3-j, 13.3-k, 13.3-m, 13.3-n, 13.3-o, 13.3-p, 13.3-q, 13.3-r, 13.3-u, 13.3-x, 13.3-y, 13.3-z, 13.3-aa, 13.3-ab | Navigated from a row in the GET /orders listing. The 13.2 'View action opens the detailed order summary' requirement (13.2-f) reuses this endpoint — no separate route in 13.2. ¦ SBE-1147 (2026-07-26, PR #372) restructured the response nested-by-show + product-gated; DTO is OrderDetailShowDto (distinct from the 13.2-shared OrderShowDto).
GET | /orders/invoices/:id | Download a SPECIFIC invoice PDF by invoice id (pdfkit render + signed URL), Option B / product-gated / paid-only. Replaced the old latest-only /orders/:orderId/invoice (invoice rework SBE-1146, 2026-07-17). | 13.2, 13.3 | 13.2-g, 13.3-s, 13.3-ac | Shared by the 13.2 listing Invoice action and the 13.3 details-page Download Invoice button — one endpoint, not two. ¦ SBE-1146 rework: per-invoice download by id (was latest-only); ids come from GET /orders/:orderId/invoices.
GET | /orders/:orderId/invoices | List every invoice on one product order (newest first: id, invoice_number, status, total, paid_at, created_at); 200 empty list when none yet. Feeds ids to GET /orders/invoices/:id. | 13.3 | 13.3-s | NEW in the invoice rework (SBE-1146, 2026-07-17) — makes split orders' older invoices reachable.
GET | /orders/:orderId/agreement | Download the stored signed agreement (PDF / signature record + acceptance metadata) for the order. | 13.3 | 13.3-v, 13.3-ac | Distinct document from the invoice — NOT merged with /orders/:orderId/invoice. Only 13.3 uses it.

## Build Consolidation
Cluster | Type | Recommendation | Conf | Build-First (owner) | Shared Build Unit (build once) | Members — relation & residual delta | Effort Saved | Evidence
C1 | subsumed-story | fold | high | 13.2 | GET /orders — the single canonical company-scoped, paginated exhibitor order-listing endpoint (reuses ppl.service listOrderHistory pagination + findExhibitorCompanyOrFail company scoping + purchased-booths buildOrderGroup multi-show grouping) | • 13.1 [13.1-a, 13.1-b, 13.1-c, 13.1-d, 13.1-e, 13.1-f] — subset; residual: none. Verified 1:1: 13.1-a (list all orders in one place) + 13.1-d (past AND current completeness) = 13.2-a; 13.1-b + 13.1-c (own-orders ownership + backend enforcement) = 13.2-j (also tracked as cross-cutting in C4); 13.1-e (empty state) is the one formerly-unique 13.1 requirement and was already folded into 13.2 as 13.2-m; 13.1-f (order-level actions, verdict Out-of-Scope, text explicitly 'Refer User Story Order Listing Table') maps to 13.2's per-row View/Invoice/Pay-availability actions (13.2-f/13.2-g/13.2-h). 13.1 introduces no independent route or logic. • 13.2 [13.2-a, 13.2-j, 13.2-m] — subset; residual: 13.2 is the primary owner and is built in full; nothing extra is owed to 13.1 once 13.2 (incl. 13.2-m empty state) is built and verified. | Eliminates a second listing endpoint/route (the invented GET /order-history was correctly removed) plus a duplicate page-level review of ownership/completeness/empty-state. 13.1 needs zero separate implementation and zero separate QA pass once 13.2 is verified. | Endpoint catalog GET /orders stories=[13.1,13.2]; reuses ppl.service listOrderHistory (exhibitor-backend-api/src/ppl/services/ppl.service.ts:916 controller / service) + findExhibitorCompanyOrFail company scoping (ppl.service.ts) + buildOrderGroup grouping (exhibitor-backend-api/src/purchased-booths/purchased-booths.service.ts:147)
C2 | shared-implementation | cross-reference | high | 13.3 | GET /orders/:orderId — the read-only ownership-scoped order-details aggregate endpoint | • 13.2 [13.2-f] — shares-endpoint; residual: none on the backend — the View action navigates a listing row to GET /orders/:orderId; building 13.3's details endpoint delivers 13.2-f entirely. Only the front-end row-to-detail wiring is outside API scope. • 13.3 [13.3-a, 13.3-b, 13.3-d, 13.3-e, 13.3-h, 13.3-i, 13.3-j, 13.3-k, 13.3-m, 13.3-n, 13.3-o, 13.3-p, 13.3-q, 13.3-r, 13.3-u, 13.3-x, 13.3-y, 13.3-z, 13.3-aa, 13.3-ab] — shares-endpoint; residual: 13.3 owns the entire aggregate build (header/booth/add-on/sponsorship line items, financial summary, payment details + reconciliation, agreement acceptance). This is the substantive work; 13.2-f is a free rider on it. Recommendation is cross-reference, NOT fold, because 13.3 is a large independent story — only 13.2-f collapses into it. | Avoids speccing/building a separate 'order summary' endpoint for the 13.2 View action; one details endpoint is reviewed once and 13.2-f is marked delivered-by-13.3. | Endpoint catalog GET /orders/:orderId stories=[13.2,13.3], 13.2-f mapped to it; underlying data written by cart checkout write-path (exhibitor-backend-api/src/cart/services/cart.service.ts:1265 + cart/helpers/cart.helpers.ts:33 materializeCartToOrder)
C3 | shared-implementation | build-once-reuse | high | 13.2 | GET /orders/:orderId/invoice — order-scoped invoice PDF (net-new order→Invoice resolution) reusing the existing ppl.service pdfkit renderer + S3 signed-URL path | • 13.2 [13.2-g] — shares-endpoint; residual: none beyond the shared endpoint — the listing Invoice action calls the same GET /orders/:orderId/invoice. • 13.3 [13.3-s, 13.3-ac] — shares-endpoint; residual: 13.3-s (Download Invoice button) is fully covered by the shared invoice endpoint. 13.3-ac is COMPOUND ('signed agreement AND invoice PDF downloadable') and only its invoice half is covered here; its signed-agreement half is served by the single-story GET /orders/:orderId/agreement (13.3-only, no cluster) and is itself Partial — only the captured signature image + acceptance metadata exist, no composed agreement document is generated. That agreement work is separate and not redundant. | One invoice endpoint instead of two; single review of the order→Invoice resolution + pdfkit/signed-URL render serves both the listing button and the details-page button (and any split-installment invoice variants). | Endpoint catalog GET /orders/:orderId/invoice stories=[13.2,13.3]; existing renderer downloadInvoicePdf at exhibitor-backend-api/src/ppl/controllers/ppl.controller.ts:1038 (delegates to ppl.service) — keyed on invoiceId, so order→Invoice resolution is the only net-new piece. Invoice rows written by external-api webhook for cart-flow orders.
C4 | duplicate-requirement | build-once-reuse | high | 13.2 | Company-ownership scoping guard/predicate (auth guard + company_id WHERE via findExhibitorCompanyOrFail) applied uniformly to every /orders* endpoint | • 13.1 [13.1-b, 13.1-c] — duplicate; residual: none — fully delivered by the listing endpoint's scoping (= 13.2-j); consistent with the C1 fold. • 13.2 [13.2-j] — duplicate; residual: Canonical owner of the scoping predicate on GET /orders. Designing and security-reviewing it once is the substantive work. • 13.3 [13.3-x] — duplicate; residual: Must apply the SAME predicate to GET /orders/:orderId AND to both sub-routes (/invoice, /agreement) — reuse the helper, but each new route still needs the guard wired plus a per-route 'wrong-company returns 404/403' test. Not zero, but no new logic. | Design and security-review the ownership rule once; the other stories assert reuse plus a per-route guard test rather than re-deriving the rule. | findExhibitorCompanyOrFail pattern in exhibitor-backend-api/src/ppl/services/ppl.service.ts (used at lines 93,148,217,248,301,...); applied per-route on GET /orders and /orders/:orderId per catalog notes
C5 | shared-implementation | build-once-reuse | medium | 13.2 | A NET-NEW read-time order-level payment-status derivation mapping {status, paid_amount, paid_in_full_at, + installment/overdue rollup} → Paid in Full / Partially Paid / Unpaid. Built once and consumed by both the listing row and the details header. | • 13.2 [13.2-c, 13.2-e] — shares-logic; residual: Owner of the derivation. 13.2-e (an Overdue installment plan must roll the order up to not-fully-paid) lives inside the same computation and requires reading PaymentTransaction.due_date/status — this is the substantive part and is NOT covered by any existing write-path. • 13.3 [13.3-a] — shares-logic; residual: none on the status computation — the details header 'Payment Status (e.g. Paid in Full)' is the identical derived value (including the overdue rollup). 13.3-a's other header fields (Order ID, date/time) are trivial passthroughs and not part of this shared unit. | Write and test the Paid/Partially/Unpaid derivation (incl. overdue rollup) once; the details header consumes the identical computed field instead of re-implementing it. | external-api computeNewOrderStatus (external-api-service/src/modules/webhook/services/webhook.service.ts:2245) is only a WRITE-PATH producing the stored Order.status (completed/partially_paid) and does NOT handle overdue — it is an input, not the reused unit. paid_in_full_at written at webhook.service.ts:2103. The shared read-time display derivation is net-new; hence medium confidence.
C6 | duplicate-requirement | cross-reference | low | 13.2 | Architectural decision/data-access pattern: read monetary figures (Order.total, total_savings, paid_amount, fees, coupon) directly from the billing-owned Order record rather than recomputing client-side. Not a single computed value. | • 13.2 [13.2-k] — shares-logic; residual: Owner of the 'Total Amount comes from billing' rule on the listing row — specifically the per-order Order.total figure. • 13.3 [13.3-n, 13.3-o, 13.3-z] — shares-logic; residual: These are DIFFERENT fields from 13.2-k's Order.total: 13.3-n = total_savings, 13.3-o = paid_amount (Total Paid), 13.3-z = full reconciliation across subtotal/fees/savings/total-paid. Only the 'read from the Order record, do not recompute' principle is shared — the breakdown, the distinct fields and the reconciliation check are all genuine separate work, not redundant. | Settle the 'do not recompute totals; read the billing-owned Order figures' decision once so list and details cannot diverge. Small but real — it is an architectural alignment, not a reusable computation. | Order monetary fields (total, total_savings, paid_amount, fees, coupon_amount) written by cart checkout write-path (exhibitor-backend-api/src/cart/helpers/cart.helpers.ts:33 materializeCartToOrder) + flipped by external-api webhook; same Order record read by both stories. No 'centralized billing service' module exists (codebase map) — 'billing' = the Order record.

## Reqs Without Endpoint
Req ID | Why no endpoint (by design)
13.1-f | out-of-scope — per-row order-level actions are delegated to/defined in 13.2; UI behavior on the shared listing, no separate endpoint.
13.2-h2 | out-of-scope — Pay-flow execution / payment-summary redirect belongs to the pay-flow epic, not an Order History endpoint.
13.3-c | not-deliverable — no Booth Number data source in schema; cannot be served by the details endpoint.
13.3-f | out-of-scope — Booth Type field not in scope; UI/display only.
13.3-g | out-of-scope — Upgrade details field not in scope; UI/display only.
13.3-l | blocked — Gift Certificate financial line has no producer writing it yet; would be a field on the details endpoint, not a separate route.
13.3-t | out-of-scope — salesperson-set Payment Schedule display not in scope.
13.3-w | out-of-scope — Onsite contact information not in scope; UI/display only.