## Overview
Story ID | 13.2
Title | Order Listing Table
Epic | Order History
Build Status | 13 requirement(s) to implement here (filter Build Focus = 'Implement here'). 0 covered elsewhere, 1 out of scope.
To implement here | 13
Summary | Story 13.2 asks for a paginated, ownership-scoped table of an exhibitor's orders showing Order ID, Order Date, derived Payment Status (Paid in Full / Partially Paid / Unpaid), Associated Shows (multi-show grouped), and Total Amount, plus per-row View / Invoice / Pay actions. Every primitive this needs is already BUILT: the Order model with paid_amount/paid_in_full_at/status; a real Stripe webhook write-path (external-api-service webhook.service.ts) that bumps paid_amount and flips status to partially_paid/completed via computeNewOrderStatus; order->orderItems->showProduct->show joins plus buildOrderGroup grouping (purchased-booths.service); a paginated company-scoped order listing pattern (ppl.service listOrderHistory); and a pdfkit render + S3 signed-URL invoice download path. Per-installment Paid/Unpaid/Overdue are also fully derivable: PaymentTransaction.due_date is written by a real path (payments.service split-schedule) and status by checkout/cron/webhook, so Overdue = due_date<now AND status!=succeeded is a pure derivation just like the order-level status. The net-new listing + invoice endpoints are therefore Deliverable. The only out-of-scope piece is the Pay-flow EXECUTION (payment-summary screen, salesperson-set method display, card capture), which the spec explicitly delegates to the Credit Card Payment Workflow / Payment Schedule Visibility stories; only the Pay-action availability flag is in scope here.
Total requirements | 14
Deliverable | 13
Partial | 0
Blocked | 0
Not Deliverable | 0
Out of Scope | 1
Implementation | 12 of 13 in-scope reqs shipped in SBE-1146; 13.2-g Invoice DEFERRED (team decision)
Impl Branch | feature/SBE-1146-order-listing-table (exhibitor-backend-api)
Impl Commits | 09bce5f (feat), fc429bd (SonarQube fix)
PR | Bitbucket #272 → dev

## Requirements
Req ID | Requirement | Verdict | Build Focus | Delivered By | Reason (exists vs to-build / gap) | Code Evidence | Dependency | Build Consolidation (reuse / delivered-by) | Story Wording (verbatim, from Confluence) | Confluence | Impl Status (2026-07-01)
13.2-a | Show a paginated list of all the logged-in exhibitor's orders. | Deliverable | Implement here | — | Order model exists and a paginated, company-scoped order listing (skip/take + count + meta) is already implemented for PPL orders; the same pattern applies to a net-new generic order listing endpoint. Only the new endpoint + DTO must be built on top of working primitives. | admin-backend-api/prisma/schema.prisma:1540 (model Order); exhibitor-backend-api/src/ppl/services/ppl.service.ts:597-690 (listOrderHistory pagination pattern) |  | [C1 fold] OWNER — build here (GET /orders — the single canonical company-scoped, paginate…); reused by other stories in this cluster. | Listing The page shall show a paginated list of all the Exhibitor's orders. | Open §Order History → Story 13.2 | ✅ Done (SBE-1146)
13.2-b | Each row shows Order ID, Order Date, Payment Status, Associated Shows, Total Amount. | Deliverable | Implement here | — | order_number (Order ID), created_at (Order Date) and total (Total Amount) are stored columns; associated shows are reachable via orderItems.showProduct.show as already done in purchased-booths. Payment Status is derived (see 13.2-c). All five columns are backed by built data. | admin-backend-api/prisma/schema.prisma:1542,1551 (order_number/total), created_at on Order; exhibitor-backend-api/src/purchased-booths/purchased-booths.service.ts:104-124 (orderItems.showProduct.show include) |  |  | Columns Each row shall include: Order ID, Order Date, Payment Status (Paid, Unpaid), Associated Shows (multi-city or multi-show support), and Total Amount. | Open §Order History → Story 13.2 | ✅ Done (SBE-1146)
13.2-c | Derive order-level payment status (Paid in Full / Partially Paid / Unpaid) from associated payment plans/installments. | Deliverable | Implement here | — | Order.paid_amount, total and paid_in_full_at are maintained by a real write-path: the Stripe webhook bumps paid_amount on each succeeded installment and sets status to partially_paid/completed via computeNewOrderStatus. Paid in Full = paid_in_full_at set / paid_amount>=total; Partially Paid = 0<paid_amount<total; Unpaid = paid_amount=0. Pure derivation over written fields. | external-api-service/src/modules/webhook/services/webhook.service.ts:2089-2104 (paid_amount/status/paid_in_full_at update), :2245-2251 (computeNewOrderStatus); admin-backend-api/prisma/schema.prisma:1571-1574 (payment_mode/installments_count/paid_amount/paid_in_full_at), :1546 (status) |  | [C5 build-once-reuse] OWNER — build here (A NET-NEW read-time order-level payment-status derivation m…); reused by other stories in this cluster. | Payment Status Derivation An order may have one or more payment plans or scheduled payment installments; the order-level payment status shall be derived from the statuses of its associated payment plans. / The overall order payment status shall be: Paid in Full (all associated payment plans fully paid), Partially Paid (one or more plans paid but an outstanding balance remains), or Unpaid (no payments received against the order). | Open §Order History → Story 13.2 | ✅ Done (SBE-1146)
13.2-d | Each payment plan/installment maintains its own status including Overdue (Paid, Unpaid, Overdue). | Deliverable | Implement here | — | Re-verified: the gap is disprovable. Although the PaymentTransactionStatus enum has no literal 'overdue' value, both inputs needed to derive it are written by real code paths — due_date is set at scheduling time (installment #1 = now, #2..N = future dates) in payments.service split-schedule, and status is written by checkout/cron/webhook. Overdue = (due_date < now AND status NOT IN succeeded/refunded/canceled) is a pure computed status, exactly analogous to the order-level derivation in 13.2-c which is Deliverable. Paid = succeeded; Unpaid = scheduled/processing/failed with due_date>=now. No stored 'overdue' column is required for a derived display status. | admin-backend-api/prisma/schema.prisma:2057-2091 (PaymentTransaction with due_date written, status), :491-500 (PaymentTransactionStatus enum); exhibitor-backend-api/src/payments/services/payments.service.ts:261-285 (due_date written per installment: now for #1, future for #2..N); background-worker-service/src/jobs/payment-charge/payment-charge.service.ts:64-78 (cron writes scheduled/failed/processing, confirming due_date+status are live) |  |  | Each payment plan shall maintain its own status: Paid, Unpaid, or Overdue. | Open §Order History → Story 13.2 | ✅ Done (SBE-1146) — order-level is_overdue rollup; per-installment breakdown = 13.3
13.2-e | An Overdue plan must be reflected in the order status as not fully paid (Partially Paid or Unpaid). | Deliverable | Implement here | — | Order status is derived from paid_amount vs total, so any order that is not fully paid resolves to Partially Paid or Unpaid regardless of whether an installment is labeled overdue. The order-level rule holds purely from written fields. | external-api-service/src/modules/webhook/services/webhook.service.ts:2090-2104 (isFullyPaid drives status); admin-backend-api/prisma/schema.prisma:1573-1574 |  | [C5 build-once-reuse] OWNER — build here (A NET-NEW read-time order-level payment-status derivation m…); reused by other stories in this cluster. | A payment plan marked Overdue shall be reflected in the order status as not fully paid (Partially Paid or Unpaid as applicable). | Open §Order History → Story 13.2 | ✅ Done (SBE-1146)
13.2-f | View action opens the detailed order summary. | Deliverable | Implement here | — | The listing only needs to expose each order's id so the UI can navigate; that id is returned in the row DTO. The detailed Order Details Page itself is a separate Order History story, but providing the View action/identifier here is fully deliverable. | admin-backend-api/prisma/schema.prisma:1540 (Order.id); exhibitor-backend-api/src/ppl/services/ppl.service.ts:667 (id returned in row DTO) | Order Details Page (separate Order History story) is the navigation target, but does not gate this listing | [C2 cross-reference] Mostly delivered by building 13.3 (GET /orders/:orderId — the read-only ownership-scoped order…). Residual: none on the backend — the View action navigates a listing row to GET /orders/:orderId; building 13.3's details endpoint delivers 13.2-f entirely. Only the front-end row-to-detail wiring is outside API scope. | View: open the detailed order summary. Refer User Story Order Details Page | Open §Order History → Story 13.2 | ✅ Done (SBE-1146) — row id returned; details endpoint owned by 13.3
13.2-g | Invoice action to download or view the invoice PDF. | Deliverable | Implement here | — | Invoice + InvoiceLineItem rows are created by the webhook for each paid installment, and a complete pdfkit render + S3 signed-URL download path already exists for PPL invoices (uploadService.upload returns a fresh signed URL) and is reusable for product orders. Net-new work is wiring a per-order invoice endpoint over these built primitives. Note: split orders produce multiple invoices (one per installment), reachable via the same Invoice/InvoiceLineItem primitives. | external-api-service/src/modules/webhook/services/webhook.service.ts:2048 (invoice.create), :2225 (invoiceLineItem.create); exhibitor-backend-api/src/ppl/services/ppl.service.ts:753-832 (downloadInvoicePdf), :985-1040 (renderInvoicePdf via pdfkit), ppl.controller.ts:1002-1011 (S3 upload + signed URL) |  | [C3 build-once-reuse] OWNER — build here (GET /orders/:orderId/invoice — order-scoped invoice PDF (ne…); reused by other stories in this cluster. | Invoice: download or view the invoice PDF. | Open §Order History → Story 13.2 | ⛔ DEFERRED — Invoice endpoint + action flag; blocked on team invoice-semantics decision (A vs B)
13.2-h | Pay action availability: Pay shown only for orders that are not Paid in Full (Partially Paid or Unpaid); View and Invoice available for every order. | Deliverable | Implement here | — | The availability rule is a boolean over the same derived payment status (paid_in_full_at set / paid_amount>=total). View and Invoice are always-available; Pay is gated on not-paid-in-full. All inputs are written fields. Only the availability FLAG is in scope here — the pay-flow destination is 13.2-h2. | external-api-service/src/modules/webhook/services/webhook.service.ts:2090-2104; admin-backend-api/prisma/schema.prisma:1573-1574 |  |  | Actions Availability View and Invoice shall be available for every order; Pay shall be available only for orders that are not Paid in Full (Partially Paid or Unpaid). | Open §Order History → Story 13.2 | ⚠️ Partial (SBE-1146) — Pay flag + View shipped; Invoice action flag deferred with 13.2-g
13.2-h2 | Pay flow execution: clicking Pay redirects to a payment summary showing the salesperson-set payment method and allows early credit/debit card payment. | Out of Scope | Out of scope | — | The payment-summary screen, salesperson-set payment method display, and card-capture/early-charge execution are explicitly delegated by the story spec to the referenced Credit Card Payment Workflow and Payment Schedule Visibility stories. Story 13.2 only surfaces the Pay action flag (13.2-h); the flow itself is another story's deliverable. | story spec lines 21,25 ('Refer User Story Credit Card Payment Workflow / Payment Schedule Visibility'); exhibitor-backend-api/src/payment-method/ and src/payments/ exist but the salesperson-method early-pay summary screen is not part of this listing story | Credit Card Payment Workflow + Payment Schedule Visibility stories own the pay execution and salesperson-method summary |  | Pay: the Exhibitor may make payments earlier than the schedule defined by the salesperson; on clicking Pay, the Exhibitor shall be redirected to a page showing the payment summary and the payment method set by the salesperson, and may complete payment using a credit or debit card. | Open §Order History → Story 13.2 | Out of Scope — Credit Card Payment Workflow / Payment Schedule Visibility stories
13.2-i | Multi-show orders displayed in a grouped format, not as disconnected rows. | Deliverable | Implement here | — | Orders reach shows via orderItems.showProduct.show, and a grouped build (buildOrderGroup grouping shows under an order) is already implemented in purchased-booths. The same grouping applies directly to the listing. | exhibitor-backend-api/src/purchased-booths/purchased-booths.service.ts:104-145 (showProduct.show include + buildOrderGroup grouping) |  |  | Multi-Show Display Multi-show orders shall be displayed in a grouped format. / Multi-Show Grouping Orders spanning multiple shows shall be grouped, not shown as disconnected rows. | Open §Order History → Story 13.2 | ✅ Done (SBE-1146)
13.2-j | Only the logged-in exhibitor's orders are listed, enforced on the backend. | Deliverable | Implement here | — | Ownership scoping by resolving the exhibitor's company (findExhibitorCompanyOrFail) and filtering Order.company_id is already implemented behind the auth guard. Directly reusable for the new endpoint. | exhibitor-backend-api/src/ppl/services/ppl.service.ts:601,607-608 (findExhibitorCompanyOrFail + company_id filter), :1555-1565 (findExhibitorCompanyOrFail impl) |  | [C1 fold] OWNER — build here (GET /orders — the single canonical company-scoped, paginate…); reused by other stories in this cluster. ¦ [C4 build-once-reuse] OWNER — build here (Company-ownership scoping guard/predicate (auth guard + com…); reused by other stories in this cluster. | Ownership Only the logged-in Exhibitor's orders shall be listed, enforced on the backend. | Open §Order History → Story 13.2 | ✅ Done (SBE-1146)
13.2-k | Total Amount shall come from the centralized billing service. | Deliverable | Implement here | — | Order.total is a stored, authoritative snapshot written at order creation and is the value the listing returns. There is NO separate standalone 'centralized billing service' in the codebase — pricing is computed in-process by cart-pricing.service and frozen onto Order.total at checkout; the stored total satisfies the column. Deliverable using order.total. | admin-backend-api/prisma/schema.prisma:1551 (Order.total); codebase_map.md (pricing is in-process cart-pricing.service, no standalone billing service) |  | [C6 cross-reference] OWNER — build here (Architectural decision/data-access pattern: read monetary f…); reused by other stories in this cluster. | Column Accuracy Each column shall reflect the order's actual values; Total Amount shall come from the centralized billing service. | Open §Order History → Story 13.2 | ✅ Done (SBE-1146)
13.2-l | Pagination works correctly across one, few, and many orders. | Deliverable | Implement here | — | A proven skip/take + count + meta (page/limit/total/totalPages/hasNext/hasPrev) pagination pattern already exists in two places and is directly reusable for the new endpoint. | exhibitor-backend-api/src/ppl/services/ppl.service.ts:633-690 (pagination + meta); purchased-booths.service.ts:88-142 (count + skip/take + meta) |  |  | Pagination The list shall paginate correctly across one, few, and many orders. | Open §Order History → Story 13.2 | ✅ Done (SBE-1146)
13.2-m | Empty state: when the logged-in exhibitor has no orders, the listing shows an appropriate empty state. (Folded in from story 13.1-e so the listing story is self-contained; building this satisfies 13.1's empty-state requirement automatically.) | Deliverable | Implement here | — | Trivial on the built listing path: the GET /orders endpoint is company-scoped and naturally returns an empty result when the exhibitor has no orders; an isEmpty/total flag is already produced by the purchased-booths list response and the PPL paginated meta, so the empty-state contract is reused directly. No new data or producer needed. | exhibitor-backend-api/src/purchased-booths/purchased-booths.service.ts:142 (isEmpty: total === 0), meta lines 132-143; ppl.service.ts:651 (count for paginated meta) |  | [C1 fold] OWNER — build here (GET /orders — the single canonical company-scoped, paginate…); reused by other stories in this cluster. | Empty State If the Exhibitor has no orders, an appropriate empty state shall be shown. | Open §Order History → Story 13.2 | ✅ Done (SBE-1146)

## Endpoints
Method | Path | Purpose | Serves Req(s) | Shared With
GET | /orders | Paginated, company-scoped order listing with row fields (Order ID, Date, derived payment status, grouped shows, total) and per-row action-availability flags (view/invoice always; pay when not paid in full). | 13.2-a, 13.2-b, 13.2-c, 13.2-d, 13.2-e, 13.2-h, 13.2-i, 13.2-j, 13.2-k, 13.2-l, 13.2-m | Shared with 13.1 Order History container page (same GET /orders).
GET | /orders/:orderId | View action opens the detailed order summary by loading the order-details aggregate. | 13.2-f | Shared with 13.3 Order Details Page — no separate route; the View action reuses 13.3's GET /orders/:orderId endpoint.
GET | /orders/:orderId/invoice | Invoice action downloads/views the invoice PDF for a row. | 13.2-g | Shared with 13.3 Order Details Page (Download Invoice button) — same GET /orders/:orderId/invoice endpoint.

## Open Questions
# | Open Question | Status | Resolution / Decision
1 | [RESOLVED 2026-06-30] Does 'all the Exhibitor's orders' include PPL subscription/ppl_addon orders (which have no showProduct and would render an empty 'Associated Shows' column), or is the listing limited to product/booth (show) orders? Today these are listed by two different, non-overlapping paths — ppl.service.listOrderHistory filters to subscription/ppl_addon only and explicitly EXCLUDES product orders, while purchased-booths filters to product/show orders only — so the unified scope of this new listing is a genuine product decision. | Resolved (2026-06-30) | Decision: GET /orders spans ALL THREE order types (product, subscription, ppl_addon) from the single orders table — no order_type narrowing. All orders live in one Order model (admin-backend-api/prisma/schema.prisma:1540; order_type enum at :1545); the existing PPL and purchased-booths pages differ only by their order_type filter, so the unified listing relaxes that predicate. Consequence: Associated Shows renders only for product orders (orderItems -> showProduct -> show) and is an empty array for subscription/ppl_addon orders, which the row DTO returns as shows: [] (not null).
2 | Should abandoned pending orders appear in the listing? A pending Order row is written at place-order time (before the Stripe redirect); if the exhibitor backs out it stays pending forever. The existing PPL history deliberately excludes pending and shows only terminal/active states. | Open — for team discussion | Current direction (2026-06-30): INCLUDE pending rows in GET /orders so in-flight/current orders surface (consistent with 13.1 past-AND-current mandate and the Pay action on payable orders). Flagged for TEAM DISCUSSION because this also surfaces never-paid abandoned-checkout rows, which may add noise; team to decide whether to keep, filter by an age cutoff, or exclude pure abandoned-checkout pending orders.
3 | What does the Invoice action mean for the listing — a formal tax invoice/receipt for money actually paid, or an order document/summary downloadable regardless of payment state? Current invoice generation is PPL/subscription-only: the Stripe webhook persists Invoice+InvoiceLineItem rows ONLY on successful payment (unpaid order -> 0 invoices; split order -> N invoices), and the single PDF renderer (ppl.service.ts:985 renderInvoicePdf, pdfkit, GET /ppl/invoices/:id/download) is hardcoded subscription-shaped and cannot render product/booth orders as-is. No product-order invoice renderer exists. | Open — team confirmation · work DEFERRED | Decision (2026-06-30): DEFER the Invoice endpoint work (13.2-g, GET /orders/:orderId/invoice) until the team confirms invoice semantics. Option A: generate an order-level invoice/summary PDF from Order+OrderItems (works for every order & payment state). Option B: serve only persisted Invoice rows (unpaid -> 404, split -> latest-vs-all ambiguity, still needs a product-shaped renderer). The listing endpoint and all other rows/actions proceed now; the invoice PDF endpoint and Invoice action-availability flag are HELD pending this answer.

## Cross-Epic Dependencies
Dependency | Needed For | Likely Owner
Pay/early-payment execution: payment-summary screen, salesperson-set payment method display, and credit/debit card charge capture | 13.2-h2 (Pay action destination/flow). The Pay availability FLAG in 13.2-h is independently deliverable and does NOT depend on this. | Credit Card Payment Workflow / Payment Schedule Visibility stories
Order Details Page (detailed order summary screen + endpoint) | 13.2-f navigation target only. The View action's identifier is returned by this listing, so 13.2-f is not blocked. | Order History epic (separate Order Details story)

## Implementation Status
Section | Detail
Shipped (SBE-1146) | GET /orders listing endpoint (src/orders/) — satisfies 12 of 13 in-scope reqs: 13.2-a,b,c,d,e,f,h(Pay+View),i,j,k,l,m. Exposed in Swagger under the Orders tag. Live-smoke-tested, code-reviewed, pre-push gate green.
Remaining — 13.2-g | Invoice action + endpoint GET /orders/:orderId/invoice AND the Invoice action-availability flag (Invoice half of 13.2-h). DEFERRED — blocked on team invoice-semantics decision: Option A (order-level PDF from Order+OrderItems, works for every order/state) vs Option B (serve persisted Invoice rows). Only piece of 13.2 own backend not yet built.
Open decision — invoice semantics | A vs B — gates 13.2-g. No code until answered.
Open decision — pending orders | Currently SHIPPED as included; team to confirm keep / age-filter / exclude abandoned-checkout pending (single where predicate if changed).
Dependency — 13.3 | GET /orders/:orderId order-details aggregate owned by story 13.3 (View navigation target; 13.2 only owes the row id, which is shipped).
Dependency — 13.2-h2 | Pay-flow execution (Out of Scope) — Credit Card Payment Workflow / Payment Schedule Visibility stories.
Out of API scope | Front-end row-to-detail / action wiring.