## Overview
Story ID | 24.14
Title | Internal Notes & Administrative Information
Epic | Order Management
Build Status | 7 requirement(s) to implement here — all 7 confirmed Deliverable with the human on 2026-07-02 (per-item walkthrough; Confluence sync check passed). 0 covered elsewhere, 0 out of scope. Confirmed build scope: 24.14-a…g. Jira: SBE-1138 (In Progress, Prantik Saha).
To implement here | 7
Summary | Admin-only Notes surface on Order Details: Internal Notes, Payment Memo, Invoice Note/PO Number, Additional Terms, each change captured in the permanent append-only AdminAuditLog. All primitives verified on dev 2026-07-02. KEY CORRECTION: Order.notes cannot be reused — it is the exhibitor checkout idempotency-key store (cart.service.ts:1277/:1541, payments.service.ts:213/:465, 24h duplicate-charge protection) — so 24.14-a gets a net-new internal_notes column. One migration adds four nullable columns to orders: internal_notes Text, payment_memo Text, invoice_note VarChar(255) (copied from Cart), additional_terms Text (copied from Cart) — created blank at checkout (resolved 2026-07-02, no Cart seeding). API surface = single endpoint pair GET+PATCH /api/v1/orders/:id/notes on the shipped orders module (per-field audit via recordMany in one transaction; permissions orders.notes.read/update documented in Swagger). Fully Deliverable now, zero external dependencies, no open questions.
Total requirements | 7
Deliverable | 7
Partial | 0
Blocked | 0
Not Deliverable | 0
Out of Scope | 0
Implementation | Not started — scope finalized with the human 2026-07-02 (all 7 Deliverable). SBE ticket: SBE-1138 (In Progress, Prantik Saha).
Impl Branch | —
Impl Commits | —
PR | —

## Requirements
Req ID | Requirement | Verdict | Build Focus | Delivered By | Reason (exists vs to-build / gap) | Code Evidence | Dependency | Build Consolidation (reuse / delivered-by) | Story Wording (verbatim, from Confluence) | Confluence | Impl Status (2026-07-02)
24.14-a | Admin can add, edit, and maintain Internal Notes on an order (admin-only). | Deliverable | Implement here | — | Confirmed 2026-07-02 WITH DELIVERY CORRECTION: Order.notes must NOT be reused — it is the exhibitor checkout idempotency-key store (written as 'idempotency_key:<key>' at order creation, substring-matched for 24h replay/duplicate-charge protection in BOTH exhibitor checkout paths); admin overwrite would break duplicate-order protection and the tab would render machine tags. Delivery = net-new internal_notes String? @db.Text column + shared GET/PATCH /orders/:id/notes on the shipped orders module. | exhibitor-backend-api/src/cart/services/cart.service.ts:1277 (notes write), :1541 (contains replay lookup); src/payments/services/payments.service.ts:213 (write), :465 (lookup); src/cart/helpers/cart.helpers.ts:11 (buildIdempotencyKey); admin schema.prisma:1570 (Order.notes — leave untouched); other 3 repos: zero Order.notes references |  | [C5 cross-reference] OWNER — build here (GET + PATCH /api/v1/orders/:id/notes — the single read/write pair); reused by other stories in this cluster. CORRECTION 2026-07-02: net-new internal_notes column — Order.notes is reserved (exhibitor idempotency-key store). | Add, edit, and maintain Internal Notes visible only to admin users. | Open §Order Management → Story 24.14 | ◻ Not started — scope confirmed 2026-07-02
24.14-b | Admin can add a Payment Memo for internal accounting / reference purposes. | Deliverable | Implement here | — | Confirmed 2026-07-02. No payment_memo column on Order, no write path in any of the 5 repos (grep clean). Decision: payment_memo String? @db.Text (Text over VarChar, per human) in this story's migration, exposed via the shared notes endpoints. Order-level — distinct from story 24.8's planned payment_transactions.payment_memo (installment-level). Resolved 2026-07-02: created blank at checkout (no Cart seeding). | admin-backend-api/prisma/schema.prisma:1540-1604 (Order model — no payment_memo); grep 'payment_memo' across all 5 repos → no matches |  | [C5 cross-reference] OWNER — build here (GET + PATCH /api/v1/orders/:id/notes — the single read/writ…); reused by other stories in this cluster. | Add Payment Memo for internal accounting or reference purposes. | Open §Order Management → Story 24.14 | ◻ Not started — scope confirmed 2026-07-02
24.14-c | Admin can add or update Invoice Notes / Purchase Order (PO) Number on an order. | Deliverable | Implement here | — | Confirmed 2026-07-02. Decision: ONE combined column (not separate invoice_note + po_number), copying Cart.invoice_note verbatim — String? @db.VarChar(255), comment 'Invoice Note / PO Number' — one shape for the same field across the domain; DTO/validation proven by the existing Cart write path. Resolved 2026-07-02: created blank at checkout (no Cart seeding). | admin-backend-api/prisma/schema.prisma:2853 (Cart.invoice_note template); src/admin/cart/dto/update-cart.dto.ts:85 + cart.service.ts:359 (existing Cart write-path); Order model 1540-1604 has no such column |  | [C5 cross-reference] OWNER — build here (GET + PATCH /api/v1/orders/:id/notes — the single read/writ…); reused by other stories in this cluster. | Add or update Invoice Notes / Purchase Order (PO) Number. | Open §Order Management → Story 24.14 | ◻ Not started — scope confirmed 2026-07-02
24.14-d | Admin can add Additional Terms & Conditions applicable to the order. | Deliverable | Implement here | — | Confirmed 2026-07-02. Copy Cart.additional_terms verbatim — String? @db.Text, comment 'Additional Terms & Conditions'; semantics proven by the existing consumer (agreement-document generator). Resolved 2026-07-02: created blank at checkout (no Cart seeding). | admin-backend-api/prisma/schema.prisma:2854 (Cart.additional_terms template); src/admin/cart/services/agreement-document.service.ts:112 (existing consumer); Order model 1540-1604 lacks it |  | [C5 cross-reference] OWNER — build here (GET + PATCH /api/v1/orders/:id/notes — the single read/writ…); reused by other stories in this cluster. | Add Additional Terms & Conditions applicable to the order. | Open §Order Management → Story 24.14 | ◻ Not started — scope confirmed 2026-07-02
24.14-e | System maintains a permanent, non-editable audit trail of note additions and modifications (backend-enforced). | Deliverable | Implement here | — | Confirmed 2026-07-02. Append-only AdminAuditLog (monthly-partitioned) + tx-aware record()/recordMany() fully built; enum 'order' already used by admin checkout. Non-editable is structural (audit controller is GET-only). Delivery = one recordMany call inside the PATCH $transaction — one entry per changed field with previous/new snapshots, per the account-history-notes pattern. Display = existing GET /logs/admin-audit (zero new endpoints). | admin schema.prisma:2193 (enum 'order'), :2209-2226 (AdminAuditLog append-only/partitioned); src/admin/common/audit/admin-audit.service.ts:30-48 (record, tx-aware) + recordMany; src/admin/account-history-notes/account-history-notes.service.ts:25-55 (template); src/admin/audit-log/admin-audit-log.controller.ts (GET-only) |  | [C5 cross-reference] OWNER — build here (GET + PATCH /api/v1/orders/:id/notes — the single read/writ…); reused by other stories in this cluster. ¦ [C9 build-once-reuse] OWNER — build here (AdminAuditService.record()/recordMany() with entity_type='o…); reused by other stories in this cluster. | Audit Trail The system shall maintain an audit trail of note additions and modifications. / Note additions and modifications shall be recorded in a permanent, non-editable audit trail. | Open §Order Management → Story 24.14 | ◻ Not started — scope confirmed 2026-07-02
24.14-f | Internal Notes (and other internal note fields) are visible only to admin users and never exposed to the customer. | Deliverable | Implement here | — | Confirmed 2026-07-02. Routes behind the global JWT + roles + @Permissions stack (app.module.ts:86-91). Delivery = orders.notes.read / orders.notes.update permission seeds + decorators; permission keys documented on the Swagger route docs (human addition 2026-07-02). Customer side structurally safe: exhibitor uses frozen SELECT constants that never select the new columns (siblings carry them in schema.prisma for db-push safety — carrying ≠ exposing). | src/auth/guards/jwt-auth.guard.ts, roles.guard.ts; src/auth/decorators/permissions.decorator.ts; permission.seeder.ts ~:1203 ('orders' block precedent); role.seeder.ts:178 (grant precedent) |  | [C5 cross-reference] OWNER — build here (GET + PATCH /api/v1/orders/:id/notes — the single read/writ…); reused by other stories in this cluster. | Visibility Internal Notes shall be visible only to admin users. | Open §Order Management → Story 24.14 | ◻ Not started — scope confirmed 2026-07-02
24.14-g | Note handling and the audit trail are enforced on the backend. | Deliverable | Implement here | — | Confirmed 2026-07-02. AC umbrella over a–e mechanics: DTO validation + order-exists/soft-delete 404 in the service layer; note write + per-field audit entries in one Prisma $transaction (failed audit write rolls back the note change); audit permanence is DB/API-structural. No build beyond the agreed endpoints. | src/admin/account-history-notes/account-history-notes.service.ts:25-55 (transactional template); src/admin/common/audit/admin-audit.service.ts:30-48 |  | [C5 cross-reference] OWNER — build here (GET + PATCH /api/v1/orders/:id/notes — the single read/writ…); reused by other stories in this cluster. ¦ [C8 build-once-reuse] Mostly delivered by building 24.1 (The existing JWT + roles guard + @Permissions(...) decorato…). Residual: none beyond applying the guard on notes routes. | Backend Enforcement Note handling and the audit trail shall be enforced on the backend. | Open §Order Management → Story 24.14 | ◻ Not started — scope confirmed 2026-07-02

## Endpoints
Method | Path | Purpose | Serves Req(s) | Shared With
GET | /api/v1/orders/:id/notes | Return the order's notes bundle — internal_notes, payment_memo, invoice_note, additional_terms — for the admin Notes tab. Permission: orders.notes.read (documented in the route's Swagger docs). | 24.14-a, 24.14-b, 24.14-c, 24.14-d, 24.14-f
PATCH | /api/v1/orders/:id/notes | Update any subset of the four fields in one $transaction (all DTO fields optional; omitted fields untouched); one AdminAuditLog entry per changed field via recordMany. Permission: orders.notes.update (documented in the route's Swagger docs). | 24.14-a, 24.14-b, 24.14-c, 24.14-d, 24.14-e, 24.14-g | 24.6 — Order Details notes/invoice-note/terms editing (24.6-c/e/f) reuses this canonical write path; 24.6-d flips Not Deliverable → Deliverable when payment_memo lands.
GET | /api/v1/logs/admin-audit?entity_type=order&entity_id=:id | List the permanent, non-editable audit-trail entries for an order's note changes. | 24.14-e | Reuses the existing admin-audit-log controller GET / route (already built); no new endpoint.

## Open Questions
# | Open Question | Status | Resolution / Decision
— | None — register empty. The single item (cart-seeding of the new Order columns) was resolved with the human on 2026-07-02; decision recorded in the 24.14-b/c/d Requirements rows per the doc-format rule. | RESOLVED (2026-07-02) | Leave the new Order columns blank at order creation — the spec frames these as admin-entered fields on the Notes tab; no checkout write-path changes in any repo.

## Cross-Epic Dependencies
Dependency | Needed For | Likely Owner
None

## Implementation Status
Section | Detail
Branch | — (not started). SBE ticket: SBE-1138 (In Progress, Prantik Saha). No PR / Swagger tag yet.
Overall | Scope finalized with the human 2026-07-02 — all 7 requirements confirmed Deliverable (per-item walkthrough; Confluence sync check passed). Implementation not started; every requirement ◻ Not started.
Remaining — 24.14-a | ◻ Not started — Internal Notes GET/PATCH via NET-NEW internal_notes Text column (Order.notes reserved: exhibitor checkout idempotency-key store)
Remaining — 24.14-b | ◻ Not started — Payment Memo; net-new payment_memo Text column on Order (distinct from 24.8's payment_transactions.payment_memo)
Remaining — 24.14-c | ◻ Not started — Invoice Notes / PO Number; net-new invoice_note VarChar(255), one combined column copied from Cart.invoice_note
Remaining — 24.14-d | ◻ Not started — Additional Terms; net-new additional_terms Text copied from Cart.additional_terms
Remaining — 24.14-e | ◻ Not started — Permanent non-editable audit trail via AdminAuditService.record() in the same Prisma transaction.
Remaining — 24.14-f | ◻ Not started — Admin-only visibility via JWT + roles + @Permissions guards on the net-new controller.
Remaining — 24.14-g | ◻ Not started — Backend-enforced transactional note update + audit, per account-history-notes pattern.
Resolved decision — Cart-seeding | RESOLVED 2026-07-02: new Order note columns are created blank at checkout (no seeding from Cart); admin fills them on the Notes tab. No checkout write-path changes in any repo.
Dependency | None. Cross-Epic Dependencies: None; no Covered-elsewhere requirements.
Out of API scope | Front-end wiring (the admin Notes tab UI). Nothing in this story is currently marked Out of Scope.