## Summary
Story | Title | Deliverable | Partial | Blocked | Not Deliverable | Out of Scope | Total | To Implement (net) | Build Status | # Endpoints | # Open Qs
24.1 | View and manage all orders | 11 | 1 | 1 | 0 | 1 | 14 | 13 | 13 to build | 1 | 2
24.2 | Filters | 7 | 2 | 0 | 0 | 0 | 9 | 9 | 9 to build | 2 | 2
24.3 | Search Order | 7 | 0 | 0 | 0 | 0 | 7 | 7 | 7 to build | 1 | 1
24.4 | Sorting | 3 | 0 | 0 | 0 | 0 | 3 | 3 | 3 to build | 1 | 0
24.5 | Quick Actions Per Order Item | 10 | 1 | 0 | 0 | 2 | 13 | 11 | 11 to build | 8 | 2
24.6 | Order Details | 11 | 13 | 3 | 1 | 0 | 28 | 27 | 27 to build | 11 | 4
24.7 | Manual Payment Methods | 3 | 2 | 0 | 0 | 0 | 5 | 5 | 5 to build | 2 | 2
24.8 | Payment Plan Management | 9 | 3 | 1 | 0 | 0 | 13 | 13 | 13 to build | 4 | 1
24.9 | Refund Management | 7 | 1 | 0 | 0 | 1 | 9 | 8 | 8 to build | 3 | 1
24.10 | Order Cancellation | 5 | 2 | 2 | 0 | 1 | 10 | 9 | 9 to build | 1 | 2
24.11 | Order Cancellation - Email Notification | 4 | 1 | 0 | 0 | 0 | 5 | 5 | 5 to build | 2 | 1
24.12 | Booth Release and Other Products Inventory Behaviour | 5 | 0 | 1 | 0 | 0 | 6 | 6 | 6 to build | 1 | 1
24.13 | Move/Change Show functionality | 8 | 1 | 0 | 0 | 1 | 10 | 9 | 9 to build | 2 | 2
24.14 | Internal Notes & Administrative Information | 7 | 0 | 0 | 0 | 0 | 7 | 7 | 7 to build | 3 | 1
24.15 | Payment Reminder Notifications | 3 | 0 | 5 | 0 | 0 | 8 | 8 | 8 to build | 1 | 2
TOTAL | 15 stories | 100 | 27 | 13 | 1 | 6 | 147 | 140 | net items to build (excl. covered/out-of-scope)

## Endpoint Catalog
Method | Path | Purpose | Stories | Requirements | Notes
GET | /api/v1/orders | Paginated, filterable, searchable, sortable Order Management list (order_type=product) returning per-row id, order_number, customer & company name, item total, balance due, show name, sales person, sales channel, date, with backend RBAC. Filtering (from_date/to_date/show_city_id/sales_channel), search (order_number/company/billing name), and sorting (sortBy/sortOrder) are all combinable query params on this one endpoint, applied before pagination. | 24.1, 24.2, 24.3, 24.4 | 24.1-a, 24.1-c, 24.1-d, 24.1-f, 24.1-g, 24.1-h, 24.1-i, 24.1-j, 24.1-k, 24.1-l, 24.1-m, 24.1-n, 24.2-a, 24.2-b, 24.2-c, 24.2-e, 24.2-f, 24.2-g, 24.2-h, 24.2-i, 24.3-a, 24.3-b, 24.3-c, 24.3-d, 24.3-e, 24.3-f, 24.3-g, 24.4-a, 24.4-b, 24.4-c | ONE canonical list endpoint shared by 24.1 (View/manage all orders container), 24.2 (Filters), 24.3 (Search), 24.4 (Sorting). Stories had proposed inconsistent paths (/orders, /admin/orders) — standardized to bare 'orders' controller under the api/v1 global prefix (no /admin segment). None of 24.2/24.3/24.4 introduces a separate route; they add query params. The row id is consumed by Order Details (24.6) and the quick-action endpoints (24.5).
GET | /api/v1/cities | Source the Show City filter dropdown options (optionally narrowed to cities that have shows via City.shows). | 24.2 | 24.2-d | Reuses the existing city-management list endpoint; no new endpoint required.
GET | /api/v1/orders/:id | Full Order Details aggregate: general info, billing snapshot, line items (product/show links, included flag, sub-items via parent_order_item_id), fees, totals + balance, payment plan (via cart_id) + next installment, signer/agreement metadata, sales rep/source, customer link. | 24.6 | 24.6-a, 24.6-b, 24.6-c, 24.6-e, 24.6-f, 24.6-g, 24.6-h, 24.6-i, 24.6-j, 24.6-k, 24.6-l, 24.6-l2, 24.6-m, 24.6-n, 24.6-o, 24.6-p, 24.6-q | Detail read model opened from the 24.1 list row id (24.1 introduces no separate route — its clickable-row requirement 24.1-c is served by the list endpoint exposing the id, so 24.1 was dropped from this endpoint's stories[]). Display of notes/invoice-note/terms (24.6-c/e/f) lives here; the WRITE for those fields is consolidated on PATCH .../notes (24.14).
PATCH | /api/v1/orders/:id | Admin edit of Billing Address (and order-level fields) with status-based edit rules and backend enforcement. | 24.6 | 24.6-h, 24.6-aa, 24.6-y | Notes / invoice-note / additional-terms editing (24.6-c/e/f) was removed from this route and consolidated into PATCH /api/v1/orders/:id/notes (24.14) so those fields have a single write path.
GET | /api/v1/orders/:id/actions | Return the permission- and status-gated set of available quick actions for an order (e.g. Booth Build only when completed/signed and the caller holds the Booth Build role). | 24.5 | 24.5-a, 24.5-d, 24.5-l | Drives which quick-action buttons render; the actions themselves are the sibling POST/GET endpoints below.
GET | /api/v1/orders/:id/agreement.pdf | Stream the order agreement as PDF (reuses AgreementDocumentService / buildSimplePdf), built from OrderAgreement. | 24.5, 24.6 | 24.5-f, 24.6-s | PDF variant of the order agreement download. 24.6-s (view/download agreement) is format-agnostic and maps onto both the .pdf and .docx routes — 24.6 introduces no separate agreement route (its invented /agreement/download was removed). Follows the existing cart agreement.pdf route convention.
GET | /api/v1/orders/:id/agreement.docx | Stream the order agreement as Word/DOCX (reuses AgreementDocumentService), reflecting booth details/pricing/terms. | 24.5, 24.6 | 24.5-e, 24.6-s | DOCX variant of the same agreement generator. Two routes kept (matching the existing cart agreement.docx / agreement.pdf convention) rather than one format-query endpoint — these are distinct formats, not duplicates.
GET | /api/v1/orders/:id/invoice.pdf | Stream the order invoice PDF from the order's written Invoice rows. | 24.5 | 24.5-g | Distinct from the agreement document; sourced from Invoice rows.
POST | /api/v1/orders/:id/additional-users | Admin adds one or more portal-user email IDs for the order's company; invitation sent, per-user permissions set later by the exhibitor. | 24.5 | 24.5-h
POST | /api/v1/orders/:id/resend-confirmation | Resend the order confirmation email (with invoice details) to the customer via mailer.sendFromTemplate. | 24.5 | 24.5-i | Distinct from POST .../send-email (24.6) which dispatches an admin-selected template; this resends the fixed confirmation.
POST | /api/v1/orders/:id/resend-portal-password | Trigger a portal password-reset / temp-password email for the order's customer (logged). | 24.5 | 24.5-j, 24.5-m
POST | /api/v1/orders/:id/impersonate | Permission-gated login as the order company's primary exhibitor (mint exhibitor portal JWTs), logged via impersonated_by. | 24.5 | 24.5-k, 24.5-m | Reuses the impersonate(company_id) primitive in ppl-service-provider-overview.service.
POST | /api/v1/orders/:id/send-email | Send an order email using an admin-selected notification template (dropdown sourced from the notification-template list; dispatch via MailerService.sendFromTemplate). | 24.6 | 24.6-r | Kept separate from resend-confirmation (24.5-i): this is template-selectable. Reuses notification-template module + background-worker MailerService.
PATCH | /api/v1/orders/:id/sales-rep | Reassign the Assigned Sales Rep / Deal Owner (permission-gated, reusing the cart assertAssignableDealOwner pattern but writing Order.sales_person_id) and trigger the HubSpot Deal Owner update. | 24.6 | 24.6-t, 24.6-u, 24.6-v, 24.6-y | Reuses cart deal-owner assignable-user logic. HubSpot Deal Owner update sub-action currently blocked.
POST | /api/v1/orders/:id/hubspot-sync | Manually sync the order to HubSpot (create contact/company/deal via existing client). | 24.6 | 24.6-x | Persisting the returned deal id needs a net-new hubspot_deal_id column on Order.
POST | /api/v1/orders/:id/quickbooks-sync | Force-sync invoices, payments, and customers for the order to QuickBooks. | 24.6 | 24.6-w | BLOCKED — no QuickBooks integration exists yet.
PATCH | /api/v1/orders/:id/payment-status | Admin manually sets a manual-method order's payment status to Paid or Unpaid; server-side validation, @Permissions check, method-eligibility gate, and an AdminAuditLog write in one transaction. | 24.7 | 24.7-b, 24.7-c, 24.7-d
GET | /api/v1/orders/:id/payments | The order's Payments view backing the admin Payments screen: current paid/unpaid status, payment method, amounts, and installment/transaction rows. | 24.7 | 24.7-a, 24.7-e | Overlaps in data with GET .../payment-plan (24.8) but kept distinct: this backs the Payments screen (status/method focus); payment-plan backs installment management (Unallocated Balance, 60/30-day warnings).
GET | /api/v1/orders/:id/payment-plan | The order's installments (PaymentTransaction rows) with Invoice #, date, status, amount due, order total, amount paid, plus computed Unallocated Balance and 60/30-day warnings. | 24.8 | 24.8-a, 24.8-h, 24.8-i | Read side of the payment-plan management sub-resource.
POST | /api/v1/orders/:id/payment-plan/installments | Manually add a new installment (incl. non-card types once schema relaxed); validates Unallocated Balance remains, runs the 60/30-day rule (warn/bypass for authorized users), enforces totals server-side. | 24.8 | 24.8-f, 24.8-i, 24.8-j, 24.8-k, 24.8-m
PATCH | /api/v1/orders/:id/payment-plan/installments/:installmentId | Edit a future installment's date, or mark it Paid/Unpaid/Refund; enforces post-payment lock (Refund-only after paid), date rules with warning-bypass, milestone-status/QuickBooks action, and backend total enforcement. | 24.8 | 24.8-b, 24.8-c, 24.8-d, 24.8-g, 24.8-j, 24.8-k, 24.8-l, 24.8-m | The mark-as-Paid capability here is what the 24.15 payment-reminder cron's stop-condition depends on.
DELETE | /api/v1/orders/:id/payment-plan/installments/:installmentId | Delete an unpaid installment and return its amount to the Unallocated Balance; blocked when the installment is already paid. | 24.8 | 24.8-e, 24.8-g, 24.8-h
GET | /api/v1/orders/:id/refund-options | Return available refund methods (always Manual; Stripe only when the order/installment has a stripe_charge_id) and the refundable cap (paid_amount minus prior refunds). | 24.9 | 24.9-d, 24.9-f
POST | /api/v1/orders/:id/refunds | Issue a Manual or Stripe refund for the order's payment plan: validate cap + mandatory reason, persist a net-new Refund record, set payment-plan status to Refunded (manual, or on Stripe success) or Refund Failed (Stripe failure); optionally email a refund notice. | 24.9, 24.6, 24.11 | 24.9-a, 24.9-b, 24.9-c, 24.9-d, 24.9-e, 24.9-g, 24.9-h, 24.6-z, 24.11-a, 24.11-b, 24.11-c, 24.11-d, 24.11-e | ONE canonical refund endpoint owned by 24.9. Consolidates 24.6-z's refund half (its bundled refund+void entry was split — void is a separate endpoint) and 24.11's refund-email notice. Accepts send_notification (default true) which emails the exhibitor via MailerService.sendFromTemplate (24.11). Calls external-api-service POST /v1/refunds for the Stripe leg. Neither 24.6 nor 24.11 introduces a separate refund route.
POST | /api/v1/orders/:id/void | Initiate a void on the order's payment. | 24.6 | 24.6-z | Void half of 24.6-z, split from refund. BLOCKED — no Stripe void execution path or Refund model exists yet.
POST | /api/v1/orders/:id/cancel | Cancel an entire order: validate & cap refund against Order.paid_amount, set Order.status=canceled, flip unpaid/pending/scheduled PaymentTransactions to canceled, release all committed InventoryReservation rows (booths + other products) in one transaction, initiate the Stripe refund via stripe_charge_id, return a manual-floorplan-release reminder when booth lines were present, optionally email a cancellation notice, and write an AdminAuditLog (entity_type=order). | 24.10, 24.11, 24.12 | 24.10-a, 24.10-b, 24.10-c, 24.10-d, 24.10-e, 24.10-f, 24.10-g, 24.10-i, 24.11-a, 24.11-b, 24.11-c, 24.11-d, 24.11-e, 24.12-a, 24.12-b, 24.12-c, 24.12-e, 24.12-f | ONE cancel endpoint owned by 24.10, merging the three sibling stories that each proposed POST .../cancel: 24.10 (refund cap + status flip + Stripe refund + audit log), 24.11 (send_notification, default true, cancellation email), and 24.12 (release InventoryReservation rows + manual floorplan-release reminder flag). 24.11 and 24.12 introduce no separate route. All server-side enforced; explicit confirmation captured client-side.
POST | /api/v1/orders/:id/move-show/validate | Pre-validate moving an order to a chosen destination show: confirm equivalent booth(s) + included products exist with sufficient inventory; return the unavailability reason without mutating anything. | 24.13 | 24.13-e, 24.13-f, 24.13-g | Dry-run companion to the move-show execute endpoint — a distinct validate-only operation, not a duplicate of move-show.
POST | /api/v1/orders/:id/move-show | Execute a direct transfer in one $transaction: re-map every order line to the destination show's ShowProduct (same product_id), release source-show committed reservations (status->released by order_id), re-commit destination reservations under a FOR UPDATE lock; reject in-move edits; fail with a clear message if inventory is unavailable. | 24.13 | 24.13-a, 24.13-b, 24.13-c, 24.13-d, 24.13-g, 24.13-h, 24.13-i
GET | /api/v1/orders/:id/notes | Return the order's internal notes, payment memo, invoice/PO note, and additional terms for the admin Order Details -> Notes tab. | 24.14 | 24.14-a, 24.14-b, 24.14-c, 24.14-d, 24.14-f | Dedicated notes sub-resource (read).
PATCH | /api/v1/orders/:id/notes | Add/edit internal notes, payment memo, invoice/PO note, and additional terms in one Prisma transaction, recording an AdminAuditLog (entity_type=order) per change. Behind JWT + roles + @Permissions. | 24.14, 24.6 | 24.14-a, 24.14-b, 24.14-c, 24.14-d, 24.14-e, 24.14-g, 24.6-c, 24.6-e, 24.6-f | Canonical write path for notes/additional-terms; absorbs the notes-editing concern that 24.6's PATCH /api/v1/orders/:id originally referenced (24.6-c/e/f), so those fields have a single mutation route. 24.6 introduces no separate notes-write route.
GET | /api/v1/logs/admin-audit?entity_type=order&entity_id=:id | List the permanent, non-editable audit-trail entries for an order's note changes. | 24.14 | 24.14-e | ALREADY BUILT — the existing admin-audit-log.controller GET / route already exposes entity_type (AdminAuditEntityType includes 'order') and entity_id filters; no new endpoint required. A dedicated alias /api/v1/orders/:id/notes/audit-trail is optional sugar.
POST | background-worker-service: /manual-trigger/payment-reminders/run | Dev-only manual trigger to invoke the payment-reminder cron on demand (reuses task.run() so the cron re-entrancy guard applies). | 24.15 | 24.15-c, 24.15-e, 24.15-g | Lives in background-worker-service, mirroring the existing @Controller('manual-trigger') + @Post('lead-distribution/run') / @Post('low-balance/run') convention. The reminder itself runs on a registered cron; no customer- or admin-facing REST/UI endpoint (story has no screen). Depends on the admin mark-as-Paid capability (PATCH .../installments/:installmentId, 24.8).
POST | external-api-service: /v1/refunds (internal) | stripe.refunds.create wrapper against the order's stripe_charge_id, returning the Stripe refund result/status so the admin refund service can set Refunded / Refund Failed. | 24.9 | 24.9-b, 24.9-g | Lives in external-api-service (matches its Stripe controller convention, e.g. @Controller('v1/payment-intents')); called internally by the admin POST /api/v1/orders/:id/refunds service. Not a public/admin route.

## Build Consolidation
Cluster | Type | Recommendation | Conf | Build-First (owner) | Shared Build Unit (build once) | Members — relation & residual delta | Effort Saved | Evidence
C1 | shared-implementation | build-once-reuse | high | 24.1 | GET /api/v1/orders — the single paginated/filterable/searchable/sortable list query (Prisma findMany over Order where order_type=product with RBAC) plus its row projection (order_number, customer/company, item total, balance due, show, sales person, sales channel, date) | • 24.1 [24.1-a, 24.1-c, 24.1-d, 24.1-f, 24.1-g, 24.1-h, 24.1-i, 24.1-j, 24.1-k, 24.1-l, 24.1-m, 24.1-n] — shares-endpoint; residual: owner — the base list query, row projection, pagination, RBAC and totals/balance columns. Booth-build rows (24.1-b) are Blocked (no producer) and stay out; Quick Links (24.1-e) is Out of Scope (belongs to 24.5). • 24.2 [24.2-a, 24.2-b, 24.2-c, 24.2-e, 24.2-f, 24.2-g, 24.2-h, 24.2-i] — shares-endpoint; residual: the from_date/to_date + show_city_id + sales_channel query params and their WHERE logic (incl. End>=Start validation, the OrderItem->ShowProduct->Show->City join for show-city [Partial: only cart-originated product orders carry show_product_id], and the cart.created_by_type derivation for sales-channel [Partial: null for non-cart orders]). 24.2-d (city dropdown) is NOT here — it reuses GET /api/v1/cities. 24.2-i is a frontend calendar-picker concern, not endpoint work. Empty-state (24.2-g) and backend-enforcement (24.2-h) are inherent to the shared endpoint = no extra work. • 24.3 [24.3-a, 24.3-b, 24.3-c, 24.3-d, 24.3-e, 24.3-f, 24.3-g] — shares-endpoint; residual: the single search query param with the insensitive-contains OR over order_number + company.name + billing_first/last_name. VERIFIED net-new: the ppl-order search (ppl-order.service.ts:299-300) covers only order_number + company.name, so the customer-name (billing first/last) clause is genuinely additional. Empty-state/backend (24.3-f/g) come free with the endpoint. • 24.4 [24.4-a, 24.4-b, 24.4-c] — shares-endpoint; residual: the sortBy/sortOrder params mapped to Prisma orderBy for order_number and created_at only — small (ppl-order.service.ts:90-100 is the exact precedent). Full-dataset enforcement (24.4-c) is inherent to server-side sort. | Avoids designing/reviewing 4 separate list endpoints. Filters, search and sorting are query-param layers on ONE controller+service+DTO+test surface, not independent builds. Pagination, RBAC, row projection and empty-state are written once and inherited by all four. | endpointCatalog GET /api/v1/orders stories[24.1,24.2,24.3,24.4]; verified near-identical pattern at admin/ppl-order/ppl-order.service.ts (sortBy/sortOrder :90-100, created_at date-range :293, insensitive contains over order_number+company.name :299-300, filter order_type IN [subscription,ppl_addon] :280 — confirming the product-order list is net-new and customer-name search is additional)
C2 | shared-implementation | build-once-reuse | high | 24.10 | POST /api/v1/orders/:id/cancel — one $transaction: refund cap vs Order.paid_amount, Order.status=canceled, flip unpaid/pending PaymentTransactions to canceled, release committed InventoryReservation rows, optional cancellation email, AdminAuditLog(entity_type=order) | • 24.10 [24.10-a, 24.10-b, 24.10-c, 24.10-e, 24.10-f, 24.10-i] — shares-endpoint; residual: owner — status flip + installment cancel + refund cap + Stripe-refund leg + audit log. Partial-refund accounting / Refund-record (24.10-d/h) and offline-refund marking (24.10-g) remain Blocked on the Refund-Management primitive. 24.10-j (per-plan refunds instead of full cancel) is Out of Scope. • 24.12 [24.12-a, 24.12-b, 24.12-c, 24.12-e, 24.12-f] — shares-endpoint; residual: the inventory-release call (flip committed->released by order_id for booth + non-booth lines) plus the manual-floorplan-release reminder flag returned in the cancel response. NOTE: the release helper itself is the shared build unit of C12 (net-new in admin-backend-api — no admin-side release method exists today). Auto Social-Tables release (24.12-d) stays Blocked. 24.12-a is the same cancel action as 24.10 = no separate endpoint. • 24.11 [24.11-a, 24.11-b, 24.11-c, 24.11-d, 24.11-e] — shares-logic; residual: the send_notification boolean param (default true) on the cancel request + the conditional MailerService.sendFromTemplate dispatch; still needs the cancellation trigger_event slug + template seeded. Same toggle is reused by the refund endpoint (see C3/C4). | Three stories each proposed POST .../cancel. Building one endpoint avoids three competing cancel routes and three reviews; inventory release and the email toggle become in-transaction steps of the single cancel service, not separate features. | endpointCatalog POST /api/v1/orders/:id/cancel stories[24.10,24.11,24.12]; inventory release pattern proven at external-api-service/src/modules/webhook/services/webhook.service.ts:2762-2765 (updateMany {order_id, status:committed} -> {status:released, released_at}); AdminAuditService.record at admin/common/audit/admin-audit.service.ts reused across configuration/gift-certificates/shows-management/account-history-notes
C3 | shared-implementation | build-once-reuse | high | 24.9 | POST /api/v1/orders/:id/refunds — validate cap (paid_amount minus prior refunds) + mandatory reason, persist Refund record, set Refunded / Refund Failed, optional refund email; calls external-api-service /v1/refunds for the Stripe leg | • 24.9 [24.9-a, 24.9-b, 24.9-c, 24.9-d, 24.9-e, 24.9-g, 24.9-h] — shares-endpoint; residual: owner — the Refund model, refund_failed enum value, cap/reason validation, status transitions, and the Stripe wrapper call. 24.9-f (manual-only for offline-paid) stays Partial pending an offline-payment-recording story; 24.9-i (QuickBooks tracking) is Out of Scope. • 24.6 [24.6-z] — shares-endpoint; residual: the refund HALF of 24.6-z is delivered by this endpoint. The VOID half is a SEPARATE endpoint (POST .../void) and remains Blocked (no Stripe void path / no Refund model) — do not fold void here. 24.6-z is overall Blocked in the input precisely because of the void half + net-new Refund model. • 24.11 [24.11-a, 24.11-b, 24.11-c, 24.11-d, 24.11-e] — shares-logic; residual: the send_notification toggle on the refund request + conditional refund-email dispatch — the SAME toggle logic as on the cancel endpoint (C2); needs the refund trigger_event/template seeded. | 24.6's refund action and 24.11's refund-email do not get their own routes/services; they are delivered by 24.9's single refund endpoint. Avoids duplicate refund implementations and reviews. | endpointCatalog POST /api/v1/orders/:id/refunds stories[24.9,24.6,24.11]; external-api-service /v1/refunds (stripe.refunds.create wrapper, internal) — VERIFIED ABSENT today (grep for refunds.create returns nothing across all repos), so it is net-new
C4 | subsumed-story | cross-reference | high | 24.10 | A single send_notification boolean (default true) + conditional MailerService.sendFromTemplate dispatch, applied identically on both POST .../cancel (24.10) and POST .../refunds (24.9) | • 24.11 [24.11-a, 24.11-b, 24.11-c, 24.11-d, 24.11-e] — subset; residual: the ONLY net-new work unique to 24.11 is seeding the cancellation and refund trigger_event slugs + notification templates (the notification-template create endpoint rejects a type with no matching trigger_event — gating detail from the 24.11 summary). The flag, default-checked behavior, unchecked-suppression and backend enforcement are inherent to the C2/C3 endpoints. Recommendation is cross-reference (NOT fold) because this template/trigger seeding is real, separately-deliverable work. | 24.11 needs no endpoint, controller, service or DTO of its own — its toggle is one request field reused on two endpoints. Review collapses to: confirm the boolean is honored server-side + the two templates/triggers are seeded. | endpointCatalog: 24.11 appears only as a member of POST .../cancel and POST .../refunds, introduces no route; MailerService.sendFromTemplate verified at background-worker-service/src/notification/mailer.service.ts:88 (writes notification_logs; reused by lead/low-balance/daily-summary crons)
C5 | subsumed-story | cross-reference | high | 24.14 | GET + PATCH /api/v1/orders/:id/notes — the single read/write path for internal notes, payment memo, invoice-note/PO, and additional terms (with per-change AdminAuditLog) | • 24.14 [24.14-a, 24.14-b, 24.14-c, 24.14-d, 24.14-e, 24.14-f, 24.14-g] — shares-endpoint; residual: owner — the notes GET/PATCH, the net-new payment_memo / invoice_note / additional_terms scalar columns on Order (VERIFIED: Order has only a free-text notes column at schema.prisma:1570; invoice_note/additional_terms exist on Cart at :2811-2812 but NOT on Order), and the audit-trail write. • 24.6 [24.6-c, 24.6-d, 24.6-e, 24.6-f] — subset; residual: the WRITE/EDIT of internal-notes / invoice-note / additional-terms / payment-memo is delivered by 24.14's PATCH .../notes (24.14-a/b/c/d) — these were removed from 24.6's PATCH .../:id. 24.6 retains only DISPLAY of these fields inside its GET .../:id aggregate (reading the columns 24.14 adds; no separate write path). NOTE: 24.6-d (Payment Memo) is 'Not Deliverable' in the input ONLY because the column does not exist yet — once 24.14 adds payment_memo + its PATCH (24.14-b), 24.6-d's edit IS delivered by 24.14 and only its display remains 24.6's. The catalog deliberately excludes 24.6-d from the notes-write requirements list, but the column dependency is real. | Avoids two write paths for the same note fields. 24.6 references 24.14 instead of building note-editing; only the read display lives in 24.6's detail aggregate. 24.6-d becomes deliverable once 24.14's payment_memo column lands. | endpointCatalog PATCH /api/v1/orders/:id/notes stories[24.14,24.6]; Order.notes schema.prisma:1570; Cart.invoice_note/additional_terms schema.prisma:2811-2812 (not on Order); account-history-notes module (admin/account-history-notes/account-history-notes.service.ts) is the working transactional note-update + AdminAuditService.record template
C6 | shared-implementation | cross-reference | high | 24.5 | GET /api/v1/orders/:id/agreement.pdf and /agreement.docx (reuse AgreementDocumentService / buildSimplePdf over OrderAgreement) | • 24.5 [24.5-e, 24.5-f] — shares-endpoint; residual: owner — the two format routes (.docx and .pdf) reusing the existing cart agreement generator (admin/cart/services/agreement-document.service.ts + utils/pdf.util.ts). • 24.6 [24.6-s] — subset; residual: none for the route — 24.6-s (view/download agreement) is format-agnostic and maps onto both routes 24.5 already builds; 24.6 introduces no separate agreement route. 24.6-s's 'Partial' verdict is a shared DATA caveat (not every order has an OrderAgreement row) that 24.5's routes inherit identically — it is not separate build work for 24.6. | 24.6's agreement view/download is delivered by 24.5's two routes; no duplicate agreement endpoint or generator wiring. | endpointCatalog GET /api/v1/orders/:id/agreement.pdf and .docx stories[24.5,24.6]; AgreementDocumentService verified at admin/cart/services/agreement-document.service.ts (+ utils/pdf.util.ts)
C7 | duplicate-requirement | build-once-reuse | high | 24.9 | external-api-service POST /v1/refunds (internal) — stripe.refunds.create against the order/installment stripe_charge_id, returning status so callers set Refunded / Refund Failed | • 24.9 [24.9-b, 24.9-g] — duplicate; residual: owner — builds the outbound Stripe refund wrapper (VERIFIED none exists today). • 24.10 [24.10-f] — shares-logic; residual: the cancel endpoint's Stripe-refund leg CALLS this same wrapper; residual is only wiring the call into the cancel transaction. Partial-refund amount accounting stays Blocked (24.10-h). • 24.6 [24.6-z] — shares-logic; residual: the refund action invoked from Order Details routes through 24.9's endpoint which calls this wrapper; no separate Stripe call. (Void half of 24.6-z is unrelated and Blocked.) | One Stripe refund integration point instead of three. Cancel, refund-management and the Order-Details refund all hit the same external-api wrapper. | endpointCatalog external-api-service /v1/refunds (internal) stories[24.9]; VERIFIED grep 'refunds.create' returns nothing across admin/external/exhibitor repos (only inbound charge.refunded webhook handling exists)
C8 | duplicate-requirement | build-once-reuse | high | 24.1 | The existing JWT + roles guard + @Permissions(...) decorator pattern applied on the Order Management controllers (no new mechanism — reuse src/auth/decorators/permissions.decorator.ts) | • 24.1 [24.1-m] — duplicate; residual: define the order-list permission key + apply the guard. • 24.2 [24.2-h] — duplicate; residual: none beyond the list guard it already inherits (same endpoint as 24.1). • 24.3 [24.3-g] — duplicate; residual: none beyond the list guard (same endpoint). • 24.4 [24.4-c] — duplicate; residual: none beyond the list guard (same endpoint). • 24.5 [24.5-l] — duplicate; residual: per-action permission keys (e.g. Booth-Build role) + the actions GET that returns gated set. • 24.6 [24.6-y] — duplicate; residual: per-action keys for edit/refund/void/sync/reassign on the detail routes. • 24.7 [24.7-d] — duplicate; residual: the method-eligibility gate (manual-method-only) is extra DOMAIN logic on top of the shared guard (24.7-d is Partial for that reason). • 24.8 [24.8-m] — duplicate; residual: plan totals/allocation/date-rule enforcement is domain logic beyond the guard. • 24.9 [24.9-h] — duplicate; residual: refund cap + mandatory-reason validation beyond the guard. • 24.10 [24.10-i] — duplicate; residual: none beyond applying the guard on cancel (audit-log half of 24.10-i is C9). • 24.12 [24.12-f] — duplicate; residual: none — inventory release runs inside the guarded cancel endpoint. • 24.13 [24.13-h] — duplicate; residual: none beyond applying the guard on move-show. • 24.14 [24.14-g] — duplicate; residual: none beyond applying the guard on notes routes. | "Enforced on the backend (RBAC/permissions)" is the same guard pattern in 13 stories. Recognize it as one reusable cross-cutting concern rather than re-analyzing/re-implementing auth per story; review focuses only on each route's permission KEY and any domain-specific gate. | src/auth/decorators/permissions.decorator.ts VERIFIED present; reused across admin modules
C9 | duplicate-requirement | build-once-reuse | high | 24.14 | AdminAuditService.record()/recordMany() with entity_type='order' (append-only, transaction-aware) — already implemented and in production use | • 24.14 [24.14-e] — duplicate; residual: owner of the order-notes audit trail; reuses the existing service + the existing GET /api/v1/logs/admin-audit read route (no new endpoint). • 24.7 [24.7-c] — duplicate; residual: one record() call inside the payment-status transaction. • 24.10 [24.10-i] — duplicate; residual: one record() call inside the cancel transaction (guard half of 24.10-i is C8). | "Status changes / actions shall be logged" is the same audit primitive across 3 mutating stories. Build zero new logging infra; each story adds a single record() call. The audit READ is the already-built admin-audit-log GET route. | AdminAuditService verified at admin/common/audit/admin-audit.service.ts (record/recordMany), used by configuration/gift-certificates/shows-management/account-history-notes/product-categories/notification-template/pricing-tier; endpointCatalog GET /api/v1/logs/admin-audit already exposes entity_type=order + entity_id (ALREADY BUILT)
C10 | duplicate-requirement | cross-reference | medium | 24.1 | A single source-of-truth for money figures: balance due = Order.total - Order.paid_amount, both read straight off the Order columns (there is NO separate 'centralized billing service'). The detail page's fee/subtotal breakdown is NOT part of this shared unit. | • 24.1 [24.1-f, 24.1-g, 24.1-n] — duplicate; residual: per-row Item Total (Order.total) + Balance Due (total - paid_amount) in the list projection — two scalar columns. 24.1-n's prescribed 'centralized billing service' component does not exist (Partial); figures come straight off Order columns. • 24.6 [24.6-o] — shares-logic; residual: MOSTLY SEPARATE WORK — the detail breakdown (Items Subtotal, Fees, Subtotal, Order Total, Balance Payable, Total Payable) is a richer aggregation over OrderItem + fees that the list does NOT compute. The ONLY genuinely shared part is the Order Total / Balance scalars off Order.total/paid_amount. Treat as cross-reference (agree on the authoritative source), not a reused computation. | Modest — agreeing that both surfaces read Order.total/paid_amount as the authoritative money source avoids two divergent balance calculations. The detail breakdown remains its own build. | schema.prisma:1573 Order.paid_amount 'Running sum ... bumped by webhook'; codebase_map: 'No separate centralized billing service' (pricing is in-process cart-pricing.service.ts)
C11 | duplicate-requirement | build-once-reuse | medium | 24.5 | MailerService.sendFromTemplate (renders a NotificationTemplate, sends via SendGrid, writes NotificationLog) — already built and proven | • 24.5 [24.5-i, 24.5-j] — shares-logic; residual: resend-confirmation and resend-portal-password each pick a fixed template — distinct endpoints, same mailer. (24.5-j password-reset may also route through an existing auth reset path; either way no new send infra.) • 24.6 [24.6-r] — shares-logic; residual: send-email dispatches an admin-SELECTED template (dropdown from notification-template list) — distinct selection UI, same mailer. • 24.11 [24.11-c] — shares-logic; residual: cancellation/refund email — same mailer; needs the trigger_event + template seeded (see C4). • 24.15 [24.15-c, 24.15-d] — shares-logic; residual: the cron calls the same mailer with upcoming/overdue templates — same dispatch primitive; the TRIGGERING (24.15-a/b/e/f/g) is Blocked on a manual-pay mark-as-Paid path, NOT a mailer concern. | No story builds an email-sending mechanism; each reuses the existing template mailer + NotificationLog. Review focuses on which template/recipient each uses, not on send infrastructure. | background-worker-service/src/notification/mailer.service.ts:88 sendFromTemplate VERIFIED; reused by lead-notification/low-balance/daily-summary crons
C12 | duplicate-requirement | build-once-reuse | medium | 24.12 | A net-new admin-side 'release reservations by order_id' helper — Prisma updateMany {order_id, status:committed} -> {status:released, released_at} (mirroring webhook.service.ts:2762-2765, which lives in external-api-service and is NOT reachable from admin) — plus reuse of the existing InventoryService.commitForCart (FOR UPDATE lock) for the move re-commit | • 24.12 [24.12-b, 24.12-c, 24.12-f] — shares-logic; residual: owner of the admin release helper; cancel calls release(order_id) for booth + non-booth committed lines inside the cancel transaction. Auto Social-Tables release (24.12-d) stays Blocked. • 24.13 [24.13-e, 24.13-i] — shares-logic; residual: move-show calls the SAME release helper for the source show, then re-maps each OrderItem to the destination ShowProduct and re-commits via InventoryService.commitForCart under FOR UPDATE. Net-new to 24.13: the line re-mapping + destination validation orchestration. Included-product availability (24.13-f) stays Partial (default-included lines are excluded from inventory commit). | The committed->released release logic is written ONCE in admin-backend-api and reused by both the cancel and move-show transactions, instead of two independent release implementations. Avoids two divergent reservation-state mutations. | admin/inventory/inventory.service.ts:104 commitForCart (FOR UPDATE) + :53 getAvailability, NO release method; release pattern proven at external-api-service/src/modules/webhook/services/webhook.service.ts:2762-2765 (committed->released by order_id); endpointCatalog POST .../cancel (24.12 release reqs) and POST .../move-show (24.13-i atomic release+commit)
C13 | shared-implementation | cross-reference | low | 24.8 | A single PaymentTransaction -> installment-row mapper (Invoice #, date, status, amount due, order total, amount paid, + next-installment derivation) reused by the three read surfaces | • 24.8 [24.8-a, 24.8-h] — shares-logic; residual: owner — the full payment-plan read with Unallocated Balance + 60/30-day warnings; the base installment row projection is the shared piece. Missing Payment Type / Payment Memo columns keep 24.8-a Partial. • 24.7 [24.7-a, 24.7-e] — shares-logic; residual: the Payments screen reuses the installment row projection but focuses on status/method; catalog deliberately keeps GET .../payments a DISTINCT endpoint from GET .../payment-plan. No endpoint merge — only the row mapper is shared. • 24.6 [24.6-p, 24.6-q] — shares-logic; residual: the detail aggregate embeds the payment-plan reference + next-installment amount/date (24.6-q), derivable from the same PaymentTransaction projection (next = earliest unpaid by due_date). 24.6-p stays Partial (cart_id linkage caveat). | Build the PaymentTransaction->row projection and next-installment derivation once; three read surfaces reuse it instead of three divergent installment mappers. Endpoints stay distinct (per catalog) — this is reuse of the projection, not a fold. | endpointCatalog notes on GET .../payments: 'Overlaps in data with GET .../payment-plan but kept distinct'; PaymentTransaction is the single installment ledger (one row per installment with amount, due_date, status, paid_at, invoice_id) per 24.8 summary

## Reqs Without Endpoint
Req ID | Why no endpoint (by design)
24.1-b | Blocked — booth-build orders are not yet produced; would be a data-scope behavior of the shared list endpoint, not a separate endpoint.
24.1-e | Out of Scope — per-row Quick Links are a UI affordance; no endpoint.
24.5-b | Out of Scope — Upsell quick action only links to the Upsell workflow.
24.5-c | Out of Scope — Onsite Sale quick action only links to the Onsite Sale workflow.
24.6-d | Not Deliverable — payment-memo display/edit is not modeled on Order; feasible payment-memo writes are handled by the 24.14 notes endpoint.
24.9-i | Out of Scope — refund-reason QuickBooks/accounting tracking.
24.10-h | Blocked — no Refund model exists to record/track refund activity; no endpoint.
24.10-j | Out of Scope — managing refunds individually at the plan level instead of cancelling.
24.12-d | Blocked — no Social Tables/floorplan integration for automatic booth release; no endpoint.
24.13-j | Out of Scope — operational note about creating floorplan inventory before retrying.
24.15-a | Cron-only / Blocked — automatic upcoming-payment reminder trigger; no REST endpoint.
24.15-b | Cron-only / Blocked — automatic overdue-payment reminder trigger; no REST endpoint.
24.15-d | No endpoint — payment-reminder templates are provided via seed/config, not an API.
24.15-f | Cron-only / Blocked — reminder stop-on-Paid logic runs in the scheduled job, not an endpoint.
24.15-h | UI-only — 'no dedicated screen' statement; no endpoint.