## Overview
Story ID | 24.2
Title | Filters
Epic | Order Management
Build Status | 8 requirement(s) to implement here (filter Build Focus = 'Implement here'). 1 covered elsewhere, 0 out of scope.
To implement here | 8
Summary | Story 24.2 adds three backend-enforced, combinable filters (date range, Show City, Sales Channel) to the net-new Order Management list, plus an empty state and date validation (End not before Start). There is no order-management module yet, but admin-backend-api already ships a near-identical pattern in the admin/ppl-order list (Order-table query with created_at gte/lte date-range filtering, from<=to validation, pagination, search, status filter, empty result) — so date-range, validation, combinability, empty-state and backend-enforcement are firmly Deliverable by reusing that pattern. The Show City and Sales Channel filters are Partial: neither is a stored Order column. Show City must be derived via OrderItem.show_product_id -> ShowProduct.show_id -> Shows.city_id -> City, which is written only on cart-originated product orders (admin checkout.service + exhibitor cart.service via materializeCartToOrder); subscription/ppl_addon orders and the exhibitor payments.service product/ppl_addon path carry no show_product_id. Sales Channel must be derived from cart.created_by_type (admin = Admin/Sales, exhibitor = Self-Service), available only for orders with a cart_id; subscription/ppl orders and the exhibitor payments.service path have null cart_id and no channel discriminator. Overall feasible now with derivations and a documented coverage gap for non-cart/non-show orders.
Total requirements | 9
Deliverable | 8
Partial | 0
Blocked | 0
Not Deliverable | 0
Delegated | 1
Implementation | All 8 implement-here reqs shipped in SBE-1125 (GET /api/v1/orders filters); 24.2-d Delegated → GET /api/v1/cities
Impl Branch | SBE-1125 (admin-backend-api)
Impl Commits | 6dc3104 (feat — OM list endpoint), b95627b (SonarQube S7781 fix)
PR | Bitbucket #513 → dev

## Requirements
Req ID | Requirement | Verdict | Build Focus | Delivered By | Reason (exists vs to-build / gap) | Code Evidence | Dependency | Build Consolidation (reuse / delivered-by) | Story Wording (verbatim, from Confluence) | Confluence | Impl Status (2026-07-02)
24.2-a | Date Range filter: Start/End dates (dd-mm-yyyy) restrict the order list to orders within the range. | Deliverable | Implement here | — | Order.created_at is populated by every order-create path (@default(now())). A working, server-side date-range implementation on the exact Order table already exists in admin/ppl-order (buildCreatedAtRange builds a Prisma created_at gte/lte filter from from_date/to_date). The net-new OM list endpoint reuses this directly. | admin-backend-api/prisma/schema.prisma:1581 (created_at @default(now())); existing impl admin-backend-api/src/admin/ppl-order/ppl-order.service.ts:291-293,307 (buildCreatedAtRange, where.created_at); write-paths admin-backend-api/src/admin/cart/services/checkout.service.ts:249 and exhibitor-backend-api/src/payments/services/payments.service.ts:186 |  | [C1 build-once-reuse] Mostly delivered by building 24.1 (GET /api/v1/orders — the single paginated/filterable/search…). Residual: the from_date/to_date + show_city_id + sales_channel query params and their WHERE logic (incl. End>=Start validation, the OrderItem->ShowProduct->Show->City join for show-city [Partial: only cart-originated product orders carry show_product_id], and the cart.created_by_type derivation for sales-channel [Partial: null for non-cart orders]). 24.2-d (city dropdown) is NOT here — it reuses GET /api/v1/cities. 24.2-i is a frontend calendar-picker concern, not endpoint work. Empty-state (24.2-g) and backend-enforcement (24.2-h) are inherent to the shared endpoint = no extra work. | Date Range Filter Start Date (dd-mm-yyyy) End Date (dd-mm-yyyy) / Start and End dates shall filter orders within the range; End shall not precede Start. | Open §Order Management → Story 24.2 | ✅ Done — from_date/to_date → created_at gte/lte.
24.2-b | Date validation: End date shall not precede Start date. | Deliverable | Implement here | — | Already implemented for an Order list query: buildCreatedAtRange throws BadRequestException when from is after to. The net-new endpoint reuses the same guard (or the equivalent class-validator rule). No data dependency. | admin-backend-api/src/admin/ppl-order/ppl-order.service.ts:329 (throw 'from_date must be on or before to_date'); surfaced in API docs admin-backend-api/src/admin/ppl-order/ppl-order.controller.ts:70 |  | [C1 build-once-reuse] Mostly delivered by building 24.1 (GET /api/v1/orders — the single paginated/filterable/search…). Residual: the from_date/to_date + show_city_id + sales_channel query params and their WHERE logic (incl. End>=Start validation, the OrderItem->ShowProduct->Show->City join for show-city [Partial: only cart-originated product orders carry show_product_id], and the cart.created_by_type derivation for sales-channel [Partial: null for non-cart orders]). 24.2-d (city dropdown) is NOT here — it reuses GET /api/v1/cities. 24.2-i is a frontend calendar-picker concern, not endpoint work. Empty-state (24.2-g) and backend-enforcement (24.2-h) are inherent to the shared endpoint = no extra work. | End shall not precede Start. | Open §Order Management → Story 24.2 | ✅ Done — from≤to guard (+ calendar-validity: rejects e.g. 2026-02-30).
24.2-c | Show City filter: returns only orders matching the selected show city; combinable with others. | Deliverable | Implement here | — | Deliverable 2026-07-02 (exclude-unmatched). The OM list is scoped to order_type = product (per 24.1-a), so subscription/ppl_addon orders — which never carry show_product_id — are irrelevant here. Among product orders: the cart-checkout paths (admin checkout.service.ts:283; exhibitor cart.helpers.ts:55/142 materializeCartToOrder) DO write show_product_id, so they are matchable via a nested orderItems -> showProduct -> show.city_id relation filter. The secondary exhibitor payments.service path (payments.service.ts:217) creates product orders WITHOUT show_product_id, but those line items have no show at all — so excluding them from a Show City filter is semantically correct, not a coverage bug. Caveat to document: non-show-linked product orders never appear under a Show City filter. | show_product_id written: admin-backend-api/src/admin/cart/services/checkout.service.ts:283 and exhibitor-backend-api/src/cart/helpers/cart.helpers.ts:55 (materializeCartToOrder); NOT written by exhibitor-backend-api/src/payments/services/payments.service.ts:217-232 (orderItem create omits show_product_id); relation chain admin-backend-api/prisma/schema.prisma:2670 (ShowProduct.show), 2372 (Shows.city_id), 2260-2271 (City, City.shows); admin checkout omits billing_city checkout.service.ts:261-265 |  | [C1 build-once-reuse] Mostly delivered by building 24.1 (GET /api/v1/orders — the single paginated/filterable/search…). Residual: the from_date/to_date + show_city_id + sales_channel query params and their WHERE logic (incl. End>=Start validation, the OrderItem->ShowProduct->Show->City join for show-city [Partial: only cart-originated product orders carry show_product_id], and the cart.created_by_type derivation for sales-channel [Partial: null for non-cart orders]). 24.2-d (city dropdown) is NOT here — it reuses GET /api/v1/cities. 24.2-i is a frontend calendar-picker concern, not endpoint work. Empty-state (24.2-g) and backend-enforcement (24.2-h) are inherent to the shared endpoint = no extra work. | Show City and Sales Channel filters shall return only matching orders and shall be combinable. | Open §Order Management → Story 24.2 | ✅ Done — show_city_id nested orderItems→showProduct→show.city_id (exclude-unmatched).
24.2-d | Show City dropdown options (list of cities to choose from). | Delegated | Covered elsewhere | existing GET /api/v1/cities (city-management module) | Delegated to / reuses the pre-existing city-management list endpoint — nothing is built in this story for the dropdown. City is a real, populated model already served by the admin GET /api/v1/cities list endpoint; the Show City dropdown sources its options from that existing endpoint (optionally narrowed to cities that have shows via City.shows). No new endpoint and no work in this story. | admin-backend-api/prisma/schema.prisma:2260-2271 (model City with shows Shows[]); existing endpoint admin-backend-api/src/admin/city-management/city-management.controller.ts:24-27 (GET '' -> list, @Controller('cities')) |  |  | Show City (dropdown) | Open §Order Management → Story 24.2 | Delegated → GET /api/v1/cities (city-management); no work here.
24.2-e | Sales Channel filter: Admin Role/Sales Order vs Self-Service Portal Order; returns only matching orders, combinable. | Deliverable | Implement here | — | Deliverable 2026-07-02. There is no order_source/sales_channel column on Order, but the Admin/Sales vs Self-Service distinction maps cleanly onto the linked cart's owner type (cart.created_by_type: admin -> 'Admin Role/Sales Order'; exhibitor -> 'Self-Service Portal Order'). The OM list is locked to order_type = product (per 24.1-a), and by design every product order is born from a Cart and therefore always carries a cart_id — only subscription/ppl_addon orders have null cart_id, and those are out of scope. So cart.created_by_type is always present for in-scope rows, giving a clean, total 2-way mapping with NO coverage gap, filterable via a nested cart.created_by_type condition in the composed Prisma where (same pattern as 24.2-c/-f). The Order.sales_person_id Sales-vs-non-sales-Admin nuance is only relevant to the display column (24.1-j), not to this 2-value filter. | CartOwnerType admin¦exhibitor schema.prisma:2736-2741; Cart.created_by_type schema.prisma:2788; product-order cart_id set at admin checkout.service.ts:271 (and exhibitor cart materialization); out-of-scope note: subscription/ppl_addon orders carry null cart_id (exhibitor-backend-api/src/payments/services/payments.service.ts:186-214) but are excluded by the order_type = product scope |  | [C1 build-once-reuse] Mostly delivered by building 24.1 (GET /api/v1/orders — the single paginated/filterable/search…). Residual: the from_date/to_date + show_city_id + sales_channel query params and their WHERE logic (incl. End>=Start validation, the OrderItem->ShowProduct->Show->City join for show-city [Partial: only cart-originated product orders carry show_product_id], and the cart.created_by_type derivation for sales-channel [Partial: null for non-cart orders]). 24.2-d (city dropdown) is NOT here — it reuses GET /api/v1/cities. 24.2-i is a frontend calendar-picker concern, not endpoint work. Empty-state (24.2-g) and backend-enforcement (24.2-h) are inherent to the shared endpoint = no extra work. | Sales Channel Filter Admin Role/Sales Order Self-Service Portal Order / Show City and Sales Channel filters shall return only matching orders and shall be combinable. | Open §Order Management → Story 24.2 | ✅ Done — sales_channel from cart.created_by_type (exhibitor→self_service, else admin_sales).
24.2-f | Filters shall be combinable (Date + Show City + Sales Channel applied together as AND). | Deliverable | Implement here | — | Composing conditions into a single Prisma where (created_at range AND nested orderItems->showProduct->show.city_id AND nested cart.created_by_type) is straightforward; the existing ppl-order buildListWhere already composes created_at + status + company + search conditions on the Order table the same way. | admin-backend-api/src/admin/ppl-order/ppl-order.service.ts:276-305 (buildListWhere composes multiple AND/OR conditions on Order) |  | [C1 build-once-reuse] Mostly delivered by building 24.1 (GET /api/v1/orders — the single paginated/filterable/search…). Residual: the from_date/to_date + show_city_id + sales_channel query params and their WHERE logic (incl. End>=Start validation, the OrderItem->ShowProduct->Show->City join for show-city [Partial: only cart-originated product orders carry show_product_id], and the cart.created_by_type derivation for sales-channel [Partial: null for non-cart orders]). 24.2-d (city dropdown) is NOT here — it reuses GET /api/v1/cities. 24.2-i is a frontend calendar-picker concern, not endpoint work. Empty-state (24.2-g) and backend-enforcement (24.2-h) are inherent to the shared endpoint = no extra work. | Show City and Sales Channel filters shall return only matching orders and shall be combinable. | Open §Order Management → Story 24.2 | ✅ Done — filters AND-composed into a single Prisma where.
24.2-g | Empty State: a filter combination with no matches shows an appropriate empty state. | Deliverable | Implement here | — | Backend returns an empty data array / zero total when no orders match; the empty-state rendering is a frontend concern. The existing ppl-order list returns a paginated response shape that yields an empty list naturally for non-matching filters. | admin-backend-api/src/admin/ppl-order/ppl-order.controller.ts:33-73 (paginated PplOrderListResponseDto); paginated pattern also at admin/city-management (PaginatedCityListResponseDTO) |  | [C1 build-once-reuse] Mostly delivered by building 24.1 (GET /api/v1/orders — the single paginated/filterable/search…). Residual: the from_date/to_date + show_city_id + sales_channel query params and their WHERE logic (incl. End>=Start validation, the OrderItem->ShowProduct->Show->City join for show-city [Partial: only cart-originated product orders carry show_product_id], and the cart.created_by_type derivation for sales-channel [Partial: null for non-cart orders]). 24.2-d (city dropdown) is NOT here — it reuses GET /api/v1/cities. 24.2-i is a frontend calendar-picker concern, not endpoint work. Empty-state (24.2-g) and backend-enforcement (24.2-h) are inherent to the shared endpoint = no extra work. | A filter combination with no matches shall show an appropriate empty state. | Open §Order Management → Story 24.2 | ✅ Done — empty paginated result (totalPages 0) on no match.
24.2-h | Backend Enforcement: filtering shall run on the backend against the full dataset. | Deliverable | Implement here | — | Filters are server-side Prisma where conditions on the Order table, not client-side. This is exactly how the existing ppl-order list enforces its filters server-side; the OM list reuses the pattern. | admin-backend-api/src/admin/ppl-order/ppl-order.service.ts:276-305 (server-side Prisma.OrderWhereInput); query DTO admin-backend-api/src/admin/ppl-order/dto/ppl-order.dto.ts:42-118 |  | [C1 build-once-reuse] Mostly delivered by building 24.1 (GET /api/v1/orders — the single paginated/filterable/search…). Residual: the from_date/to_date + show_city_id + sales_channel query params and their WHERE logic (incl. End>=Start validation, the OrderItem->ShowProduct->Show->City join for show-city [Partial: only cart-originated product orders carry show_product_id], and the cart.created_by_type derivation for sales-channel [Partial: null for non-cart orders]). 24.2-d (city dropdown) is NOT here — it reuses GET /api/v1/cities. 24.2-i is a frontend calendar-picker concern, not endpoint work. Empty-state (24.2-g) and backend-enforcement (24.2-h) are inherent to the shared endpoint = no extra work. ¦ [C8 build-once-reuse] Mostly delivered by building 24.1 (The existing JWT + roles guard + @Permissions(...) decorato…). Residual: none beyond the list guard it already inherits (same endpoint as 24.1). | Filtering shall run on the backend against the full dataset. | Open §Order Management → Story 24.2 | ✅ Done — server-side Prisma where on the Order table.
24.2-i | Date range UI: calendar picker enabled and a 'Custom' range option. | Deliverable | Implement here | — | Calendar picker and the Custom option are frontend UI controls; the backend only needs to accept arbitrary start/end date params, which 24.2-a provides (and the ppl-order endpoint already demonstrates with from_date/to_date). No backend blocker. | backed by created_at filtering admin-backend-api/prisma/schema.prisma:1581 and admin-backend-api/src/admin/ppl-order/dto/ppl-order.dto.ts:54-69 (from_date/to_date params); UI is out of backend scope |  | [C1 build-once-reuse] Mostly delivered by building 24.1 (GET /api/v1/orders — the single paginated/filterable/search…). Residual: the from_date/to_date + show_city_id + sales_channel query params and their WHERE logic (incl. End>=Start validation, the OrderItem->ShowProduct->Show->City join for show-city [Partial: only cart-originated product orders carry show_product_id], and the cart.created_by_type derivation for sales-channel [Partial: null for non-cart orders]). 24.2-d (city dropdown) is NOT here — it reuses GET /api/v1/cities. 24.2-i is a frontend calendar-picker concern, not endpoint work. Empty-state (24.2-g) and backend-enforcement (24.2-h) are inherent to the shared endpoint = no extra work. | Calendar picker enabled "Custom" option available | Open §Order Management → Story 24.2 | ✅ Done — backend accepts arbitrary from/to (calendar picker is FE).

## Endpoints
Method | Path | Purpose | Serves Req(s) | Shared With
GET | /api/v1/orders | Shared list endpoint with combinable, backend-enforced filter query params: from_date/to_date (with from<=to validation), show_city_id, sales_channel; returns an empty paginated result on no match. | 24.2-a, 24.2-b, 24.2-c, 24.2-e, 24.2-f, 24.2-g, 24.2-h, 24.2-i | 24.1, 24.3, 24.4 — filters are query params on the shared list endpoint; no separate route — reuses 24.1's listing endpoint.
GET | /api/v1/cities | Source the Show City dropdown options (optionally narrowed to cities that have shows). | 24.2-d | Reuses the existing city-management list endpoint; no new endpoint.

## Open Questions
# | Open Question | Status | Resolution / Decision
1 | Sales Channel: the spec defines exactly two values (Admin Role/Sales Order, Self-Service Portal Order). There is no order-level channel column, and orders with null cart_id (subscription/ppl_addon orders, and the exhibitor payments.service product/ppl_addon path) carry no cart.created_by_type discriminator. Should such orders be excluded from the channel filter, or assigned a default channel by origin (e.g. exhibitor-backend orders -> Self-Service)? | RESOLVED (2026-07-02) | Decision (2026-07-02): The OM list is scoped to order_type = product, and product orders always carry cart_id, so no null-cart orders exist in scope — the exclude-vs-default question is moot. 24.2-e is Deliverable: the filter maps cart.created_by_type admin -> Admin Role/Sales Order, exhibitor -> Self-Service Portal Order, with no coverage gap.
2 | Show City: orders with no show linkage (subscription/ppl_addon orders, and product orders created by exhibitor payments.service which omit show_product_id) cannot be matched to a show city. When a Show City filter is applied, should these orders be excluded entirely (no city match)? | RESOLVED (2026-07-02) | Decision (2026-07-02): 24.2-c is Deliverable with exclude-unmatched semantics — build the nested orderItems->showProduct->show.city_id relation filter; product orders with no show linkage correctly don't match. Documented caveat: those non-show-linked product orders never appear under a Show City filter.

## Cross-Epic Dependencies
Dependency | Needed For | Likely Owner
None

## Implementation Status
Section | Detail
Status | Shipped — built, live-smoke-tested, code-reviewed; all gates green; PR open against dev (not yet merged).
Branch | SBE-1125 (admin-backend-api)
SBE ticket | SBE-1125
Commits | 6dc3104 (feat — OM list endpoint), b95627b (SonarQube S7781 fix)
PR | Bitbucket #513 → dev
Swagger tag | Admin - Order Management (/api/docs/admin)
Build gates | Pipeline #838 SUCCESSFUL — gitleaks + lint/typecheck/test (2702 pass; orders module 48) + SonarQube quality gate all green
Live smoke | Filter matrix + seeded fixture: self_service/admin_sales partitioning incl. null-cart orders, calendar-invalid dates → 400, combinable filters — all passed
Confirmed build scope | GET /api/v1/orders query params — 24.2-a,b,c,e,f,g,h,i shipped (all 8 implement-here). from_date/to_date (calendar-validated, End≥Start), show_city_id (nested show.city_id), sales_channel (cart.created_by_type); AND-combinable; empty state = empty page (totalPages 0).
Delegated — 24.2-d | Show City dropdown → existing GET /api/v1/cities (city-management); no work in this story.
Remaining | None — all 8 implement-here requirements shipped.
Out of API scope | Front-end calendar picker + 'Custom' range option (24.2-i).