## Overview
Story ID | 24.15
Title | Payment Reminder Notifications
Epic | Order Management
Build Status | SCOPE LOCKED at Step-1 gate 2026-07-03 (final story of the 7-story gate). 8/8 Deliverable — 5 sequenced intra-release on 24.8, 3 buildable now. Ship-together release; 24.15 builds LAST.
To implement here | 8
Summary | Gate outcome: independent worker cron (D4a — not waiting for the unstarted E&S scheduling system; hand-off note to the scheduling register), email-only (D1), settings-driven cadence (D2: payment_reminder_{upcoming_days,overdue_interval_days,hour_utc} = 7/7/14 pending BA — spec specifies NOTHING; gate directive: document provenance in code), manual-rows-only predicates mirroring the 24.8-D3 cron guard (disjoint partition), self-seeded slugs per the ownership rule, stop = PT.status read at send time (24.8 PATCH / 24.6 void) — no new state anywhere. All five former Blocked verdicts re-resolved to Deliverable-sequenced under the ship-together model.
Sequenced on 24.8 | 5 (a, b, e, f, g) — in-release, 24.8 builds first
Total requirements | 8
Deliverable | 8
Partial | 0
Blocked | 0
Not Deliverable | 0
Out of Scope | 0
Implementation | Not started — scope locked 2026-07-03 (gate complete); plan after full 7-story gate
Impl Branch | —
Impl Commits | —
PR | —

## Requirements
Req ID | Requirement | Verdict | Build Focus | Delivered By | Reason (exists vs to-build / gap) | Code Evidence | Dependency | Build Consolidation (reuse / delivered-by) | Story Wording (verbatim, from Confluence) | Confluence | Impl Status (2026-07-03)
24.15-a | System shall automatically trigger reminder notifications to customers for UPCOMING payments. | Deliverable — sequenced intra-release (24.8) | Implement here |  | Re-resolved from Blocked (ship-together release; 24.8 builds first). Cron mechanics always buildable ([status,due_date] index); the missing SEMANTIC — customer-actionable manual installment — is 24.8's payment_type column. Selection: status=scheduled AND payment_type != credit_card AND due_date <= now()+upcoming_days — mirror image of the charge cron's 24.8-D3 guard, so the two crons partition rows disjointly by construction. D3 (interim predicate) RESOLVED-BY-SEQUENCING: 24.15 builds after 24.8, so the manual-rows predicate ships day one (no dark launch, no courtesy-email interim). | PT :2073 (webhook-owned transitions), due_date :2086, index :2103; worker payment-charge.service.ts:60-67; 24.8 gate D2/D3 locked 2026-07-03 | 24.8 payment_type migration + cron guard — same release, builds first |  | The system shall automatically trigger reminder notifications to customers for upcoming or overdue payments. / Reminders shall be sent for upcoming and overdue payments. | Open §Order Management → Story 24.15 | Gate 2026-07-03: Blocked -> Deliverable-sequenced (D3 resolved-by-sequencing).
24.15-b | System shall automatically trigger reminder notifications to customers for OVERDUE payments. | Deliverable — sequenced intra-release (24.8) | Implement here |  | Re-resolved from Blocked. No stored 'overdue' — by design: mirror exhibitor deriveIsOverdue (due past AND status not in settled {succeeded,refunded,canceled}). Manual rows never cron-charged (24.8 guard) -> overdue-manual = scheduled AND past-due AND payment_type != credit_card, repeating per overdue_interval_days w/ notification_logs dedupe. SUB-DECISION (option a, locked): retry-exhausted card rows (failed, retry_count=3) EXCLUDED — story is manual-framed; those rows already get the per-failure update-card email; BA may extend later (OQ-2). | PaymentTransactionStatus :491-500 (no overdue value); MAX_AUTO_RETRIES=3 :18, retryFailed :74-82; exhibitor orders.helpers.ts:74-79 deriveIsOverdue, settled set :31 | 24.8 payment_type migration — same release |  | The system shall automatically trigger reminder notifications to customers for upcoming or overdue payments. / Reminders shall be sent for upcoming and overdue payments. | Open §Order Management → Story 24.15 | Gate 2026-07-03: Blocked -> Deliverable-sequenced (manual-only, option a).
24.15-c | Reminder delivery engine: send a templated notification to the customer via a backend scheduled job (cron). | Deliverable | Implement here |  | Buildable NOW, independent of 24.8. D4a: INDEPENDENT worker cron (not waiting for the unstarted E&S dynamic-scheduling system, which claims payment-due reminders — hand-off note filed in the SCHEDULING register per register-separation rule, OQ-4). Clone the payment-charge registrar/task pair (settings hours, CronJob.from + registry.addCronJob, per-kind overlap guard); reads the D2 settings family; dispatch via WORKER MailerService.sendFromTemplate (SendGrid; NotificationLog PENDING->SENT/FAILED). Worker has exactly 5 registrars, zero 'reminder' hits. MAILER SPLIT: cron leg = worker mailer; admin-triggered action emails (24.6-r/24.11/24.5) = admin's mailer; both write notification_logs — keep notification_type consistent. | registrar :63-84 (hours :40-41, defaults 02:00/06:00); task :22/:32/:65; worker mailer.service.ts:88 (sgMail :5; log :48/:124/:160/:176); low-balance.service.ts precedent |  | [C11 build-once-reuse] Mostly delivered by building 24.5 (MailerService.sendFromTemplate (renders a NotificationTempl…). Residual: the cron calls the same mailer with upcoming/overdue templates — same dispatch primitive; the TRIGGERING (24.15-a/b/e/f/g) is Blocked on a manual-pay mark-as-Paid path, NOT a mailer concern. | (no verbatim line — derived from System Specification: "The system shall automatically trigger reminder notifications" + Backend Enforcement: "Reminder scheduling and stop logic shall be enforced on the backend.") | Open §Order Management → Story 24.15 | Gate 2026-07-03: Deliverable (D4a independent cron).
24.15-d | Provide payment-reminder notification templates (upcoming + overdue) for the customer. | Deliverable | Implement here |  | Buildable NOW. D1 EMAIL-ONLY (SendGrid is the only dispatch path; SMS = enum value w/ no client in any repo; enum accommodates SMS later w/o migration). D5 slugs payment_reminder_upcoming / payment_reminder_overdue, seeded BY 24.15 per the template-ownership rule (locked 24.11: flows own their templates; E&S epic manages only). SBE-671 MERGED — unmerged-branch collision concern retired; dev's 29 trigger slugs have zero reminder entries (no collision). Placeholders from PT + order context (amount, due date, order number, method label via payment_type); copy at plan time, admin-editable after. | NotificationTemplate :255; NotificationChannel :239-242; template seeder :142/:619 (receipt only); trigger-event seeder 29 slugs (verified 2026-07-03); SBE-671 merged PR#426 |  | [C11 build-once-reuse] Mostly delivered by building 24.5 (MailerService.sendFromTemplate (renders a NotificationTempl…). Residual: the cron calls the same mailer with upcoming/overdue templates — same dispatch primitive; the TRIGGERING (24.15-a/b/e/f/g) is Blocked on a manual-pay mark-as-Paid path, NOT a mailer concern. | (no verbatim line — derived from System Specification: "The system shall automatically trigger reminder notifications to customers for upcoming or overdue payments.") | Open §Order Management → Story 24.15 | Gate 2026-07-03: Deliverable (D1 email-only; D5 self-seeded slugs).
24.15-e | Reminders shall CONTINUE (repeat) until the installment is marked Paid. | Deliverable — sequenced intra-release (24.8) | Implement here |  | Re-resolved from Blocked: NO NEW STATE — cron re-selects unpaid rows each tick and checks PT.status at send time; when 24.8's PATCH flips succeeded (or 24.6's void -> canceled) the row drops out naturally. Dedupe-per-interval (D2) bounds 'continues' to the configured cadence. Recipient: billing_email per 24.11 chain; additional_emails CC pending consolidated OQ (with 24.6) — if ratified, one-line CC-append. | webhook.service.ts:738 (current sole succeeded writer); no installment write-path on dev (re-grepped 2026-07-03); 24.8-c locked semantics | 24.8 installment PATCH — same release |  | Reminder notifications shall continue until the payment status is manually updated as "Paid" from the admin panel. / Reminders shall continue until the installment is marked Paid. | Open §Order Management → Story 24.15 | Gate 2026-07-03: Blocked -> Deliverable-sequenced (no new state; recipient locked).
24.15-f | Stop condition: once the admin marks the installment Paid from the admin panel, all future reminders for that installment stop automatically. | Deliverable — sequenced intra-release (24.8) | Implement here |  | Re-resolved from Blocked: mark-as-Paid = 24.8's PATCH :id/payment-plan/installments/:installmentId (locked at its gate: manual-method-only, Paid -> succeeded). Stop check is the SAME status read as 24.15-e — same build; works the day 24.8 ships (before 24.15 in release order). Evidence refresh: PaymentTransactionSource now 6 values (+admin_change_plan, +admin_manual per 24.8-D4) — no exhaustive switch may assume fewer. | 24.8 doc 24.8-c/D4 locked 2026-07-03; PaymentTransactionSource :503-511 (6 values) | 24.8 installment PATCH — same release |  | Once the payment is marked as paid by the admin, all future reminders for that installment shall stop automatically. / Marking an installment Paid shall stop its future reminders. | Open §Order Management → Story 24.15 | Gate 2026-07-03: Blocked -> Deliverable-sequenced (+ source-enum refresh).
24.15-g | Reminder scheduling AND stop logic shall be enforced on the backend (not the client). | Deliverable — sequenced intra-release (24.8) | Implement here |  | Re-resolved from Blocked: scheduling half = worker cron (no client involvement by construction); stop half = e/f status check, sequenced on 24.8. CORRECTION from later gates: 24.7's order-level PATCH :id/payment-status (the old 'secondary stop signal') was DROPPED at the 24.7 gate — stop signals are exactly 24.8's PATCH (succeeded) and 24.6's void (canceled), both covered by the settled-set check without special-casing. | registrar refs (24.15-c); 24.7 doc D3 (PATCH dropped, locked 2026-07-03) | 24.8 (stop half) — same release |  | Backend Enforcement Reminder scheduling and stop logic shall be enforced on the backend. | Open §Order Management → Story 24.15 | Gate 2026-07-03: Blocked -> Deliverable-sequenced (24.7 correction folded in).
24.15-h | No dedicated screen — the feature is purely an automatic backend behavior with no UI. | Deliverable | Implement here |  | Buildable NOW. Cron-only + one dev-only POST manual-trigger/payment-reminders/run (controller has exactly the lead-distribution + low-balance precedents). Nav-clause tension ('System, payment reminders' breadcrumb vs UI-less Design Spec) resolved cheaply by D2: the settings family IS the future config surface if BA ever wants one; flagged in OQ-1. | manual-trigger.controller.ts :17/:26/:55 (only 2 handlers today) |  |  | No dedicated screen; the system shall send upcoming and overdue payment reminders that automatically stop once the installment is marked Paid. | Open §Order Management → Story 24.15 | Gate 2026-07-03: Deliverable.

## Endpoints
Method | Path | Purpose | Serves Req(s) | Shared With
POST | background-worker-service: /manual-trigger/payment-reminders/run | Dev-only manual trigger invoking the reminder task on demand (mirrors low-balance/lead precedents). The feature itself is a registered cron — no customer/admin REST or UI endpoint. | 24.15-c, e, g, h | Stop condition reads statuses written by 24.8's PATCH + 24.6's void
(settings) | payment_reminder_upcoming_days / payment_reminder_overdue_interval_days / payment_reminder_hour_utc | ppl-settings family (defaults 7 / 7 / 14 UTC pending BA ratification, OQ-1) with gate-provenance doc-comments per the D2 directive — the spec contains NO cadence/window/hour anywhere. | 24.15-a, b, e | Mirrors payment_charge_hour_utc family

## Open Questions
# | Req | Item | Verdict | Open Question / What is needed | Dependency (blocking story + Jira) | Assignee | Sprint / Jira status | Decision / Current direction
OQ-1 | 24.15-a/b/e (D2) | Cadence defaults ratification + nav clause | Deliverable (mechanism locked) | Ratify proposed defaults: upcoming 7 days before due (single send); overdue every 7 days after due until settled; send hour 14:00 UTC. Values exist NOWHERE in the spec — set at the 2026-07-03 gate; settings-driven so BA's answer changes a seeded default, not code. Also: does the 'System, payment reminders' nav breadcrumb imply a cadence-config screen? (Build is UI-less per 24.15-h; the settings family is the natural surface if yes.) | — | BA | Open 2026-07-03 | Build proceeds on defaults; code doc-comments state provenance + pending ratification (gate directive).
OQ-2 | 24.15-b | Retry-exhausted card rows excluded | Deliverable (manual-only locked) | Overdue reminders select MANUAL rows only. Stuck card rows (failed, retry_count=3, abandoned by retry cron) are customer-actionable but excluded — they already get the per-failure update-card email. BA may extend the predicate later (small change: widen the status/type filter). | — | BA | Open 2026-07-03 | Option (a) locked; extension is a predicate tweak, not a redesign.
OQ-3 | 24.15-e (recipient) | additional_emails CC scope | Deliverable (to = billing_email locked) | Consolidated with 24.6's OQ-2 — ONE BA answer for all four senders (24.6-r, 24.11, 24.15, 24.5). If ratified: one-line CC-append in this cron's dispatch. | — | BA | Open 2026-07-03 | Reminders go to billing_email until answered.
OQ-4 | 24.15-c (D4) | Scheduling-system hand-off | Deliverable (independent cron locked) | E&S dynamic-scheduling design (implementation not started) claims payment-due reminders (ANCHOR_RELATIVE). 24.15 ships independent; the future scheduling build must absorb or knowingly coexist with this cron. Hand-off note to be filed in the SCHEDULING known-issues register (per register-separation rule — NOT the main E&S register) when 24.15 ships. | E&S scheduling implementation (unstarted; own doc set) | — (recorded for the scheduling effort) | Design done, build not started | D4a locked: ship now, migrate later.

## Cross-Epic Dependencies
Dependency | Needed For | Likely Owner
In-release (NOT external): 24.8 payment_type migration + cron guard + installment PATCH (SBE-1132) — manual lifecycle, selection column, stop signal | 24.15-a, b, e, f, g | Same release — 24.8 builds first; 24.15 builds last
In-release: 24.6 void endpoint (canceled rows drop out via the settled-set check) | 24.15-e/f stop coverage | Same release (24.6, D-z)
E&S dynamic-scheduling system (future) — absorbs/supersedes this cron per OQ-4 hand-off | post-release migration only | E&S scheduling effort (docs done, build unstarted)

## Implementation Status
Section | Detail
Status | Not started — Step-1 gate complete 2026-07-03 (8-item walkthrough with Prantik; FINAL story of the 7-story gate). Scope locked: 8/8 Deliverable — 5 sequenced intra-release on 24.8 (a,b,e,f,g), 3 independently buildable (c,d,h). Release model: ship-together; 24.15 builds LAST.
Branch | —
SBE ticket | SBE-1139 (In Progress, Prantik Saha)
Commits | —
PR | —
Swagger tag | —
Build gates | —
Live smoke | —
Confirmed build scope | Independent worker cron (clone payment-charge registrar/task pair) + selection predicates (upcoming/overdue, manual rows only via payment_type) + 2 EMAIL templates + slugs payment_reminder_upcoming/overdue (self-seeded) + 3 ppl-settings knobs (7/7/14 defaults, gate-provenance doc-comments REQUIRED) + notification_logs dedupe + dev-only manual trigger. Recipient = billing_email.
Decisions | D1 email-only · D2 settings mechanism (values pending BA, OQ-1) · D3 resolved-by-sequencing · D4a independent cron (hand-off OQ-4) · D5 self-seeded slugs · 24.15-b manual-only (OQ-2)
External dependencies — see Cross-Epic Dependencies | None external; in-release: 24.8 (builds first) + 24.6 void
Out of API scope | FE anything (story is UI-less); SMS channel (D1 — enum-ready, no client)
Evidence baseline | Verified @admin 0ac2769 (+4 siblings) 2026-07-03; line-drift corrections applied (PT :2073, seeder :142/:619, registrar :63-84, source enum 6 values); dev same-day move to 34c6fb4 does not touch this story's evidence.