## Open Questions for BA
# | Category | Req ID | Topic | Open Question | Why it matters / what it blocks | Priority
1 | Scope | 13.x | Cross-cutting | Four referenced user stories are NOT included in this file: 'Payment Schedule Visibility', 'Credit Card Payment Workflow', 'Booth Upgrade', and 'View Onsite Booth Contact'. Can you share these stories / their data contracts? Several Order Details sections (payment schedule, early-pay, booth upgrade, onsite contact) depend on them. | Blocks: 13.2 Pay action, 13.3 Payment schedule, 13.3 Upgrade details, 13.3 Onsite contact | High
2 | Architecture | 13.2 / 13.3 | Cross-cutting | The requirements repeatedly say Total Amount and Total Saving Made are 'computed by the centralized billing service'. No such service exists in any of the 5 repos. Does this mean (a) read the values already snapshotted on the Order at checkout (Order.total / Order.total_savings), or (b) a separate authoritative billing service must (re)compute them at read time? If (b), where does it live and is building it in scope? | Affects: 13.2 Total Amount, 13.3 Financial Summary, 13.3 reconciliation | High
3 | Data model | 13.2 | Payment plans | 13.2 says an order 'may have one or more payment plans or scheduled payment installments'. The DB models installments as a FLAT set of rows per order (no parent 'payment plan' entity grouping them). Is a single order ever expected to carry MULTIPLE distinct payment plans, or is 'payment plan' just the order's one installment schedule? | Affects: 13.2 payment status derivation, 13.3 payment schedule | High
4 | Requirement detail | 13.1 | Order History page | Should canceled/failed and soft-deleted (deleted_at != null) orders appear in the Order History list, or only the active/successful ones? This affects the base query filter. | Verdict: Deliverable. No data-model gap. There is no existing orders/order-history module in exhibitor-backend-api (confirmed: no src/orders dir, only GET agreement/signed/:orderId/d | Low
5 | Requirement detail | 13.2 | Order Listing Table | Should the listing display order_number (e.g. ORD-2026-00001) or the numeric Order.id as 'Order ID'? | Verdict: Deliverable. | Low
6 | Requirement detail | 13.2 | Order Listing Table | Map 'Paid in Full' to OrderStatus.completed and 'Unpaid' to pending — or compute purely from paid_amount vs total and PaymentTransaction rollups? Confirm whether refunded/canceled orders appear in the listing and how their Payment Status renders. | Verdict: Partial. OrderStatus enum (schema:418) has only pending¦partially_paid¦completed¦failed¦refunded¦canceled — NO literal 'unpaid' or 'paid in full'. Raw inputs exist (Orde | Medium
7 | Requirement detail | 13.2 | Order Listing Table | 13.2 says an order may have 'one or more payment plans' — but the schema has only a flat set of PaymentTransaction installments per order (no PaymentPlan grouping). Is one Order ever expected to carry MULTIPLE distinct payment plans, or is 'payment plan' synonymous with the order's single installment schedule? And should Overdue be a derived/computed state or a persisted enum value? | Verdict: Partial. PaymentTransaction (the de-facto payment-plan/installment model) has status enum scheduled¦processing¦succeeded¦failed¦canceled¦refunded with NO 'overdue' value | Medium
8 | Requirement detail | 13.2 | Order Listing Table | For non-product orders (subscription / ppl_addon) that have no show linkage, what should the 'Associated Shows' column display — blank, the subscription name, or are those orders excluded from this listing entirely? | Verdict: Partial. Order has NO direct show_id (verified at schema.prisma:1532-1596 — no show_id/show relation). Associated Shows is derivable ONLY via OrderItem.show_product_id ( | Medium
9 | Requirement detail | 13.2 | Order Listing Table | Confirm the intended grouping semantics: ONE listing row per order with all its shows listed inside it, OR rows grouped/clustered by show? And how should a multi-city order's 'Total Amount' be presented when grouped (single order total vs per-show split)? | Verdict: Partial. No denormalized show grouping exists on Order; grouping must be COMPUTED by joining OrderItem.show_product_id -> ShowProduct -> Shows and aggregating per order. | Medium
10 | Requirement detail | 13.2 | Order Listing Table | Should the order-history Invoice action reuse/generalize the existing PPL pdfkit renderer, or is invoice PDF generation owned by an external/QuickBooks flow (Order.quickbooks_order_id exists)? Confirm expected invoice template/branding. | Verdict: Partial. Invoice/InvoiceLineItem data models exist (schema:1953/1987) but Invoice has NO file_url/PDF field and no stored invoice document. A working pdfkit renderer exi | Medium
11 | Requirement detail | 13.2 | Order Listing Table | The Pay action references external stories (Payment Schedule Visibility, Credit Card Payment Workflow) not provided. What is the exact early-pay behavior — pay the full remaining balance, the next single installment, or all remaining installments at once? And must it always use the salesperson-set payment method, or may the exhibitor choose a card? | Verdict: Partial. Charge primitives exist (external-api-service stripe.service.createPaymentIntent + saved PaymentMethod brand/last4 + PaymentTransaction.source=manual_retry) but | Medium
12 | Requirement detail | 13.2 | Payment plan / scheduled installment data model exists | The schema models installments FLAT (no PaymentPlan parent grouping multiple installments). The brief says 'an order may have one or more payment plans' AND each plan has 'scheduled installments' - is a 'payment plan' here equivalent to a single installment row, or a grouping of installments (e.g. one plan = the whole split schedule)? This changes whether plan-level vs installment-level status rollup is one tier or two. | Verdict: Deliverable. | Low
13 | Requirement detail | 13.2 | Per-plan status: Overdue | Is Overdue required to be a PERSISTED status (needs admin-backend-api enum migration + a background-worker overdue-marking cron), or is computing it at read time from due_date < now() AND not-succeeded sufficient for the listing/details display? | Verdict: Partial. PaymentTransactionStatus enum (admin-backend-api/prisma/schema.prisma:488) has NO 'overdue' value (scheduled¦processing¦succeeded¦failed¦canceled¦refunded). 'Ov | Medium
14 | Requirement detail | 13.2 | Order-level status: Unpaid | Brief column header lists Payment Status as 'Paid/Unpaid' (13.2 line 13) but the derivation section lists three states (Paid in Full/Partially Paid/Unpaid). Confirm the listing column shows the full tri-state label (Paid in Full/Partially Paid/Unpaid), not a binary Paid/Unpaid. | Verdict: Deliverable. | Low
15 | Requirement detail | 13.2 | Order Listing Actions | Should the order-history Invoice PDF be generated on-demand (generalize the existing PPL pdfkit renderer) or pre-rendered and stored (needs a new Invoice.file_url column via admin-backend-api migration + S3 storage)? | Verdict: Partial. No order-invoice PDF generator and no stored invoice file. Invoice model has NO file_url/PDF field (exhibitor-backend-api prisma/schema.prisma:1953; only file_u | Medium
16 | Requirement detail | 13.2 | Order Listing Actions | Per the external Credit Card Payment Workflow / Payment Schedule Visibility stories: which payment method is authoritative for early-pay — the salesperson-set stripe_payment_method_id on the scheduled PaymentTransaction, the company default PaymentMethod, or a card entered at pay time? And does 'pay early' settle ALL remaining installments (full payoff) or allow paying a single chosen future installment? | Verdict: Partial. No endpoint to pay an EXISTING order's outstanding/future scheduled installment. exhibitor-backend-api payments controller exposes ONLY POST /payments/checkout | Medium
17 | Requirement detail | 13.3 | Order Details Header | For a multi-show order, what should the single Order-Details header show as Event Name / City / Event Dates — the first show, a combined list, or should the header be per-show-group? | Verdict: Partial. No direct Order->Shows relation. Event Name (Shows.title) is only reachable for product/booth orders via OrderItem.show_product_id -> ShowProduct.show_id -> Sho | Medium
18 | Requirement detail | 13.3 | Order Details Header | How should Event Dates render when Shows.date is null / date_to_be_added is true (TBA) for an order's show? | Verdict: Partial. Event Dates derived from Shows.date / start_time / end_time / timezone via the OrderItem->ShowProduct->Shows path. Fields are all nullable (date DateTime?, star | Medium
19 | Requirement detail | 13.3 | Order Details Header | Confirm the order-level status label set required for the header (Paid in Full / Partially Paid / Unpaid) and whether 'Overdue' must surface as a distinct badge or simply collapse into 'not fully paid'. | Verdict: Partial. OrderStatus enum has pending¦partially_paid¦completed¦failed¦refunded¦canceled but NO literal 'unpaid'/'overdue' value. The required Paid-in-Full / Partially Pa | Medium
20 | Requirement detail | 13.3 | Booth/Workshop Pavilion section | Where does an assigned Booth Number come from (is it assigned post-purchase by show ops, or never captured today)? It is not stored or computed anywhere in the current data model — is creating it in scope, or does it depend on an unprovided external story? | Verdict: NotDeliverable. No booth_number / boothNumber field exists anywhere in schema or code (grep over both prisma schemas and src returned no matches). OrderItem has NO metadata col | High
21 | Requirement detail | 13.3 | Booth/Workshop Pavilion section | Should Booth Size be snapshotted onto the order line at purchase, or is reading it live from the current Product acceptable (risk of drift if the product is later edited)? | Verdict: Partial. No booth-size field on OrderItem; size is derivable from Product.length/width (Decimal) via OrderItem.product_id -> Product, since the booth is modeled as a Pro | Medium
22 | Requirement detail | 13.3 | Booth/Workshop Pavilion section | Where is Booth Type (Standard / Premium / Corner) sourced? It does not map to any existing ProductType code in the schema — is it a new attribute, and does it depend on the Booth Upgrade external story? | Verdict: Partial. No first-class Booth Type on the order line. ProductType hierarchy (ProductType.name/code, parent_type_id) classifies products as booth/sponsor/etc., but there | Medium
23 | Requirement detail | 13.3 | Booth/Workshop Pavilion section | Provide the Booth Upgrade story's data contract: how is an upgrade recorded against an order line (parent/child OrderItem? a dedicated upgrade record? from/to size, upgrade type, price delta), so we can determine what 'Upgrade details' must render? | Verdict: NeedsClarification. This requirement explicitly references the external Booth Upgrade story, which is NOT provided. Structurally, an upgrade could be represented via OrderItem.pare | High
24 | Requirement detail | 13.3 | OrderItem typing distinguishes booth vs add-on vs sponsorship | Confirm whether display name should come from OrderItem.description (frozen snapshot at purchase) or be re-resolved live from Product/ShowProduct; snapshot is the modeled source and is recommended for historical accuracy. | Verdict: Deliverable. Minor: cart_item_type is nullable (CartItemType?). For cart-originated booth/add-on/sponsorship product orders (the scope of 13.3) it is populated from the cart | Low
25 | Requirement detail | 13.3 | Financial Summary | Does the Financial Summary need only the applied coupon code + discount amount (snapshot is enough), or must it resolve the live CouponCode definition (type/value) — which would require uncommenting/adding a coupon-to-order relation? | Verdict: Deliverable. Coupon-to-order link is a snapshot only (Order.coupon_code + Order.coupon_amount); the CouponOrders join table is commented out (schema ~1752-1768). Sufficient | Low
26 | Requirement detail | 13.3 | Financial Summary | Must reconciliation be performed/owned by a dedicated centralized billing service (not present today), or is reconciling the frozen Order snapshots within the exhibitor-backend-api order-history read endpoint sufficient? | Verdict: Deliverable. All component fields exist and are mutually reconcilable in read logic (subtotal + setup_fees + cleaning_fees + tax - coupon_amount - giftcert deltas = total; p | Low
27 | Requirement detail | 13.3 | Payment Details | Should the displayed card be the one snapshotted on the PaymentTransaction (per-installment) or the company's current default PaymentMethod? They can differ if the default card changed after checkout. | Verdict: Deliverable. | Low
28 | Requirement detail | 13.3 | Payment Details | Which id is the customer-facing 'transaction reference' to display — the Stripe charge id, the payment intent id, or the internal Invoice.invoice_number? Confirm with BA the expected human-readable reference format. | Verdict: Deliverable. | Low
29 | Requirement detail | 13.3 | Payment Details | Is one invoice expected per order, or one per installment/payment (PaymentTransaction.invoice_id implies per-installment invoices)? And should the PDF be generated on-demand or pre-generated and stored? | Verdict: Partial. Invoice/InvoiceLineItem data rows exist (with InvoiceItemType covering booth/addon/sponsorship/fees and original_price vs unit_price for savings), but Invoice h | Medium
30 | Requirement detail | 13.3 | Payment Details | Does the salesperson define arbitrary custom installment dates/amounts at order-build time (origination work needed in admin cart + external-api), or is the schedule auto-derived from payment_mode=split + installments_count (display-only)? This determines whether new write-path work is required. | Verdict: Partial. The READ side is deliverable: PaymentTransaction is one-row-per-installment with installment_number, due_date, amount, status, stripe_payment_method_id, paid_at | Medium
31 | Requirement detail | 13.3 | Agreement | For non-PPL (booth/product) order types, is the same signed-DOCX renderer expected, and what should manually CS-signed orders (signature_data = 'MANUAL_SIGNED_AGREEMENT', no real signature image) show on the downloaded document? | Verdict: Deliverable. | Low
32 | Requirement detail | 13.3 | Onsite contact info | For a multi-show order, should the onsite contact be shown per-show (grouped) under each show section, or is there a single primary onsite contact per order? And what should be displayed when no OnsiteBoothContact row exists yet for a booked show? | Verdict: Partial. OnsiteBoothContact model exists (contact_name/contact_email/contact_phone) but is keyed @@unique([company_id, show_id]) — it is NOT linked to order_id. For an o | Medium