## Overview
Story ID | 24.8
Title | Payment Plan Management
Epic | Order Management
Build Status | Scope locked 2026-07-03 (Step-1 gate complete — 13 rows + 4 decisions). 13 to implement here (24.8-l = display half; automation in register). Release model: ship-together.
To implement here | 13
Summary | Payment-plan CRUD over PaymentTransactions: C13 mapper + 4 additive routes; D2 payment_type (CartPaymentMethod reuse, backfill credit_card NOT NULL) + payment_memo; D3 nullable Stripe cols + charge-cron guard; D4 admin_manual source; Mark-Paid PATCH owned here (24.15 stop-condition); Refund delegated to 24.9; chargebacks display-only (QB -> epic 65, trio ND + BA flag). 12 Deliverable + 1 split.
Total requirements | 13
Deliverable | 12
Partial | 1
Blocked | 0
Not Deliverable | 0
Out of Scope | 0
Implementation | Delivered — merged to dev 2026-07-05 (Phase 4 of the OM Phase-1 one-release).
Impl Branch | feature/SBE-1125
Impl Commits | admin 81f6fd9 (feat — manual installments, milestone mapper, plan routes); external 407a20d + exhibitor 6f84347 (payment_type on card PT writers); worker d4206c3 (charge/retry cron guard = credit_card); pulse 3127e17 (schema mirror)
PR | admin #533; external #95; exhibitor #298; worker #27; pulse #16 -> dev

## Requirements
Req ID | Requirement | Verdict | Build Focus | Delivered By | Reason (exists vs to-build / gap) | Code Evidence | Dependency | Build Consolidation (reuse / delivered-by) | Story Wording (verbatim, from Confluence) | Confluence | Impl Status (2026-07-05)
24.8-a | Plan View: list all scheduled and completed payments with Invoice #, Payment Type, Date, Status, Payment Memo, Amount Due, Total, and Amount Paid. | Deliverable | Implement here | — | CONFIRMED 2026-07-03 — upgraded Partial -> Deliverable: the two missing columns are D2's story-owned migration (payment_type reusing CartPaymentMethod, backfill credit_card NOT NULL no default; payment_memo nullable Text, service-mandatory for non-CC; doc-comments on enum declaration AND column: credit_card = Stripe card charge, sole non-manual value). Row shape = C13 mapper built here, reused by 24.7/24.6-p,q/24.15. Order.payment_memo (24.14) is order-level — deliberately distinct from per-installment memo (BA note). | admin schema PT :2073-2110, invoice_id :2093, Invoice.invoice_number :1981, Order.total :1552, paid_amount :1578 (gross per 24.9 D3), Order.payment_memo :1576; deriveBalanceDue orders.helpers.ts:33 |  | [C13 cross-reference] OWNER — build here (A single PaymentTransaction -> installment-row mapper (Invo…); reused by other stories in this cluster. | Admin shall view all scheduled and completed payments with Invoice #, Payment Type, Date, Status, Payment Memo, Amount Due, Total, and Amount Paid. | Open §Order Management → Story 24.8 | Gate 2026-07-03: upgraded Partial -> Deliverable; D2 recorded. -> ✅ DELIVERED 2026-07-05 (SBE-1132, admin 81f6fd9, PR#533) merged to dev; audit-verified.
24.8-b | Edit payment date for future (unpaid) installments. | Deliverable | Implement here | — | CONFIRMED 2026-07-03. due_date NOT NULL + [status,due_date] index; charge cron picks scheduled+due, so a date edit composes cleanly. AGREED GUARD: scheduled-only. Date validation via 24.8-j/k. | admin schema due_date :2086, index :2103; worker payment-charge.service.ts:62-67 |  |  | Edit payment date for future installments. | Open §Order Management → Story 24.8 | Gate 2026-07-03: Deliverable; scheduled-only guard. -> ✅ DELIVERED 2026-07-05 (SBE-1132, admin 81f6fd9, PR#533) merged to dev; audit-verified.
24.8-c | Mark payments as Paid or Unpaid. | Deliverable | Implement here | — | CONFIRMED 2026-07-03. Mark-as-Paid/Unpaid PATCH OWNED HERE (reassigned from 24.7; 24.7 consumes). Paid => succeeded + paid_at; Unpaid => scheduled + cleared. AGREED: manual-method installments only — service rejects hand-marking credit_card rows (webhook stays card source of truth; this IS 24.7-b's gate, built here). Mark-Paid bumps paid_amount/paid_in_full_at mirroring webhook; Unpaid reverses (the one legitimate gross decrement — bookkeeping correction, not refund). This PATCH is 24.15's stop-condition. | admin schema enum :491-500; ext webhook.service.ts:2111-2125 (write pattern) |  |  | Mark payments as Paid, Unpaid, or Refund. | Open §Order Management → Story 24.8 | Gate 2026-07-03: Deliverable; manual-only gate + bookkeeping semantics. -> ✅ DELIVERED 2026-07-05 (SBE-1132, admin 81f6fd9, PR#533) merged to dev; audit-verified.
24.8-d | Mark payments as Refund (the only allowed action after payment). | Deliverable | Implement here | — | CONFIRMED 2026-07-03 — upgraded Partial -> Deliverable (sequenced on 24.9). The Refund action IS 24.9's per-installment primitive (POST /orders/:id/refunds with payment_transaction_id: cap, mandatory reason, Manual/Stripe branch, ledger row, refunded/refund_failed flip). 24.8 OWNS NO REFUND CODE — plan view only exposes the action. Dependency owner corrected from generic 'Payments/Checkout' to 24.9. | ext webhook.service.ts:3038 (amount-aware change owned by 24.9 D2); grep refunds.create = zero pre-24.9; 24.9 doc D1 | 24.9 (SBE-1133) refunds endpoint + ledger — same release, builds first |  | Mark payments as Paid, Unpaid, or Refund. / the only allowed action after payment is Refund. | Open §Order Management → Story 24.8 | Gate 2026-07-03: upgraded Partial -> Deliverable (delegated to 24.9). -> ✅ DELIVERED 2026-07-05 (SBE-1132, admin 81f6fd9, PR#533) merged to dev; audit-verified.
24.8-e | Delete individual installments. | Deliverable | Implement here | — | CONFIRMED 2026-07-03. PT is the per-installment unit; DELETE unblocked. AGREED GUARD: scheduled-only (succeeded = lock; processing = mid-charge; canceled/refunded = audit trail). Allocation return free — balance derived, deletion IS the return. Audit in-tx with snapshot. | admin schema PT :2073-2110 |  |  | Delete individual installments. | Open §Order Management → Story 24.8 | Gate 2026-07-03: Deliverable; scheduled-only guard. -> ✅ DELIVERED 2026-07-05 (SBE-1132, admin 81f6fd9, PR#533) merged to dev; audit-verified.
24.8-f | Add new payment installments manually. | Deliverable | Implement here | — | CONFIRMED 2026-07-03 — upgraded Partial -> Deliverable: gaps became D2/D3/D4 story-owned migration work. POST creates scheduled PT: amount, due_date, payment_type (D2), payment_memo (mandatory non-CC), null Stripe ids for manual types (D3 — doc-comments: null = manual installment, no Stripe identity), app-UUID idempotency_key, source admin_manual (D4). Guards: unallocated cap (i), 60/30 two-phase (j/k), audit. CARD-SIBLING CONSTRAINT: manual credit_card installment requires existing Stripe identity on the order (ids copied from sibling card rows) else rejected. COMPANIONS: 7 card-writer updates (exhibitor x4, external x2, admin x1; corrected 2026-07-06 from gate estimate of 5, exhaustive PT-creation sweep) + worker charge/retry cron guard payment_type=credit_card. | admin schema :2084/:2085 (D3 nullable), :2094 (stays NOT NULL); creation sites verified via exhaustive sweep 2026-07-06 -- 7 pre-existing card writers, not the gate's 5: exhibitor cart:1474, payments:267, ppl/checkout:253, ppl/ppl.service:2537; external webhook:752 (create) + :1152 (upsert); admin ppl-service-provider-detail-view:970 -- all now set credit_card explicitly. The 8th PT writer, admin order-payment-plan:270, is 24.8's own manual-add (payment_type from DTO, source admin_manual). |  |  | Add new payment installments manually. | Open §Order Management → Story 24.8 | Gate 2026-07-03: upgraded Partial -> Deliverable; D2/D3/D4 recorded. -> ✅ DELIVERED 2026-07-05 (SBE-1132, admin 81f6fd9, PR#533) merged to dev; audit-verified.
24.8-g | Post-Payment Lock: once paid, the plan is no longer editable; only Refund is allowed after payment. | Deliverable | Implement here | — | CONFIRMED 2026-07-03. PLAN-LEVEL LOCK = Order.paid_in_full_at set; before that, settled installments individually immutable while scheduled rows stay editable (restructuring intent). Lock = invariant the per-row guards jointly enforce; residual = explicit consistent locked-error shape + tests. Refund stays available via 24.9. | admin schema paid_in_full_at :1579, PT.paid_at :2088; ext webhook.service.ts:2111-2125 |  |  | Once a payment plan has been paid, it shall no longer be editable by team members; the only allowed action after payment is Refund. | Open §Order Management → Story 24.8 | Gate 2026-07-03: Deliverable; plan-level lock semantics. -> ✅ DELIVERED 2026-07-05 (SBE-1132, admin 81f6fd9, PR#533) merged to dev; audit-verified.
24.8-h | Deleting an unpaid installment/plan returns its amount to the Unallocated Balance; users can restructure schedules (delete/add/split balances). | Deliverable | Implement here | — | CONFIRMED 2026-07-03. DERIVED, NEVER STORED (no unallocated column anywhere): Order.total − Σ PT.amount, Decimal floored-0 fixed-2. 'Move back' automatic — deletion shrinks the Σ. Surfaced in GET payment-plan. | admin schema Order.total :1552, PT.amount :2079; deriveBalanceDue orders.helpers.ts:33 |  | [C13 cross-reference] OWNER — build here (A single PaymentTransaction -> installment-row mapper (Invo…); reused by other stories in this cluster. | Deleting an unpaid payment plan shall move its amount back into the Unallocated Balance. Users shall be able to delete milestones, add new milestones, split balances differently, and restructure payment schedules as needed. | Open §Order Management → Story 24.8 | Gate 2026-07-03: Deliverable; derived-not-stored. -> ✅ DELIVERED 2026-07-05 (SBE-1132, admin 81f6fd9, PR#533) merged to dev; audit-verified.
24.8-i | Add Validation: new installments may be added only when an Unallocated Balance remains; block adding when the order total is fully allocated. | Deliverable | Implement here | — | CONFIRMED 2026-07-03. Guard on the POST: reject when unallocated <= 0; cap amount <= unallocated; computed INSIDE the same transaction as the insert (no stale-balance race). 'Unless deleted/adjusted' needs no code. | same as 24.8-h |  |  | New payment plans shall be added only when an Unallocated Balance remains. If the entire order total is already fully allocated, users shall not be able to add additional payment plans unless an existing plan is deleted or amounts are adjusted to create unallocated balance. | Open §Order Management → Story 24.8 | Gate 2026-07-03: Deliverable; in-tx guard. -> ✅ DELIVERED 2026-07-05 (SBE-1132, admin 81f6fd9, PR#533) merged to dev; audit-verified.
24.8-j | Date Validation: enforce the existing 60-day / 30-day rules tied to the first show date. | Deliverable | Implement here | — | CONFIRMED 2026-07-03. Shipped util current: 60/30 windows :9-10, assertPaymentPlanTotal :18, assertNoPaymentDateAfterShow :40, computePaymentDateWarnings :56. Net-new = composition: first show date via OrderItem.show_product_id :1955 -> ShowProduct :2659 -> Shows :2388. AGREED: null show date => skip window checks + 'no show date on file' warning. Plan-time: share the util (import/hoist), don't duplicate. | admin cart-payment-plan.util.ts (refs above); schema :1955/:2659/:2388 (Shows.date nullable) |  |  | Payment date validations shall follow the existing 60-day / 30-day rules tied to the first show date. | Open §Order Management → Story 24.8 | Gate 2026-07-03: Deliverable; null-show-date handling agreed. -> ✅ DELIVERED 2026-07-05 (SBE-1132, admin 81f6fd9, PR#533) merged to dev; audit-verified.
24.8-k | Admin or client-services users may bypass date validations; the system shows a warning rather than blocking. | Deliverable | Implement here | — | CONFIRMED 2026-07-03. Port the live two-phase pattern: no confirm => {plan, warnings[]}; ?confirm=true => execute (cart-payment-plan.service.ts:54-108; cart.controller.ts:1246-1283). 'Authorized users' = the route's own orders.payment-plan.* permission key (mirrors cart.manage-payment-plan, cart.constants.ts:54, role.seeder.ts:238) — no second bypass permission. | as cited |  |  | Admin or client-services users may bypass these validations; in such cases the system shall display a warning rather than blocking the action. | Open §Order Management → Story 24.8 | Gate 2026-07-03: Deliverable; two-phase port. -> ✅ DELIVERED 2026-07-05 (SBE-1132, admin 81f6fd9, PR#533) merged to dev; audit-verified.
24.8-l | Each installment carries a milestone status whose corresponding actions in QuickBooks follow the Payment Plan Milestone Status sheet. | Split: Deliverable (display) / automation in register | Implement here | — | DECIDED 2026-07-03 (D1): DISPLAY-ONLY. Display half ships — C13 mapper carries milestone status mapped from statuses this release produces (6 enum values + 24.9's refund_failed). Automation split by cause: QuickBooks actions = Out of Scope citing epic 65 'Quickbooks Integration/Invoice Creation Process' (Admin Panel Page 2, 65.1-65.5, NOT in Jira; consistent with 24.9-i/24.6); chargeback trio (Pending/Won/Lost) = Not Deliverable — no charge.dispute.* handling, no enum values, NO OWNING STORY anywhere; BA FLAG: the Milestone Status sheet references statuses no story produces. Exhibitor SETTLED/NON_PAYABLE watch stays scoped to refund_failed (actioned in 24.9). | admin schema quickbooks_* :1569-1571 dormant, QuickBooksSyncStatus :474 writer-less; grep intuit/qbo = none; ext webhook.controller.ts:154-188 (no dispute cases); enum :491-500; Jira 'QuickBooks' = zero issues | QB actions: epic 65, Admin Panel Page 2 (un-ticketed). Chargebacks: no owning story — BA flag. |  | Each installment shall carry a milestone status whose corresponding actions in QuickBooks follow the Payment Plan Milestone Status sheet. | Open §Order Management → Story 24.8 | Gate 2026-07-03: split verdict (D1 display-only). -> ◑ DISPLAY half DELIVERED (MILESTONE_STATUS_LABELS, correct at dev tip; audit 2026-07-05 partial-as-planned). QuickBooks force-sync + chargeback trio out of scope — no owning story (BA flag, register).
24.8-m | Backend Enforcement: plan totals, allocation, and date rules shall be enforced on the backend. | Deliverable | Implement here | — | CONFIRMED 2026-07-03. Composite of confirmed guards: totals (assertPaymentPlanTotal), allocation (in-tx derived), date rules (two-phase port), eligibility gates (b/c/e/f), plan lock (g) — all service/tx-side. C8/C9 residuals: seed orders.payment-plan.* keys + one audit record per mutating tx. | cart-payment-plan.util.ts:18; schema :1552/:1578/:2079; admin-audit.service.ts:50 |  | [C8 build-once-reuse] Mostly delivered by building 24.1 (The existing JWT + roles guard + @Permissions(...) decorato…). Residual: plan totals/allocation/date-rule enforcement is domain logic beyond the guard. | Plan totals, allocation, and date rules shall be enforced on the backend. | Open §Order Management → Story 24.8 | Gate 2026-07-03: Deliverable. -> ✅ DELIVERED 2026-07-05 (SBE-1132, admin 81f6fd9, PR#533) merged to dev; audit-verified.

## Endpoints
Method | Path | Purpose | Serves Req(s) | Shared With
GET | /api/v1/orders/:id/payment-plan | Installment rows via the C13 mapper (8 columns + milestone status) + derived Unallocated Balance + 60/30 warnings. | 24.8-a, h, i, l(display) | Mapper reused by 24.7 GET payments, 24.6-p/q, 24.15 cron
POST | /api/v1/orders/:id/payment-plan/installments | Add installment: D2/D3/D4 fields, unallocated + 60/30 two-phase (?confirm=), card-sibling constraint, audit in-tx. | 24.8-f, 24.8-i, 24.8-j, 24.8-k, 24.8-m
PATCH | /api/v1/orders/:id/payment-plan/installments/:installmentId | Edit future date (scheduled-only) or Mark Paid/Unpaid (manual-method-only; paid_amount bookkeeping mirror/reverse); post-payment lock; two-phase warnings; audit in-tx. Refund NOT here — delegated to 24.9's refunds endpoint. | 24.8-b, c, g, j, k, m | Mark-Paid = 24.15's stop-condition; consumed by 24.7
DELETE | /api/v1/orders/:id/payment-plan/installments/:installmentId | Delete a scheduled installment (derived balance auto-returns); post-payment lock; audit in-tx with snapshot. | 24.8-e, 24.8-g, 24.8-h
— | Migration (admin, mirrors x4) | payment_type (CartPaymentMethod, backfill credit_card, NOT NULL, no default) + payment_memo (nullable Text) + nullable stripe_payment_method_id/stripe_customer_id + admin_manual source + doc-comments (enum declaration, payment_type, both nullable cols). | 24.8-a, f (D2/D3/D4) | 24.7 classification, 24.9-f unblock, 24.15 selection
— | Writer updates (7 card sites) + cron guard | Set payment_type: credit_card explicitly at the 7 pre-existing card PT-creation sites -- exhibitor cart.service.ts:1474, payments.service.ts:267, ppl/checkout.service.ts:253, ppl/ppl.service.ts:2537; external webhook.service.ts:752 (create) + :1152 (upsert); admin ppl-service-provider-detail-view.service.ts:970. (8th PT writer admin order-payment-plan.service.ts:270 is 24.8's own manual-add: payment_type from DTO, source admin_manual.) Worker charge+retry queries add payment_type=credit_card guard. [Count corrected 2026-07-06 from gate's 5.] | 24.8-f companions | exhibitor/external/worker repos — in-release

## Open Questions
Req | Item | Verdict | Open Question / What is needed | Dependency (blocking story + Jira) | Assignee | Sprint / Jira status | Decision / Current direction
24.8-l | QuickBooks per-status actions | Out of Scope | QB integration to execute the sheet's per-status actions (Received Payment, credit memo, journal entries) | Epic 65, Admin Panel Page 2 (un-ticketed; no Jira issues) | — (BA) | Not commissioned | Display half ships in 24.8; captured statuses + ledger are what the future sync consumes.
24.8-l | Chargeback trio (Pending/Won/Lost) | Not Deliverable | charge.dispute.* webhook handling + 3 enum values + an owning story — none exist anywhere | none — no owning story | — (BA) | — | BA FLAG: Milestone Status sheet references statuses no story produces (same pattern as epic 65 missing refund story).

## Cross-Epic Dependencies
Dependency | Needed For | Likely Owner
Refund execution (per-installment primitive + ledger + wrapper) | 24.8-d | 24.9 (SBE-1133) — same release, builds first
QuickBooks integration | 24.8-l automation half | Epic 65 'Quickbooks Integration/Invoice Creation Process', Admin Panel Page 2 (un-ticketed; lacks dispute story too — BA flagged)
Downstream consumers (NOT dependencies): 24.7 (mapper + Mark-Paid gate + classification), 24.6-p/q (mapper), 24.15 (stop-condition + scan + cron guard), 24.9-f manual half (unblocked by D2/D3), 13.3-t/SBE-1154 (taxonomy aligned) | — | —

## Implementation Status
Section | Detail
Status | Delivered — merged to dev 2026-07-05 (Phase 4 of the OM Phase-1 one-release).
Branch | feature/SBE-1125 (all 5 repos; per-story SBE-ticket commit scopes; OM Phase-1 one-release model)
SBE ticket | SBE-1132 (In Progress, Prantik Saha)
Commits | admin 81f6fd9 (feat — manual installments, milestone mapper, plan routes); external 407a20d + exhibitor 6f84347 (payment_type on card PT writers); worker d4206c3 (charge/retry cron guard = credit_card); pulse 3127e17 (schema mirror)
PR | admin #533; external #95; exhibitor #298; worker #27; pulse #16 -> dev
Swagger tag | Admin - Order Management (/api/docs/admin)
Build gates | Green — admin 8-step pre-push gate (prisma migrate deploy + full seed:run, typecheck, lint:check, test:cov, build) + Bitbucket pipeline SUCCESSFUL (gitleaks + lint/test + SonarQube quality gate) on every phase.
Live smoke | Plan CRUD + locks, Mark-Paid/Unpaid (manual-only gate), scheduled-only edit/delete, milestone label map, payment_type backfill NOT NULL; all green.
Confirmed build scope | 24.8-a..k + 24.8-m delivered (12 reqs). payment_type/payment_memo migration; plan-level CRUD; installment PATCH; MILESTONE_STATUS_LABELS mapper.
Remaining | 24.8-l split: milestone-label DISPLAY delivered; QuickBooks + chargeback automation out of scope (register / BA flag).
Not ready — see Open Questions | 24.8-l automation half (QB -> epic 65; chargeback trio -> no owning story, BA flag)
External dependencies — see Cross-Epic Dependencies | 24.9 refund stack (same release); QuickBooks epic 65 (un-ticketed)
Out of API scope | Payment Plan screen FE wiring
Post-merge fix (P1) | Payment-plan GET balance_due aligned to NET-of-refund (deriveNetPaid) in Post-merge alignment (P1/P3/P4) — fix(SBE-1131) 7fd7a9b, admin PR#539 -> dev 55c6e61 (2026-07-05).