## Overview
Story ID | 24.7
Title | Manual Payment Methods
Epic | Order Management
Build Status | Scope locked 2026-07-03 (Step-1 gate complete). 2 to implement here, 3 covered elsewhere (by 24.8), 0 out of scope. Release model: ship-together, builds after 24.8.
To implement here | 2
Summary | Story converged to least-work shape: ONE read route (GET :id/payments via 24.8's mapper, incl. per-installment payment_memo + derived Paid/Unpaid label); write side (mark Paid/Unpaid + logging + enforcement) delivered by 24.8's installment PATCH; planned PATCH :id/payment-status DROPPED (D3); classification = 24.8's payment_type; both open questions resolved (derive-not-store; restrict-to-manual per-installment).
Covered Elsewhere | 3 (24.7-b/c/d -> 24.8)
Total requirements | 5
Deliverable | 2
Partial | 0
Blocked | 0
Not Deliverable | 0
Out of Scope | 0
Implementation | Not started — scope locked 2026-07-03 (gate complete)
Impl Branch | —
Impl Commits | —
PR | —

## Requirements
Req ID | Requirement | Verdict | Build Focus | Delivered By | Reason (exists vs to-build / gap) | Code Evidence | Dependency | Build Consolidation (reuse / delivered-by) | Story Wording (verbatim, from Confluence) | Confluence | Impl Status (2026-07-03)
24.7-a | Treat Check, Bank Wire, ACH, and PayPal as manual payment methods (recognize/identify a payment/order as using a manual method). | Deliverable | Implement here |  | CONFIRMED 2026-07-03 — upgraded Partial -> Deliverable (sequenced on 24.8's migration). Classification source of record = payment_type on payment_transactions (24.8 D2: CartPaymentMethod reuse — exactly this taxonomy, bank_wire_ach = Bank Wire + ACH; doc-comment: credit_card = Stripe card charge, sole non-manual). 'Treated as manual' = locked behaviors elsewhere: excluded from charge cron (24.8 D3 guard), hand-markable (24.8-c gate), Manual-refund-only without charge id (24.9-f), classified via the mapper. Historic rows credit_card via backfill (all 5 creation sites verified card flows); subscription/ppl_addon always-Stripe; no cart-plan fallback needed. | 24.8 doc D2/D3 locked 2026-07-03; admin schema CartPaymentMethod :2801-2808; cart-payment-plan.service.ts:95 (intent writer, display-only :2909-2910); Order has no payment_method :1541-1609 (correct — per-installment) | 24.8 (SBE-1132) payment_type migration — same release, builds first | [C13 cross-reference] Mostly delivered by building 24.8 (A single PaymentTransaction -> installment-row mapper (Invo…). Residual: the Payments screen reuses the installment row projection but focuses on status/method; catalog deliberately keeps GET .../payments a DISTINCT endpoint from GET .../payment-plan. No endpoint merge — only the row mapper is shared. | Check, Bank Wire, ACH, and PayPal shall be treated as manual payment methods. | Open §Order Management → Story 24.7 | Gate 2026-07-03: upgraded Partial -> Deliverable (sequenced on 24.8).
24.7-b | Admin can mark a manual-method payment as Paid or Unpaid (manual status update from backend/admin panel). | Covered elsewhere | Covered elsewhere | 24.8 (SBE-1132) — installment PATCH | CONFIRMED 2026-07-03. Delivered entirely by 24.8's PATCH :id/payment-plan/installments/:installmentId, locked with exactly this row's semantics: manual-method-only eligibility, Paid => succeeded + paid_at + webhook-mirroring money writes, Unpaid => scheduled + bookkeeping reversal, label derived. OLD OQ-1 RESOLVED derive-not-store (neither OrderStatus overload nor new field). 24.7 builds no write path (D3: planned order-level PATCH dropped). | 24.8 doc 24.8-c locked; ext webhook.service.ts:2114-2125/:2281-2287 (mirrored writes); exh orders.helpers.ts:53 | — delivered by 24.8, same release |  | For manual payment methods, the payment status shall be updated manually by admin users from the backend or admin panel. Admin users shall be able to mark payments as Paid or Unpaid. | Open §Order Management → Story 24.7 | Gate 2026-07-03: reclassified Deliverable -> Covered elsewhere (24.8).
24.7-c | Status changes shall be logged. | Covered elsewhere | Covered elsewhere | 24.8 (SBE-1132) — PATCH audit leg | CONFIRMED 2026-07-03. Logging = AdminAuditService.record() inside 24.8's PATCH tx (old->new status, admin id, non-blank note); shipped in-module precedent from 24.14 (order-notes.service.ts:94). 'Refer 24.14' pointer satisfied by the shipped audit-log read endpoint. 24.7's own route is a read — logs nothing. | admin admin-audit.service.ts:30/:50; order-notes.service.ts:94; schema :2210 | — delivered by 24.8, same release | [C9 build-once-reuse] Mostly delivered by building 24.14 (AdminAuditService.record()/recordMany() with entity_type='o…). Residual: one record() call inside the payment-status transaction. | Status changes shall be logged. | Open §Order Management → Story 24.7 | Gate 2026-07-03: reclassified -> Covered elsewhere (24.8).
24.7-d | Manual status updates shall be enforced on the backend (server-side validation/authorization, and gated so only manual-method payments may be manually toggled). | Covered elsewhere | Covered elsewhere | 24.8 (SBE-1132) — gate + route enforcement | CONFIRMED 2026-07-03 — upgraded Partial -> Covered elsewhere. Both halves locked into 24.8: method-eligibility gate (manual-only, per-installment via payment_type — handles mixed plans; OLD OQ-2 RESOLVED restrict-to-manual, no admin override on card rows) and permission/DTO enforcement on the PATCH (orders.payment-plan.* key). 24.7's residual = its read route's permission (rides 24.7-e). | 24.8 doc 24.8-c/D3 locked; orders.controller.ts:51/:95/:132 (@Permissions in-module precedent) | — delivered by 24.8, same release | [C8 build-once-reuse] Mostly delivered by building 24.1 (The existing JWT + roles guard + @Permissions(...) decorato…). Residual: the method-eligibility gate (manual-method-only) is extra DOMAIN logic on top of the shared guard (24.7-d is Partial for that reason). | Manual status updates shall be enforced on the backend. | Open §Order Management → Story 24.7 | Gate 2026-07-03: upgraded Partial -> Covered elsewhere (24.8).
24.7-e | Surface the order's Payments section (Admin Panel -> Order Management -> order -> Payments) showing payment method and current paid/unpaid status to back the status-update UI. | Deliverable | Implement here |  | CONFIRMED 2026-07-03 — THE WHOLE OF 24.7'S BUILD. GET /api/v1/orders/:id/payments: additive route on the shipped module (no payments route anywhere in admin src); installment rows via 24.8's C13 mapper (status, amounts, dates, Invoice #, payment_type, per-installment payment_memo per D3 rider) + order money summary (paid_amount, paid_in_full_at, derived Paid/Unpaid label — deriveOrderPaymentStatus port). DISTINCT from GET :id/payment-plan (same mapper, different lens). Residuals: orders.payments.read seed + Swagger. The old ppl-order hardcoded payment_type 'Credit Card' (:378) is exactly what payment_type retires. | orders.controller.ts routes :50/:94/:131 only; schema paid_amount :1578, paid_in_full_at :1579, PT :2073-2108; exh orders.helpers.ts:53/:74; ppl-order.service.ts:345/:359/:378 | 24.8 (SBE-1132) C13 mapper — same release, builds first | [C13 cross-reference] Mostly delivered by building 24.8 (A single PaymentTransaction -> installment-row mapper (Invo…). Residual: the Payments screen reuses the installment row projection but focuses on status/method; catalog deliberately keeps GET .../payments a DISTINCT endpoint from GET .../payment-plan. No endpoint merge — only the row mapper is shared. | Navigation: Admin Panel → Order Management → (order) Payments | Open §Order Management → Story 24.7 | Gate 2026-07-03: Deliverable (sequenced on 24.8 mapper).

## Endpoints
Method | Path | Purpose | Serves Req(s) | Shared With
GET | /api/v1/orders/:id/payments | The Payments view: installment rows via 24.8's C13 mapper (incl. payment_type + per-installment payment_memo) + order money summary + derived Paid/Unpaid label. 24.7's ONLY route. | 24.7-a, 24.7-e | Mapper owned by 24.8; distinct from GET :id/payment-plan by design
(dropped) | PATCH /api/v1/orders/:id/payment-status — DROPPED 2026-07-03 (D3) | Mark-as-Paid/Unpaid lives solely in 24.8's PATCH :id/payment-plan/installments/:installmentId — one writer, one audit trail, one permission surface. | 24.7-b/c/d (delivered there) | 24.8 owns

## Open Questions
Req | Item | Verdict | Open Question / What is needed | Dependency (blocking story + Jira) | Assignee | Sprint / Jira status | Decision / Current direction
— | Register empty — gate locked 2026-07-03 |  | OQ-1 (Paid/Unpaid representation) RESOLVED: derive-not-store — PT.status flip + webhook-mirroring money writes + derived label (24.8-c). OQ-2 (webhook coexistence) RESOLVED: restrict-to-manual per-installment via payment_type; card rows webhook-owned, no override; mixed plans handled per-installment. |  |  |  | 2 Deliverable + 3 covered by 24.8; PATCH dropped (D3).

## Cross-Epic Dependencies
Dependency | Needed For | Likely Owner
payment_type/payment_memo columns, NOT-NULL relaxation, C13 mapper, installment PATCH (flip + audit + gate) | 24.7-a, b, c, d, e | 24.8 (SBE-1132) — same release, builds immediately before 24.7
Downstream readers (NOT dependencies): 24.15 stop-condition (PT.status at send time); 24.10-g (manual representation for cancel/refund marking) | — | —

## Implementation Status
Section | Detail
Status | Not started — Step-1 gate complete 2026-07-03; scope locked (order-level PATCH dropped per D3; write side covered by 24.8; both old open questions resolved via 24.8-c). Release model: ship-together; builds after 24.8.
Branch | —
SBE ticket | SBE-1131 (In Progress, Prantik Saha)
Commits | —
PR | —
Swagger tag | —
Build gates | —
Live smoke | —
Confirmed build scope | GET /orders/:id/payments (C13 mapper reuse + per-installment payment_memo + derived Paid/Unpaid label) + orders.payments.read seed + Swagger registration
Remaining | The one route unbuilt
Not ready — see Open Questions | none — register empty
External dependencies — see Cross-Epic Dependencies | 24.8 (mapper + payment_type + PATCH) — same release, builds first
Out of API scope | Payments screen FE wiring, status-toggle UI